|  |
| --- |
|  5 th CIRCLE - PALAMPUR |
| Sr. No  | Job No.  | Name of Project | Date of receiving site Plan  | Date of requirments  | Date of issue of Drawings | Date of feasibility  | Date of approval | Status of Project  | Status Supplied by SE.  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
|  SCHOOLS |
| 1 | 105 | Additional Accommodation for GSSS at Salol, Distt. Kangra. | 21/1/2012 | 21/1/2012 | 4/2/2012 Sketch Drawing 9/12/2013 Working Drawing  | 4/9/2013 | 9.12.2013 | 95% work completed |   |
| 2 | 105 | Additional Accommodation for GSSS at Baroh, Kangra. ( Science Lab) | 11/8/2014 | 11/8/2014 | 22/9/2014 Working drawings 30-12-2015 working drawings  | 02.04.2014 | Std. drawing | Coloumns raised upto 2 mtr. height of 1st floor. | Work is in progress |
| 3 | 105 | Additional Accommodation for GSSS at Serathana, Nagrota Bagwan. | 23/9/2014 | 22-9-2014 | 30-12-2014 working drawing  |   |   | Under construction  |   |
| 4 | 105 | Multipurpose Hall at Khaira, Palampur. | 13/10/2014 | 13/10/2014 | 23/12/2014 Sketch Drawing 20.07.2017 revised working drawings | 9/3/2016 | Awaited | Work in progress. 90% work completed. |   |
| 5 | 105 | Science block in Govt. GSSS at Pathiar, Nagrota Bagwan. | 21-08-2015 | 21-08-2015 | 21/10/2015 Layout and working drawing 04-02-2016 working drawing ( Standrad design Model -B) | 5/1/2016 |   | funds awaited |   |
| 6 | 105 | Stage for Govt. S S School at Bhawarna, Palampur. | 12/10/2015 | 29-9-2015 | 21/10/2015 Sketch drawings 27.01.2017 working drawing | 5/3/2016 |   | A/A & E/S & funds not received. |   |
| 7 | 105 | Additional accommodation for GSSS at Baroh and Serathana. | 12/12/2015 | 12/12/2015 | 30-12-2015 working drawing  |   |   |   |   |
| 8 | 105 | Science Lab. For GSSS at Alampur | 6/3/2016 | 6/3/2016 | 17-03-2016 working drawing | 5.3.2016 |   | A/A & E/S accorded by ACS (Edu) to HP Govt. vide letter No. EDN-B-Ga (1)-1/2015-Loose dt. 24.9.2015 for Rs. 536.02 lacs as per Architect Drg. No. 268 Job . 3303. 40% work completed |  (Deposit Works) |
| 9 | 105 | Adminstrative block and multi purpose hall in Govt. SSS at Pathiar | 27-02-2016 | 26-03-2016 | 29-03-2016 revised layout plan na d sketch drawings  | 30.3.2017 |   | funds awaited |   |
| 10 | 105 | Govt SSS at Samloti, Nagrota Bagwan | 13.01.2017 | 10.01.2017 | 17.02.2017 sketch drawing | 8/3/2017 | Awaited | Working estimate under preparation  |   |
| 11 | 105 | Additional Accommodation for GSSS at Thural | 08.06.2016 | 08.06.2016 | 18.08.2016 Layout plan and working drawing |   |   |  2 No. rooms under RMSA is in progress at proposed site as per standred drawing. |   |
|  COLLEGES |
| 12 | 4808-A | IT cum Management Block for Govt. College at Dharamshala. | 19/4/2012 | 19/4/2012 | 27/8/2012 Sketch Drawings 15/2/2013 Working Drawings  | 10.10.2012 | 15/11/2012 | Funds awaited |   |
| 13 | 4808-A | Science Block in Govt. College at Dharamsala. (New Site). | 25-2-2015 | 25/2/2015 | 7-8-2015 sketch drawings 15.02.2016 working drawing | 4/9/2015 | 5/10/2015 | Under construction  |  (Deposit Works) |
| 14 | 4808-A | Department of performing arts in Govt college at Dharamsala | 18.08.2016 | 17.08.2016 | 03.10.2016 sketch drawing 21.06.2017 Revised sketch drawing | 15.07.2017 Structural feasibility | 28.10.2017 | Working drawings awaited |   |
| 15 | 336 | Govt Degree College Lunj, Kangra | 19.03.2016 | 15.03.2016 | 30.06.2016 Sketch drawing | 03.09.2016 | 17.08.2016 | Work in progress. |   |
| 16 | 355 | Govt Degree College at Matour, Kangra | 17.05.2017 | 11.05/2017 | 12.07.2017 sketch drawing | Awaited from Assistant Engineer HP.PWD Kangra  | - | - | Feasibility report awaited from A.E. HPPWD Kangra.  |
| 17 | 349 | Additional Accommodation for Govt Degree College at Baroh | 19.10.2016 | 18.10.2016 | 12.04/2017 sketch drawings 04.07.2017 working drawings | 31.05.2017 | 02.05.2017 | Working estimate under preparation  |   |
| 18 |   | Auditorium in D.I.E.T Dharamsala | 17.08.2016 | 07.11.2016 |   |   |   | Contour site plan under preparation |   |
|  HP BOARD OF SCHOOL EDUCATION DHARAMSHALA |   |   |   |   |
| 20 | 3252-A | Community Hall at Chilgari  | 28/11/2011 | 28/11/2011 | 31/12/2011sketch drawing  |   | 26/6/2012 | Estimate submitted to concerned department for funds deposit. The concerned department return the estimate with the remarks that the work could not be executed. |   |
| 19 | 3252-A | Community Hall Near Shivaji Temple at HP BOSE Colony Sidhpur, Dharamshala. | 29/10/2014 | 29/10/2014 | 28/2/2015 sketch Drawings 5/6/2015 Revised sketch drawing 06/07/2016 Working drawings | 03.10.2015 | 24/8/2015 |   |
|  |  |  |  |  |  |  |  |  |  |
|  TECHNICAL EDUCATION |   |   |   |   |   |   |
| 20 | 338 | Govt ITI Nagrota Bagwan at Serathana | 18-7-2016 | 18-7-2016 | 09-8-2016 Sketch drawings 24.10.2016 working drawing | 28.09.2016 | 01.10.2016 | Work in progress |   |
| 21 | 358 | ITI buildings at Baijnath | 26.07.2017 | 22.07.2017 | 28.09.2017 sketch drawings | 22.7.2017 | 28.9.2017 |   | Feasibility report stand submitted to Chief Architect D/shala. Working drawing awaied. |
| 22 |   | State of Art ITI Nagrota Bagwan at Baldhar | 15.09.2017 | 20.07.2017 |   |   |   | Contour site plan submitted and working drawings under preparation |   |

|  |  |  |
| --- | --- | --- |
| OFFICE OF THE SENIOR ARCHITECT (SOUTH ZONE) HP PWD SHIMLA |  |  |
| LIST OF WORK EDUCATION (COLLEGES) |  |  |
|  5 th CIRCLE - PALAMPUR |  |  |
| Sr. No  | Job No.  | Name of Project | Date of requirments received | Date of receiving site Plan & details | Date of sketch drawing issued | Date of approval | Date of feasibility  | Status of Project  | Remarks |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |
| 23 | 8116 | C/O Govt College Takipur Distt Kangra | EDN-H (9)2-38/2015 GC/ Takipur Dated 17/8/2015 | Contour site plan received for Executive Engineer HP.PWD Kangra vide letter No 1418-22 dated 6/10/2015.  |   | E.E.Kangra Division letter no 1786-89 Dated 1-12-2015.Letter received from E.E. Kangra vide no 18001-04 dated 21/12/2015  | Layout plan & working drawing along with specification issued vide letter no 2767 -70 dated 10/11/2016 | On going work  | (Deposit Works) |  |  |
| 24 | 7901 | C/O Govt. College Jaisinghpur (Science Block) |   |   |   |   | A/A & E/S accorded by Pre. Secy. (Higher Edu.) vide letter No. EDN-A –C (17)- 04/2009 dt. 27.9.2016 for Rs. 338.90 lacs As per Architect drawing No. 37, 38, 39, 40 Job No. 7901. 2 Nos slab laid and form work of ceiling slab is in progress.  | On going work  |   |  |  |
| 25 | 7794 | C/O Govt College Palampur (Vikram Batra) BBA-BCA block  |   |   |   |   | Regarding BCA-BBA-BlockE.E.Palampur Letter No 15509-13 dated 24-9-2015 | Revised Architectural drg. Awaited as desired by design wing of Chief Office (KZ) | (Deposit Works) |  |  |
| 26 | 8049 | C/O Engineering College Nagrota Bagwan Kangra | No. STV(TE) HG(2) 2014/ 69576 dated 11.4.2017 |   | Approval received from Director Technical education vide letter no 27657 dated 7/4/2016 |   | Admn. Block Electrical Engg. Block, Caterair, complex & Library Block | On going work  |  (Deposit Works) |  |  |
| 27 | 8163 | C/O B. Pharmacy Govt. College Nagrota Bagwan ( Academic Block& Admn. Block) Distt. Kangra |   | 1488-90 dated 6.7.2016 |   | 1953-54 dated 5.8.2016 | Layout plan & drawing alongwith specification issued vide leter No. 1879-82 dated 31.8.2016. | Work is in Progress work  |   |  |  |
| 28 | 7904 | C/O Govt Degree college Nohra Sub the Dhera Distt Kangra (Science Block ) |   | Contour site plan received from E.E. Palampur vide letter no 30604-07 dated 3/3/2016 |   | 6629-32 dated 16/7/2016 | Layout plan & working drawing along with specification issued vide letter no 1107-09 dated 25/6/2016 | Technical bid opened and financial bid shall be open on or before 20.2.2018 |   |  |  |
| OFFICE OF THE SENIOR ARCHITECT (SOUTH ZONE) HP PWD SHIMLA |  |  |
| LIST OF WORK EDUCATION (SCHOOL) |  |  |
|  5 th CIRCLE - PALAMPUR |  |  |
| Sr. No  | Job No.  | Name of Project | Date of requirments received | Date of receiving site Plan & details | Date of sketch drawing issued | Date of approval | Date of feasibility  | Status of Project  | Remarks |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |
| 29 | 6595 | C/O Govt Sr. Sec. School Tambar Tehsil Jaisinghpur |   | 5524-25 dated 7.7.2017 |   |   |   | A/A & E/S accorded on Drawing No. 82 & 83 Job No. 105 & Tender called & awarded  |   |  |  |
| OFFICE OF THE SENIOR ARCHITECT (SOUTH ZONE) HP PWD SHIMLA |
| LIST OF WORK (others)ITI |  |  |
|  5 th CIRCLE - PALAMPUR |  |  |
| Sr. No  | Job No.  | Name of Project | Date of requirments received | Date of receiving site Plan & details | Date of sketch drawing issued | Date of approval | Date of feasibility  | Status of Project  | Remarks |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |  |
| 30 | 297 | I.T.I Daluatpur Distt Kangra  | 19-11-2013 | 29-1-2014 | 29-1-2014 | 3/3/2014 | Work completed  | - |  (Deposit Works) |  |  |
| 31 | 8160 | C/O I.T.I building at Nagrota Bagwan Distt. Kangra | …. | 16.7.2017 |   | …… | 28.9.2016 | Drawing issued for approval ( Architect Dharamshala) on dated 9.8.2016. | On going work  |  |  |
| 32 | 7701 | Polytechnic Talwar Distt. Kangra |   |   |   |   | Revised preliminary estimate submitted to Director Tech. Edu Sundernagar vide CE (KZ) Dharamshala letter No. 5033-37 dt. 22.2.2018 for Rs. 410.83 lacs as per architect drawing No. 46/4 Job No. 7701 & drawing No. 11 Job No. 4170-B.  | On going work  |  (Deposit Works) |  |  |
| 33 |   | C/O I.T.I Baijnath Distt. Kangra | 26.7.2017 | 22.7.2017 | 28.9.2017 stetch drawing  | 28.9.2017 | 22.7.2017 |   | Feasibility report stand submitted to Chief Architect D/shala . Working drawing awaited. |  |  |
| 34 | 7701 | I.T.I Balakrupi |   |   |   |   | Revised Preliminary estimate based on Drawing No. 47/1, 62, 84 to 89 Job No. 7701 for Rs. 70371900/- submitted to SE 5th Circle Palampur vide this letter No. 14109-11 dt. 22.12.2017. Working estimate approved for Rs. 30029764/- & DNIT under preparation |   |  (Deposit Works) |  |  |

Note :- Red portion shows deposit works Which are not counted in Total Projects.