|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BUILDING WORKS OF VETRINERY DISPERSARY (ONGOING PROJECTS) | | | | | | | | | |
| 5 th CIRCLE - PALAMPUR | | | | | | | | | |
| Sr. No | Job No. | Name of Project | Date of receiving site Plan | Date of requirments | Date of issue of Drawings | Date of feasibility | Date of approval | Status of Project | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
|  |  |  |  |  |  |  |  |  |  |
| 1 | 329 | Office for Deputy Director Animal Health Kangra at Dharamshala. | 28/8/2015 | 29/8/2015 | 03.03.2016 Sketch drawing | Awaited | Awaited | Drawings awaited |  |
| 2 | 4145 | Sub- Divisional Veterinary Hospital at Palampur Distt. Kangra | 27-04-2016 | 25-04-2016 | 24.11.2016 Sketch drawings | Awaited | Std. drawing | Tender to be invited. |  |
|  |  |  |  |  |  |  |  |  |  |
| BUILDING WORKS OF POLICE AND JAIL DEPARTMENT (ONGOING PROJECTS) | | | | | | | | | |
| 5th CIRCLE- PALAMPUR | | | | | | | | | |
| Sr. No | Job No. | Name of Project | Date of receiving site Plan | Date of requirments | Date of issue of Drawings | Date of feasibility | Date of approval | Status of Project | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 3 | 256 | SP Office , SV and ACB, NR, including Distt. Attorney and PS building at Dharamshala. | 13/3/2009 | 16/3/2009 | 21/1/2010 Sketch drawing | 5/2/2010 | Awaited | Funds awaited |  |
| 4 | 284 | Office buildng for Inspector General of Police (NR) at Dharamshala. | 4/3/2011 | 4/4/2011 | 28/7/2012 Sketch Drawing | Awaited | Awaited |  | Project assigned to HIMUDA |
|  |  |  |  |  |  |  |  |  |  |
| 5 | 256 | Up- gradation of Netaji Subhash Chander Bose Police Ground at Dharamshala . | 21/5/2014 | 21/5/2014 | 10/11/2014 revised layout and working drawings. | 7/11/2014 | 08.09.2014 | Reuirement of concerned department changed and estimate re-submitted and A/A & E/S awaited |  |
| 6 | 317 | Barracks for 60 No. Lady Prisoners in Open air jail Distt. Jail at Dharamshala. | 30/7/2014 | 30/7/2014 | 17/3/2015 Sketch Drawing 07/11/2015 working drawings | 23-5-2015 | 15/5/2015 | work in progress |  |
| 7 | 331 | 9/7 Home Guard campany building Palampur Near Maranda . | 13/1/2016 | 11/1/2016 | 26-04-2016 Layourt plan and Sketch drawing | Awaited | Awaited | A/A & E/S awaited. |  |
| 8 | 317 | Administrative Block for Open Air Jail Complex at Dharamshala | 7/5/2016 | 19.11.2016 sketch drawings | Awaited | Awaited | Feasiblity awaited |  |  |
|  |  |  |  |  |  |  |  |  |  |
| 9 |  | Fire post cum residence building at Baijnath | 13.12.2016 | 06.12.2016 |  |  |  | Information awaited | Site not handed over to PWD by the concern deptt. |
|  |  |  |  |  |  |  |  |  |  |
| BUILDING WORKS OF GAD DEPARTMENT (ONGOING PROJECTS) | | | | | | | | | |
| 5 th CIRCLE - PALAMPUR | | | | | | | | | |
| Sr. No | Job No. | Name of Project | Date of receiving site Plan | Date of requirments | Date of issue of Drawings | Date of feasibility | Date of approval | Status of Project | Remarks |
| 10 | 242 | PWD Rest House at Jaisinghpur. | 31/5/2008 | 31/5/2008 | 11/12/2008 Sketch drawing 8/6/2009 Revised sketch 17/9/2009 Working Drawing | 24.07.2009 | Awaited |  |  |
| 11 | 237 | PWD rest at Behru Jakh Baba at Palampur. | 6/6/2008 | 6/6/2008 | 11/12/2008 working Drawing |  |  |  | The proposal for C/O rest house was rejected by the Principal Secretary (PW) to the Govt. of H.P. vide Engineer-in-Chief letter No. PWD/(R)-7-A-9 (MZ) 14093-94 dated 28.3.2009. Now it was decided to construct inspection hut at Behru Jakh Baba. However the matter is being taken for the prioritizing during the financial year 2013-14 but the same is not get till date. |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
| 12 | 217 | Office building for SE. Elect. 2nd Circle, HP PWD Dharamshala. | 27/6/2014 | 27/6/2014 | 11/12/2014 Sketch Drawing 19.11.2016 Layout plan (revised) & working drawings | 28/11/2015 |  | Work in progress |  |
| 13 | 306 | Office building for SE. Mech Circle, HP PWD Dharamshala. | 24/5/2014 | 24/5/2014 | 10/11/2014 Sketch Drawing 29.11.2016 working drawing | 28.01.2015 |  | Work in progress |  |
| 14 | 204 | Sub-Tehsil building at Harchakian. | 10/1/2014 | 23/9/2014 | 11/11/2014 working drawing | Awaited | Std. drawing |  |  |
| 15 | 308 | Additional Accommodation for Rest House at Dharamshala. | 3/11/2014 | 3/11/2014 | 10/12/2014 Sketch drawing | Awaited | Awaited | A/A & E/S awaited |  |
| 16 | 316 | Mini Sectt. at Nagrota Bagwan, Kangra. | 17/1/2015 | 17/1/2015 | 6/6/2015 sketch drawing 03.09.2016 working drawings | 14/10/2015 | 03.09.2015 | Work in progress |  |
| 17 | 318 | Sub- Treasury building with residence at Dheera | 28.08.2015 | 24/8/2015 | 10.08.2016 Working drawings |  | Approved drawings | site changed & site plan awaited | Land not available as per requirement of concerned department. |
| 18 | 204 | Sub- Tehsil building at Darini, Shahpur. | 10/11/2015 | 7/11/2015 | 31-03-2016 Sketch drawing 17.08.2016working drawing | 20-4-2016 | 31/3/2016 | Work in progess. |  |
| 19 | 360 | Executive Engineer Office building, HP PWD Jaisinghpur | 22.09.2017 | 22.09.2017 | 17.11.2017 sketch drawings | Awaited | Awaited |  |  |
| 20 | 204 | Sub Tehsil office at Chadhiar, Baijnath | 31.05.2017 | 27.05.2017 |  | 29.1.2018 |  | Revised site plan awaited |  |
| 21 | 357 | Divisional store for Medical College Division HP PWD Tanda | 15.07.2017 | 13.07.2017 | 29.09.2017 sketch drawings | 21.11.2017 |  |  |  |
| 22 | 217 | Type-V residence for SE Mech. And SE Elect. Circle at Chilgari, Dharamsala | 26.06.2014 | 26.06.2014 | 04.10.2016 Working drawings | Awaited | Std. drawing | SE Mech residence work is in progress and SE Elect residence A/A & E/S awaited |  |
| 23 | 217 | Type-V residence for Senior Architect (KZ) at Chilgari, Dharamsala | 26.06.2014 | 26.06.2014 | 04.10.2016 Working drawings | Awaited | Std. drawing | Work in progress |  |
| BUILDING WORKS OF MISC. DEPARTMENTS (ONGOING PROJECTS) | | | | | | | | | |
| 5 th CIRCLE - PALAMPUR | | | | | | | | | |
| Sr. No | Job No. | Name of Project | Date of receiving site | Date of requirment | Date of issue | Date of feasibility | Date of approval | Status of Project | Remarks |
| 24 | 7850-A | Toilet in the Vidhan Sabha premise at Tapovan Dharamshala. | 3/2/2011 | 3/2/2011 | 28/7/2011 Working Drawing |  |  | Project dropped | Proposal pending |
| 25 | 296 | Office of the Deputy Director Sainik Welfare Kangra at Dharamshala. | 25/7/2012 | 25/7/2012 | 5/12/2013 Sketch Drawing | 23/6/2014 |  | Approval awaited |  |
| 26 | 248 | Dr. B.R Ambedkar Bhawan at Kharat. | 7/3/2012 | 7/3/2012 | 18/5/2013 Sketch Drawing | 19/6/2013 | Awaited | Masonry work completed | Work is in progress |
| 27 | 304 | Office and multi Gym Block for SAI Complex at Dharamshala. | 30/7/2014 | 30/7/2014 | 21/10/2014 sketch drawing | Awaited | Awaited |  |  |
| 28 | 303 | E.T.O. Office at Kangra. | 29/3/2014 | 2/4/2014 | 10/9/2014Sketch drawings 15/10/2015 working drawings. | 9.1.2015 |  |  |  |
| 29 | 355 | Press Club building at Dharamsala |  |  |  |  |  | Letter recived from Ar L.M.Mastana Dharamshala & feasibility awaited | 299 dated 1/9/2017 |
| 30 | 325 | Jorawar Singh stadium at Sidhbari, Dharamsala | 22.09.2017 | 20.09.2017 |  | 15.01.2018 |  | Feasibility submitted to Sr Arct. Vide t/o letter No 20.02.2018 |  |
| 31 | 326 | Kalyan Bhawan at Rait, Shahpur | 16-2-2016 | 6/2/2016 | 31-3-2016 Layout plan and Sketch drawings | 23.08.2016 | 22/9/2016 | Work in progress |  |
| 32 | 337 | Multipurpose Hall at Kangra | 30.11.2015 | 26.11.2015 | 05.7.2016 Working drawings | 6/2/2016 | 5/7/2016 | Work in progress |  |
| 33 | 6600-A | Museum & Memorial for Freedom Fighters of HP at Dari, Dharamsala | 21.11.2016 | 19.11.2016 | 23.09.2017 sketch drawings | Awaited | Awaited | Requirement awaited |  |
| 34 | 303 | Residences for Excise and taxation at Palampur | 15.05.2017 | 09.05.2017 |  |  |  | Contour site plan for approval of layout plan and evolving working Drg. Sent to the Sr. Architect HPPWD D/shala vide letter No. 2079-81 dated 9.5.2017. |  |
| 35 | 7028-A | Stadium at Rait, Teh-Shahpur | 23.02.2006 | 23.05.2017 (Revised) | 12.07.2017 revised working drawings (Pavilion block) | 28/6/2017 | 12/7/2017 | Work in progress |  |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| OFFICE OF THE SENIOR ARCHITECT (SOUTH ZONE) HP PWD SHIMLA | | | | | | | | | |
| LIST OF WORK (OTHERS) Rest Houses | | | | | | | | | |
| 5 th CIRCLE - PALAMPUR | | | | | | | | | |
| Sr. No | Job No. | Name of Project | Date of requirments received | Date of receiving site Plan & details | Date of sketch drawing issued | Date of approval | Date of feasibility | Status of Project | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 36 | 7740 | Propossal for C/O PWD Rest House at Jagroop Nagar, Jaisinghpur Kangra (HP) |  | Vide letter No. 5944-46 dated 3.9.2016 |  |  |  | Fresh proposal sent to CE (KZ) D/Shala vide SE Palampur this office letter No. 7915-17 dt. 22.12.2017 Funds not available. |  |
| 37 | 7750 | C/O Proposed Circuit House at Palampur Distt. Kangra (HP). | Vide letter no . 11283-86 dated. 21/09/2016. | Vide letter no . 11283-86 dated. 21/09/2016 . From EE, P/Pur. Div. vide letter no 10632-35 dated. 08/09/2016. |  |  |  | Revised plan,and working drawings sent to EE, Palampur Division vide letter no 3834-37 dated 24/01/17.Work is in progress. |  |
| OFFICE OF THE SENIOR ARCHITECT (SOUTH ZONE) HP PWD SHIMLA | | | | | | | | | |
| LIST OF WORK (OTHERS)Stadium | | | | | | | | | |
| 5 th CIRCLE - PALAMPUR | | | | | | | | | |
| Sr. No | Job No. | Name of Project | Date of requirments received | Date of receiving site Plan & details | Date of sketch drawing issued | Date of approval | Date of feasibility | Status of Project | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 38 | 4787 | C/O Stadium Jaisinghpur Distt. Kangra HP |  |  |  |  |  | Proposal layout plan desired by Director sports & sent vide this office letter No. 5385-86 dt. 5.7.2017 Approval is awaited. | On going work |

Note :- Red portion shows deposit works Which are not counted in Total Projects