|  |
| --- |
| LIST OF WORK (Health Department )  |
|  5 th CIRCLE - PALAMPUR |
| Sr. No  | Job No.  | Name of Project | Date of requirments received | Date of receiving site Plan & details | Date of sketch drawing issued | Date of approval | Date of feasibility  | Status of Project  | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1 | 3493 | C/O new proposed building at Civil hospital palampur.  | Vide letter no 21906-09 dated 31/01/2017 |   |   | Vide letter no. Swa-Pa-Ka-(Mukhya)(4)..K-57/91-13131 dated 03-04-2017 |   | Drgs. Sent to Sr. medical officer, Civil hospital kangra distt. Kangra (HP) vide letter no 4344-48 dated 28/02/2017. Work is in progress. |   |
| 2 | 3390 | C/O 100 bedded indor ward at CHC Jaisinghpur  |   |   |   | vide letter No. 195-97 dated 22.4.2017 |   | Community Health Centre Jaisinghpur was upgraded to 50 bedded Civil Hospital. The preliminary estimate for 50 bedded Civil Hospital was sent to the Additional Chief Secretary (Health) to Govt. of HP by Director health service Shimla vide his office letter No. Swa- pa- ka- mukhya (4) K- 57/91 – 4794 dated 11.2.2015 amounting to Rs. 44551100/- only to accord of A/A & E/S. in the mean times 50 bedded bas been upgraded to 100 bedded vide Additional Chief Secretary (Health) Notification No. H-A- F – (4) 5/2013- Loose dt. 28.10.2015. **Again the Governor** of HP is pleased to reduce the capacity of 100 bedded Civil Hospital Jaisinghpur to 50 bedded Civil Hospital as conveyed vide Principal Secy. (Health) to Govt. of HP. Notification No. Health – A- F (4) – 5/2013 – Loose dated 4.7.2017. The reminder letter sent to Director health service Shimla vide this office letter No. 24708-12 dt. 28.10.2017 for arranging A/A & E/S |  |
| 3 | 7347 | Site plan i/c requirement of mother child hospital in Dr. R.P.G.M.C. Tanda | Vide letter No.3761-64 dated 7.11.2016 & vide letter No. 5039-41 dated 11.1.2017. | Vide letter No.3761-64 dated 7.11.2016 & vide letter No. 5039-41 dated 11.1.2017. |   | Date of approval awaited from Chief Arch. Vide T/O leeter No. 429-31 Dated:- 3.5.2017 | Vide letter No. 2931 dated 18.11.2017 as per revised working drawing vide letter No. 10152-55 dated 23.2.2018 | EE Medical division requested to supply site plan in the scale 1:200 vide letter No. 3678-80 dated 9.1.2017 Layout plan & floor wise plans sent to the Principal Health servises HP Shimla-9 vide letter No. 2163-68 dated 31.8.2017. |   |
| 4 | 7347 | Detail of Doors, windows & vents for MBBS Hostel for 60 boys/girls of Dr. R.P.G.M.C. Tanda Kangra |   |   |   |   |   | Detail of joinery ( Doors, windows & vents) detail of joints supplied to EE Medical College Division HPPWD, Tanda vide letter No. 3431-34 dated 21.12.2016  |  (Deposit Works) |

|  |
| --- |
|  BUILDING WORKS OF HEALTH DEPARTMENT (ONGOING PROJECTS) |
|  5 th CIRCLE - PALAMPUR |
| Sr. No  | Job No.  | Name of Project | Date of receiving site Plan  | Date of requirments  | Date of issue of Drawings | Date of feasibility  | Date of approval | Status of Project  | Remarks |
|   | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 5 | 3056 | Meeting Hall & Guest House in Eye Mobile Unit at Zonal Hosp Dharamshala | 14.10.2016 | 13.10.2016 | 27.12.2016 Sketch drawing | 26.10.2017 | 18.10.2017 | Funds awaited |   |
| 6 | 3056 | Distt. Store for Zonal Hospital Dharamsala | 20.02.2017 | 20.02.2017 | 14.08.2017 working drawings | 15.07.2017 | 09.08.2017 | Work in progress |   |
| 7 | 114 | Distt Ayurvedic Store & Hall at Dharamsala | 01.02.2017 | 01.02.2017 | 25.04.2017 sketch drawings 01.09.2017 working drawings | 11.07.2017 | 25.08.2017 | Work in progress |   |
| 8 | 156 | Staff Quarters for Civil Hospital Baijnath (Addl./Alterations Sarai Buildings) | 18.03.2016 | 11.03.2016 | 08/9/2016 Working drawings | 11.3.2016 | 8.9.2016 |   | 85% work completed remaining is in progress. |
| 9 | 3390-A | Meeting Hall for CHC at Nagrota Bagwan. | 29/11/2013 | 29/11/2013 | 22/2/2014 Sketch drawing 12/1/2015 working drawing  | 7/7/2014 | 17/6/2014 |   |   |
|  |  |  |  |  |  |  |  |  |  |
| 10 | 3390-A | CHC building (50 bedded) at Dheera, Distt. Kangra | 30-11-2015 | 24-11-2015 | 12/7/2016 sketch drawing 17.3.2017 working drawing | 02.08.2016 | 16.11.2016 | A/A & E/S awaited. |   |
| 11 | 3390-A | Health Institution level- II at Ropri Distt. Kangra | 12/2/2016 | 6/2/2016 | 6-5-2016 layout plan & working drawing  | 6.2.2016 | 6.5.2016 | Work in progress | work is in progress.(Deposit Works) |
| 12 | 3390A | Additional block for newly upgraded 50 bedded civ hosp at Shahpur | 19.09.2017 | 18.09.2017 | - | - | - | Comprehensive site plan sent to Sr. Architect D/Shala on dated 26/2/2018 for Architectural drawing.  |   |
| 13 | 3390A | Additional accommodation for newly upgraded 50 bedded civil hospital at Nagrota Bagwan | 19.09.2017 | 18.09.2017 |   |   |   | Contour site plan submitted and working drawings under preparation |   |
| 14 | 3390A | CHC building at Khaira, Palampur | 06.04.2017 | 24.03.2017 |   |   |   | Information awaited. Such type of correrspondence not received form the Medical Deptt. |   |
|  Dr. Rajendra Prasad Medical College Kangra at Tanda |
| 15 | 7347-A | Sarai Building for 100 persons at Dr. RPGMC Tanda at Kangra. | 7/3/2010 | 7/3/2010 | 16.09.2015 sketch drawing 13.07.2016 working drawing | 11.05.2016 | Working drg. 12/7/2016 | Tender under process |   |
| 16 | 7347-A | School of Nursing for Dr. RPGMC Kangra at Tanda  | 29-2-2016 | 26-2-2016 | 26-4-2016 Layout and sketch drawings | 482-85 dated:- 17/5/16 | Awaited | A/A & E/S awaited |   |
| 17 | 7347A | Bone Clinic in Dr. RPGMC Tanda | 22.04.2016 | 21.04.2016 | 27.12.2016 Sketch drawing 20.02.2017 working drawings | 09.01.2017 | 20.01.2017 | Site changed |  (Deposit Works) |
| 18 | 7347-A | Centre of Excellence in Mental Health for Dr. RPGMC Tanda | 20.02.2017 | 17.02.2017 | 02.06.2017 sketch drawings 16.8.2017 working drawings | 15.07.2017 | 20.06.2017 | Tender under process |   |
| 19 | 7347-A | Geriatric Centre, Skill Development Centre, Bone Clinic & Canteen for Dr. RPGMC Tanda | 11.07.2017 | 10.07.2017 | 02.8.2017 sketch drawings 16.11.2017 working drawings | 28.10.2017 | 25.08.2017 | A/A & E/S awaited |   |
| 20 | 7347-A | Trauma Centre Level-I at Dr. RPGMC Tanda | 10.07.2017 | 10.07.2017 | 02.8.2017 sketch drawings | plan changed drawing not processed | 25.08.2017 | A/A & E/S awaited |   |
| 21 | 7347-A | Sports Complex for Dr. RPGMC Kangra at Tanda | 19.06.2017 | 13.06.2017 |   |   |   | Requirement awaited from concerned deptt. |   |

Note :- Red portion shows deposit works Which are not counted in Total Projects