**LIST OF WORK (8TH CIRCLE HAMIRPUR) EDUCATION DEPARTMENT**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received-** | **Date of receiving site plan & details** | **Date of approval** | **Date of feasibility** | **Status of project** | **Status of Projects Supplied by SE.** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** |
| 1. | 6673 | Renovation & Modernization of Existing Mess kitchen & Cold Storage room in kitchen)at Sainik School Sujanpur |  | 21160-62 dated 19/1/2015  Photo graphs & cross section received vide letter no 13369-70 dated 24/9/2015 |  |  | Letter issued to EE Hamirpur vide letter no 2173-75 dated 17/8/2015 regarding cross section & photo grapes of the site along with site plan -  Drawing no 94 issued for approval vide letter no 4705-08 dated 25/3/2017 | Working Estimate under Process in Sub-Division. |
| 2 | 6673 | C/O Stadium at Govt. Sr. Sec. School at Amroh. |  | 27.11.09 vide letter No. 15987-90 |  | 29.09.10 vide letter No. 10050-54 | Sketch drgs. Issued along with layout on dt. 15.07.10 vide letter No. 1562-63  **\***  Working drgs. Issued on dt. 21.03.11 vide letter No. 5505-07 | Estimate submitted to Principal G.S.S.S Amroh vide EE letter No. 25497-98 dated 3-3-2014. |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | 6673 | C/O Distt.Library Hamirpur Distt. Hamirpur (Indira Gandhi District Library Hamirpur) | NO EDN-H(9)5-2/2010 dated 04.11.11 | 14.02.12 vide letter No. 18903-05 | 13.11.12 vide letter nill Director of High Education of HP. | Vide letter No.2538-42 05.05.12 . | \* Working dgrs.of Distt. Library issued vide letter No. 2185-86 dt. 21.07.14  528-29 dated 12/5/2016  Letter issued  Drawing issued (flooring pattern issued ) | Work is in progress |
| 4 | 6673  (II) | C/O Govt Sr Sec School Bhukkar Distt Hamirpur  (Additional Accommodation 6 nos class Room with verandah & stair case) | Endst. No –Nill dated 19/11/2015 | 4422-23 dated 12/2/2016 |  |  | E.E. Hamirpur vide letter no 34267-69 Dated16/2/2016  Working Drawing along with specification issued for approval vide this office letter no 5223-26 dated4/3/2016 | Work is in progress. |
|  |  |  |  |  |  |  |  |  |
| 6 | 6673 | Library building in Govt. Sr. Sec. School Baldhuak | Photocopy of the Principal Govt. Sr. Sec. School Baldock received vide office letter No. 851 dt. 06.04.13 | 29.05.13 vide letter No. 3096-98 from Director of High Education of HP  Contour site plan received from E.E Hamirpur Vide letter no 26990-92 dated 29/3/2016 |  |  | **\*** Sketch drawing issued vide letter No. 2969-72 dt. 28.11.13  **\*** Working drgs. Issued on dt. 21.08.14 vide letter No. 2185-86  Layout plan, working drawing along with specification issued vide letter no 4059-61 dated 8/2/2017 | Tender under process. |
| 7 | 6673 | Indoor shooting range in Sainik School Sujanpur Tihra | 04.04.14 vide letter No. 608/Q/SR received from Principal Sanik School Sujanpur Tihra Distt. Himarpur | Dt. 17.02.14 vide letter No. 24483-85  Letter recived from E.E, Hamirpur that the public of Sujanpur area has of object for the construction of indoor shooting range and subject an other site vide letter no 7896-99 dated 23/8/2014  **\*** Revised site plan layout received vide letter No. 10753-54 on dt. 23.09.14 | No.SSST/608/Q/SR dt. 05.05.15 | 789696-99 dated23/7/2014  16318-20 dated 8/12/2014 | Sketch drgs. Issued on dt. 19.06.14 vide letter No. 1124-26    sketch drgs and layout issued on dt. 28.10.14 vide letter No. 3075-77  Working drawing along with specification issued vide letter no 1866-69 dated 31/8/2016 | Estimate under process in Sub-Division Office. |
|  |  |  |  |  |  |  |  |  |
| **9** | **6673** | **C/O Science Lab in Govt Sr sec school (Girls) Hamirpur** |  | 3547-50 dated 22/5/2015 |  |  | Revised drawing no 76 to 78 issued for approval vide letter no 1589-93 dated 13/7/2015 | Tender under process in this office. |
| **10** | **6673** | **Additional Accommodation of NCC office at Hamirpur** |  | 21707-08 dated 20/2/2016 |  |  | Layout plan & working drawing along with specification issued vide letter no 5536-39 dated 28/3/2016 | Tender under process in Divisional office. |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **+List of Work Education 8th Circle Hamirpur** | | | | | | | | |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval** | **Date of feasibility** | **Status of project** |  |
| 1 | 7753 | C/O Govt Degree College Tarkwari Bhoranj.(Canteen Block) | No EDN-H (9) 3-4/2004 Dated 25/10/2008  (Provision of college canteen, Two Computer Lab,exit gate,(Emergency gate) from the Science Block ) | 3028-30 dated 24/6/2009 (Canteen Block) | NO EDN (9)5-24/2007 dated20/8/2009  (canteen Block) | 2958-59 dated 20/6/2009 (Auditorium Block )21966-68 dated 2/3/2010 (canteen Block ) | (kitchen detail ) issued vide letter no 1283-85 dated 5-7-2017 | Work is in Progress. |
| 2 | 3871 | Vertical Design & estimate for cluster class room under RUSA Grant (Govt Degree College Hamirpur) |  | 20038-41 dated 27/1/2016 | NO EDN HE(9)5-2/2016-17 dated 16/8/2017 | . | Layout plan ,working drawing along with specification issued vide letter no 1672-75 dated 29/7/2017 | Estimate for A/A & E/S submitted to C.E (HZ) vide this office letter No.9270-72 dated 18-12-2017. |
| 3 | 7501  (II)  (  III) | Additional Accommodation C/O  (Multipurpose Hall, Examination Hall, Library Hall & Lecture theatres) Govt Degree College Nadaun Bharmoti  C/O Play ground in Govt college Nadaun Bharmoti  C/O Dressing room/Green room attatched with wash room separately for boys & Girls near basket ballground at Govt Degree College Nadaun Bharmoti | No EDN-H(9)5-54/2002 dated 25/7//2011(Additional Accommodation)  EDN-HE(9) 3-54/2013 Dated 19/3/2015 | 14492-95 dated 25/11/2010 form E.E. Hamirpur & 5315-18 dated 30/6/2017  & 9205-9 dated 5/9/2014 (Playground)  21069-70 dated14-12/2012  Layout recived vide letter no 22334-35 dated 17/2/2017 | No EDN-HE (9)5-54/2002 dated 11/10/2012 (additional accommodation) | 17251-52 dated 10/2/2016  Feasibility report recived from S.E 8th Circle Hamirpur with some querries vide letter no 17251-52 dated 10/2/2016 | Revised layout plan & working drawing along with specification issued vide letter no 3795-97 dated 16/12/2014    working drawing of Play gorund issued on dated 20/7/2015 vide letter no 1683-87  amended working drawing issued vide letter no 5565-67 dated 30/3/2016  Working drawing of Dressing room /Green room , plan elevation & section issued vide letter no 3073-75 dated 13/11/2017 | Contour site plan Sent to Chief Arch. Shimla vide EE Hamirpur letter No. 5315-18 dated dated 30.06.2017  Work is in progress.  Estimate under process in Divisional office. |

**LIST OF WORK 8TH CIRCLE (I.T.I. EDUCATION )**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval** | **Date of feasibility** | **Status of project** | **Status of Projects Supplied by SE.** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| 1 | 8056 | C/O I.T.I. building at Tauni Devi | From Principal Govt. Industrial Training Hamirpur vide letter No.2013-2019 dt. 12.02.14 | Vide letter No. 14487-91 dt. 15.02.14 |  |  | Letter issued to Director Technical Education vide letter no 4858-60dated 22/3/2014 for detailed requirement | Work executed by other Agency. |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **S.No.** | **JOB NO.** | **Name of Project** | **date of requirements received** | **DATE OF RECEIVING SITE PLAN & DETAILS.** | **DATE OF APPROVAL.** | **DATE OF FEASIBILITY.** | **Status of project.** | **Status of Projects Supplied by SE.** |
| 1 | 6673 | Govt.Sen.Sec School Sohari,Hamirpur 4 rooms. | EE Barsar lt no.5402-04 dt 19-7-2014 . | Dy no 297 dt. 28-7-2014. |  |  | Drgs. Issued on dated 30-8-2014 Letter no.688-93 | lt.no765-66 dt.20-9-2014 to principal gsss sohari make further correspondance with ee Barsar Hamirpur |
| 2 | 6673 | Govt.high school Pansai ,Nadaun,Hamirpur lal out plan |  | 6529 dt.17/8/09 |  |  | Drawing issued on dt 1/9/09 |  |
| 3 | mz-151 | Stadium at Bijhri,Hamirpur lay- out plan. |  | 11253-54 dt 20-10-10 |  |  | Working Drgs. Issued on dated 19-8-2010 w.drg issued on dt.25-3-11 |  |
| 4 | 6673 | Govt.Sen.Sec School Patlander |  | 17344-46 dt. 16-10-10 |  |  | layout Issued on dated 3-2-2011 vide lt. no.2082-87 |  |
| 5 | 6673 | Govt.Sen.Sec School Bhadarwar,Sarkaghat LAY-OUT PLAN |  | 7807-08 Dt.11-10-10 |  |  | Drgs. Issued on dated 20-7-2011 vide lt.no. 1676-81 | procure drgs from c a office shimla lt no.2333-34 dt. 28-3-2011 |
| 6 | 4170 | 50 Beded girls hostel at govt. poly.,Hamirpur (Provision of 50 beded grils hostel. |  | 9591-92 dated 1-10-09 | approval received on dated 20-5-2011 vide letter no.1451-53. | FEASIBILITY & approval received on dated 20-5-2011 vide letter no.1451-53 | Drgs. Issued on dated 2-2-2011 lt.no.2071-75 dt 2-2-11 |  |
| 7 | 6673 | Govt.Sen.Sec School Jamni,Sarkaghat . |  | 11300-02 Dt.19-1-11 |  |  | Drgs. Issued on dated 14-2-2011 |  |
| 8 | MZ-202 | I .T .I Paplog ,Sarkaghat ,Mandi detail of boundary wall &gate. | 2/3/2011 | 6/3/2011 |  |  | Drgs. Issued on dated 17-3-2011 lt.no.2161-65. |  |
| 9 | 6673 | Govt.Sen.Sec School Baroti,SARKAGHAT (four rooms). | 16109-11 Dt.27-1-11 dy.no.648 dt.2-2-11 | 16109-11 Dt.27-1-11 dy.no.648 dt.2-2-11 |  |  | Lay -out /sketch Drgs. Issued on dated 1-3-2011 lt.no.2182-87 dt 1-3-11 | in ref lt.no. 18677-79 dt. 28-6-2011 additional acommodation lt.no.441-44 dt 1-7-11 procure drgs from c a office shimla |
| 10 | 4170 | 100 Beded boys hostel at govt. poly.Baru,Hamirpur (hostel. |  | 12114-16 dated 26-3-11 lt.fromdir. Tech edu.33013dt 24-8-11 | approval received on dt.24-8-2011. |  | in ref lt no.1520-21 dt.24-5-11sketch drgs issued lt.no. Dt.18-7-11 | approval received with some necessary changes required to be incorporate in drgs PROJECT DEALT AT CA OFFICE SHIMLA |
| 11 | 3001 | shoping complex &gymnasium at sainik school sujanpur tihra | FROM E.E. 16-12-2011. | FROM E.E. 16-12-2011. |  |  | WORKING DRGS ISSUED ON DT.28-4-2012. |  |
| 12 |  | Const.of Cafetaria & csd building at sainik school Sujanpur Tihra vide lt no.1320-22dt 27-4-11 | vide lt no.1320-22dt 27-4-11 |  |  |  | Drgs. Issued on dated 29-6-2011 lt.no.426-30 | feasibility received lt. no.9238-41 dt. 26.8.2011. approval received on 5.7.11 lt. no. ssst/608/q |
|  |  |  |  | vide lt no.4260-62dt 16-6-11 |  |  | working drgs issued vide lt. no. 98-103 dt. 28-4-12 |  |
| 13 | 6673 | play ground at Barmoti,Nadaun hamirpur vide lt no.204dt 17-3-11 |  | from E.E. letter no.204dt 17-3-11 |  |  | auditorium block already proposed in master plan at proposed site for play ground | in ref lt no.20490-93 dt.17-3-11 lt.no.1509-14 dt 8-7-11 from edn-he(9)-54/2013 gdc nadaun 347 dt may.2013 regarding c/o play ground as audit objection raised by ag shimla **\* Being dealt at ca office Shimla** |
| 14 | 4365 | ITI Rail girl's hostel,nadaun hamirpur detail of cubboard. |  |  |  |  | Drgs. Issued on dated 11-4-2012 letter no.19-24. |  |
| 15 | 4365 | I. T. I . RAIL. c/o second floor with pitched roof to prevent leakage |  | from ca 3664-67 Dt.9-12-14 from ee hmr lt no.17239-43 dt 16-12-14 accommodation at 2nd floor **principal iti lt.no.3238 dt.4-11-15 regarding c/o second floor** |  |  | lt no.1220-23 dt 5-1-15no scope for future expansion structure stability to be examined **received on dt.9-11-15** |  |
| 16 | 6673 | Sr. Sec. School at Sujanpur | 23-5-2011 | 31-5-2011 |  |  | working Drawing issued .on dt. 2/3/10 ,detail of rwht,sdb,ff, drg issued 15-7-11 lt.no.1626-31 in ref 6172-74 dt 11-7-11 dy no.176 dt 20-7-11 Clour scheme issued to E.E.on dt.9-1-12 vide lt. no. 2443-48 |  |

Note :- Red portion shows deposit works Which are not counted in Total Projects