|  |
| --- |
| **OFFICE OF THE SENIOR ARCHITECT (KANGRA ZONE) HP PWD DHARAMSHALA** |
| **BUILDING WORKSOF EDUCATION DEPARTMENT (ONGOING PROJECTS)** |
|  **9 th CIRCLE - NURPUR** |
| **Sr. No**  | **Job No.**  | **Name of Project** | **Date of receiving site Plan**  | **Date of requirments**  | **Date of issue of Drawings** | **Date of feasibility**  | **Date of approval** | **Status of Project**  | **Status of Projects Supplied by SE.** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
|  **SCHOOLS** |
| 1 | 105 | Govt. High School at Gummer Teh. Dehra. | 27/5/2013 | 27/5/2013 | 1/7/2013 Sketch Drawings 13/9/2013 working drawing (Block A & B) | 29.08.2013 | 16/7/2013 | Work in progress (Block -B) |   |
| 2 | 105 | Additional Accommodation for GSSS at Majheen Teh. Khundian. | 5/8/2009 | 5/8/2009 | 15/10/2009 Sketch Drawings. | Awaited | Std. drawing |  Work awarded. |   |
| 3 | 105 | Additional Accommodation for GHS at Dhatti. Teh. Khundian. | 26/10/2013 | 26/10/2013 | 10/1/2014 Sketch Drawings 16/10/2015 working drawings  | 03.07.2015 | Awaited | Work in progress |   |
| 4 | 105 | Additional Accommodation for GSSS at Mahadev Teh. Khundian. | 5/8/2014 | 5/8/2014 | 22/8/2014 Sketch Drawings 22/12/2014 working drawing  | 10.10.2014 | 10/9/2014 |  2nd floor work in progress. |   |
| 5 | 105 |  S.J.S Govt. Senior Secondary School at Kot Plahri Teh. Nurpur  | 18-4-2016 | 6/4/2016 | 7-5-2016 Layout and working drawing | Awaited | --  | Work is in progress. |  |
| 6 | 105 | GSSS Bari Kalan (addl. 5 rooms) | 06.08.2016 | 06.08.2016 | 15.5.2017 working drawings |   |   |  Slab laid over 2nd floor |   |
| 7 | 105 | GSSS Thill (addl. 5 rooms) | 06.8.2016 | 06.8.2016 | 15.5.2017 working drawings |   |   |  2nd floor work in progress. |   |
| 8 | 105 | Play Ground at GSSS Khundian | 26.04.2016 | 22.04.2016 | 17.08.2016 sketch drawing 15.5.2017 revised sketch drawings | Awaited | Awaited |  Work in progress |   |
| 9 | 105 | GSSS Nahlian (addl. 05 rooms) | 07.10.2016 | 24.09.2016 |   |   |   | Information awaited |   |
| 10 | 105 | Govt SSS at Lagru | 21-03-2015 | 18-08-2015 | 31-03-2016 Layout Plan and Sketch drawing  | Awaited | Awaited |  Work in progress |   |
| 11 | 105 | GSSS Pihri (addl. 05 rooms) | 07.10.2016 | 24.09.2016 | 15.5.2017 working drawings |   |   |  Tender under process |   |
| 12 | 105 | GSSS Seorbala (addl. 05 rooms) | 07.10.2016 | 24.09.2016 | 15.5.2017 working drawings |   |   |  -do- |   |
| 13 | 105 | Govt. S.S.School at Fatehpur | 23.06.2017 | 19.06.2017 | 12.07.2017 working drawings | Awaited | Approved drawing |  Work in progress. |   |
|  **COLLEGES** |
| 14 | 315 | Additional Accommodation for Govt. Arya College at Nurpur.(Old) | 11/12/2014 | 11/12/2014 | 27/1/2015 sketch Drawings 21-9-2015 working drawings | 20-7-2015 | 13-7-2015 | Work in progress |   |
| 15 | 335 | Govt. Degree College Dadasiba | 24/02/2016 | 22/02/2016 | 02.7.2016 Working drawing 03.09.2016 working drawing | 20.08.2016 | 22.08.2016 | Block-A GF slab laid Block –B Column work in progress. |   |
| 16 | 345 | Wazir Ram Singh Govt College at Dehri Teh. Nurpur | 18.10.2016 | 15.10.2016 | 19.11.2016 sketch drawings 06.02.2017 working drawing | 01.12.2016 | 08.12.2016 |  Work awarded |   |
| 17 | 315 | Govt Arya Degree College Nurpur(New) | 20.08.2016 | 17.08.2016 | 06.02.2017 sketch drawings 30.03.2017 working drawings | 17.02.2017 | 07.03.2017 |  Tenders are being recalled. |   |
| 18 | 348 | Govt Degree College at Jandaur, Teh-Jaswan | 13.12.2016 | 05.12.2016 | 13.02.2017 sketch drawings 12.04.2017 working drawings | 07.03.2017 | 08.03.2017 |  Work awarded |   |
| 19 | 351 | Govt Degree College at Rakkar | 11.01.2017 | 10.01.2017 | 31.03.2017 working drawings 29.05.2017 working drawings | 11.04.2017 | 26.04.2017 |  -do- |   |
| 20 | 352 | Govt Degree College at Majheen | 28.03.2017 | 20.03.2017 | 01.05.2017 sketch drawings 18.08.2017 working drawings | 24.07.2017 | 27.06.2017 |  Working estimate under preparation. |   |
| 21 | 353 | Govt Degree College at REY | 28.04.2017 | 24.04.2017 | 06.05.2017 working drawings 22.06.2017 working drawings | 12.06.2017 | 02.06.2017 |  -- | Revised estimate sent to Director Higher Education for A/A & E/S |
| 22 | 4737-A | Toilet Block for Govt Degree College at Dhaliara  | 28.03.2017 | 16/03/2017 | 26.09.2017 sketch drawings | Awaited | 0 |   |   |
| 23 | 4737-A | Play Grnd & Pavilion at Degree College Dhaliara | 28.03.2017 | 16.03.2017 | 18.11.2017 sketch drawings | Awaited | Awaited |   |   |
|  **Technical Education**  |   |   |   |   |   |   |
| 24 | 321 | Additional Accommodation for ITI at Nurpur  | 8/7/2015 | 6/8/2015 | 19/9/2015 sketch drawing | Awaited | Awaited |  -- | -- |

**`LIST OF WORK, 9th CIRCLE, NURPUR (EDUCATION)**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr No.**  | **Job No.**  | **Name of Project** | **Date of Requirement received** | **Date of receiving site plan & details** | **Date of approval** | **Date of feasibility**  | **Status of project**  | **Remarks** |
| 25 | 6595 | Govt. Sr. Sec. School Dah khulara, MalahriFatehpur distt. Kangra Dah Khulara | 25/11/2014 through E.E. | 25/11/2014 | 20/01/2015 | 19/03/2015 | Layout plan & working drawings alongwith specification issued vide letter No. Drawing No. 23 & 28 to 31 on dated 26-08-2015 On dated 31/7/2015 |  |
| 26 | 6595- A  | Govt. Sr. Sec. School Kot Plahri, Nurpur Div.  | 29/03/2013, 11/11/2013 | 22/07/2013 | 03/01/2014 | 25/03/2014 | Working drawing alongwith detail have been issued 21/07/2014 | . |
| 27 | 8063 | Govt. Degree College at Nagrota Surian | 03.03.2014 | Letter No. 263-64 dated 03/03/2017 | dated 22-12-2015 | Letter No. 13041-42 dated 31-12-2015 | Details of gate and boundary wall issued.Letter no.2452-54 dated 15/09/2017Details of joints, windows, screen, railing and flooring issued on dated 5/01/2017 |  |
| 28 | 8093 | Govt. Degree College Khundian  | Requirement received on Feb., 2014 | Site plan received on 08/01/2015 | Awaited  | Awaited  |  Working drawings & specification issued on dt.Dated 07-08-15, |  |
| 29 | 4737 | Degree College Dhaliara Academic Block  | 23/03/2010 | 15/11/2010 | 22/02/2013 | 07/01/2013 | Revised drawings of Academic block bearing drg. no. 25 to 27 of Job No. 4737 issued. |  |
| 30 | 7986 | C/O Chander Dhar Guler Degree college (Science Block)( Stadium & Pavillion) | Letter No. 8744-46 dated 28/8/2017(Through EE Dehra  | (As per Cm Announcement) Letter No. 14437-40 dated 3/1/2017 From EE DehraLetter No. 13676 -77 dated 6/2/2014 |  | Feasibility Vide letter No. 10700-01 dated 28/9/17 | Letter No. 3770-74 dated 20/1/2017 regarding detailed requirements.Letter issued to Director vide letter no. 2670-73 to vet the requirements.Sketch drawings issued for feasibility and approval vide letter No 265-68 dated 22/4/16W/D issued vide letter No. 2983-84 dated 6/11/2017 |  |
| 31 | 8003 | I.T.I. at Gangath  | 18/02/2015 | 31/07/2014 |  | 19/01/2015 | Working drawings issued vide Letter No.1232-36 dated08/07/2016 |  |
| 32 | 8013 | I.T.I. Khundian, Jawalamukhi  | 30/01/2015 | 24/01/2015 from E.E. to this office  | dated: 08/07/2015  | 4964-65, dated: 10/07/2015, | Working drawings supplied on Dated 07-08-15 . |  |
| 33 |  | G. S.S.S. Paloura  |  -do- | 25/07/2013  |  |   | Working drawing alongwith detail. Supplied On dated 22/05/2014  | . |
| 34 |  | G. S.S.S. Bahi Pathiar  |  -do- | 25/07/2013  |  |  | Working drawing alongwith detail. Supplied On dated 28/05/2014  | . |
| 35 |  | G. S.S.S. Harsar |  -do- | 04/01/2014 | 03/03/2014 | 28/03/2014 | Working drg. Supplied alongwith detail.On dated 22/05/2014  |  |
| 36 |  | Govt. High School, Talian  |  -do- | 01/12/2014 | 11/06/2014 | 08/08/2014 | Drawing suppliedOn dated 30/05/2014 |  |
| 37 |  | Govt. High School, Nanhar, Jawali  |  | 04/01/2014 | 23/06/2014  | 25/07/2014 | Drawing supplied 30/05/2014 |  |

Note :- Red portion shows deposit works Which are not counted in Total Projects