|  |
| --- |
| **BUILDING WORKS OF VETRINERY DEPARTMENT (ONGOING PROJECTS)** |
| **9 th CIRCLE - NURPUR** |
| **Sr. No**  | **Job No.**  | **Name of Project** | **Date of receiving site Plan**  | **Date of requirments**  | **Date of issue of Drawings** | **Date of feasibility**  | **Date of approval** | **Status of Project**  | **Status of Projects Supplied by SE.** |
| 1 | 111 | Vet. Dispensary at Khehar Teh.Nurpur. | 18/12/2010 | 18/12/2010 | 7/7/2011 Standrad Design | Awaited | Std. drawing |  Work completed. |   |
| 2 | 111 | Vet. Dispensary at Ghar Jarot. Teh.Jawali.  | 14/8/2012 | 14/8/2012 | 25/10/2012 SketchDrawings 26/3/2013 Working Drawing . | Awaited | Std. drawing |  P/E sent to Director Animal Husbandry Shimla vide this office No.973-75 dt.5-2-14 for A/A&E/Sof Rs.9,17,200/-,same still awaited. |  Standard working drawing received vide Sr.Architect (KZ)D/salaNo.619-23 dt.26-3-2013. |
| 3 | 111 | Vet. Dispensary at Chhatral Teh. Fatehpur. | 26/11/2013 | 26/11/2013 | 18/12/2013 Working drawing | Awaited | Std. drawing |  Work completed. |   |
| 4 | 111 | Vet. Hospital at Rey Teh. Fatehpur. | 17/2/2014 | 17/2014 | 14/3/2014 Working drawing | Awaited | Std. drawing |  Work completed. |   |
| 5 | 111 | Vet. Dispensary at Patta Jattian.Teh. Fatehpur. | 17/4/2014 | 17/4/2014 | 5/5/2014 Working drawing | Awaited | Std. drawing |  Work completed. |   |
| 6 | 111 | Vet. Dispensary at Baranda Teh. Nurpur. | 16/8/2014 | 16/8/2014 | 19/9/2014 Sketch Drawing , 19/12/2014 working Drawing. | 17.11.2014 | Std. drawing |  Work in progress. |   |
|   |   |   |   |   |   |   |   |   |   |
|  **BUILDING WORKS OF GAD DEPARTMENT (ONGOING PROJECTS)** |
|  **9TH CIRCLE - NURPUR** |
| **Sr. No**  | **Job No.**  | **Name of Project** | **Date of receiving site Plan**  | **Date of requirments**  | **Date of issue of Drawings** | **Date of feasibility**  | **Date of approval** | **Status of Project**  | **Status of Projects Supplied by SE.** |
| 7 | 268 | Office of Executive Engineer, HP PWD Dehra. | 9/9/2014 | 18/9/2014 | 19/1/2015 Sketch Drawing 09.08.2016 sketch drawing revised | 18.08.2016 | Awaited |   |   |
| 8 | 318 | Treasury Office building at Fatehpur. | 10/12/2014 | 12/12/2014 | 20-3-2015 sketch drawing 21-8-2015 revised sketch drawing 17-03-2016 working drawings  | 25.04.2015 | 30.11.2015 |  Work in progress. |   |
| 9 | 204 | Sub- Tehsil Office building at Nagrota Surian | 5/3/2015 | 2/3/2015 | 02.09.2016 Sketch drawing 21.04.2017 working drawings | 27.09.2016 | 20.03.2017 |  Preliminary estimate sent to Secretary (GAD) Shimla vide Deputy Commissioner Kangra at Dharmshala letter No.3739 dated 17.10.2017 for A/A & E/S of Rs. 14801600/- only and same is awaited.  |   |
| 10 | 340 | Rajasav Sadan at Haripur, Distt. Kangra | 21.2.2015 | 21.2.2015 | 02.9.2016 Sketch drawings | 17.10.2016 | Awaited |   |   |
| 11 | 204 | Sub- Tehsil Office building at Kotla | 11/1/2016 | 8/1/2016 | Presentation drawings |   |   | Revised site plan awaited | Adequate site not made available by client deptt. |
| 12 | 204 | Sub Tehsil Building at Majheen | 28.03.2017 | 20.03.2017 | 16.06.2017 sketch drawings | 18.07.2017 | 24.11.2017 | Working drawings under preparation |   |
|   |   |   |   |   |   |   |   |   |   |
| **BUILDING WORKS OF MISC. DEPARTMENTS (ONGOING PROJECTS)** |
| **9TH CIRCLE - NURPUR**  |
| **Sr. No**  | **Job No.**  | **Name of Project** | **Date of receiving site Plan**  | **Date of requirments**  | **Date of issue of Drawings** | **Date of feasibility**  | **Date of approval** | **Status of Project**  | **Status of Projects Supplied by SE.** |
| 13 | 265 | Shaheed Bhubnesh Dogra Stadium at Dehra. | 12/10/2010 | 12/10/2010 | 12/8/2010 sketch drawings 28.06.2011 working Drawing | 12/10/2010 | 22.02.2011 | **Work awarded to the contractor.** |  |
| 14 | 246 | Residence accommodation ( Flat wise ) at Nurpur. Type III Type IV. | 6/6/2010 | 06.06.2010 | 10/11/2010 working drawing  | 19/1/2015  | 6/4/2010 |  Work of Type-III qtr.completed. |  |
| 15 | 334 | PWD Rest house at Sulyali Teh. Nurpur. | 19.03.2016 | 19.03.2016 | 20.5.2016 Sketch drawings 23.02.2017 working drawings | 27.06.2016 | awaited | Work in progress |  |
| 16 | 314 | Book distribution Centre-Cum- Guest House at Jawalamukhi, Distt Kangra | 19/1/2015 | 19/1/2015 | 13/5/2015 sketch drawings 28-1-2016 working drawings | 28/8/2015 | 11/8/2015 | Work in progress |   |
| 17 | 303 | E.T.O Office cum residance at Jawali | 1/2/2016 | 29-01-2016 | 20-02-2016 layout and sketch drawing  | Awaited | awaited |  Drawing sent to ETO Jawali vide EEJawali No.1909-10 dt.5-3-2016 for feasibility which is still awaited. |   |
| 18 | 343 | Kalinath Temple at Kaleshwar Mahadev Tehsil Rakkar | 30-03-2016 | 22-3-2016 | 15.12.2016 Sketch drawing 23.2.2017 working drawings | 28.12.2016 |   |  Tender called. |   |
| 19 | 359 | Rennovation of Old Pond at Haripur | 19.08.2017 | 16.08.2017 | 28.09.2017 sketch drawings (Landscape) | 23.11.2017 | awaited |  -do- |   |
| 20 | 327 | Football stadium at Jawali. | 20/1/2016 | 18/1/2016 |   |   |   | Revised Site plan awaited |  Clear and sufficient site not made available by client deptt.yet. |
| 21 |   | Outdoor Stadium at Jawalamukhi (Drang). | 06.8.2016 | 06.8.2016 |   |   |   | Under preparation |   |
|   |   |   |   |   |   |   |   |   |   |
| **BUILDING WORKS OF POLICE DEPARTMENT (ONGOING PROJECTS)** |
|  **9 th CIRCLE - NURPUR** |
| **Sr. No**  | **Job No.**  | **Name of Project** | **Date of receiving site Plan**  | **Date of requirments**  | **Date of issue of Drawings** | **Date of feasibility**  | **Date of approval** | **Status of Project**  | **Status of Projects Supplied by SE.** |
| 22 | 3292-A | Police Station at Dehra | 29.05.2017 | 19.05.2017 | 30.06.2017 working drawings (std. drawings) 05.09.2017 Revised drawings (addition of 2nd floor plan) | 22.09.2017 | awaited |  Counter site plan submitted to Sr.Architect Office. |   |

**LIST OF WORK, 9th CIRCLE, NURPUR REST HOUSE**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.**  | **Job No.**  | **Name of Project** | **Date of Requirement received** | **Date of receiving site plan & details** | **Date of approval** | **Date of feasibility**  | **Status of project**  | **Status of Projects Supplied by SE.** |
| 23 | 7178 | HP. PWD., Rest House Khundian, additional accommodation, Dehra, Division, 9th Circle | 06/02/2015, from Architect (KZ) |  |  | Letter No. 4860-61 dated 9/7/2016 | . Working drawings No 12 to 14 issued on 05-08-2015. |  |
| 24 | 3444 | Rest House at Indora(addl. Accommodation) | Letter No. 7805-08 dated 27/12/2014 | Letter No. 7990-91 dated 5/11/2015 | Letter No. 9306-08 dated 28/10/2016 | Letter No. 2852-54 dated 2/1/2016 | Sketch drawing issued on 19/12/2015 for feasibility & approvalW/D issued vide letter No. 3823-26 dated 21/1/2017 |   |
| 25 | 3305 | Rest House at Dehra(Addition & alteration ) | 04/07/2013 from E.E. Dehra as desired by the Hon’ble CM | Site plan received vide letter 577-78 on 04/07/2013  | Letter NO. 1246-49 dated 15/5/2016 | Letter No. 162-63 dated 5/5/2015  | W/D issued for feasibility and approval vide letter no. 6176-79 dated 21/3/2015Revised Working drawing No. 28 to 30 are to be sent on 07/07/2015  |  |
| 26 | 3131 | Rest House at JawalamukhiAdditional accommodation  | Hon’ble Chief announcement Minister on 30/06/2016 | Letter No. 7096-98 dated 18/8/2016 | ---------- | 28/10/2015 | Working drawings alongwith typed specification issued vide Letter No.1762-64 dated 23/8/2016Detail of staircase & balcony issued vide letter no. 2728-29 dated 7/10/2017 |  |
| 27 | 3474 | Rest House at Nurpur  | ----------------- | Requirements & Site plan were received in this office through Architect KZ on 14/06/2013 & ground floor photographs & CD were received in this office on 15/07/2013, from E.E.  | Awaited  | Awaited  | Working drawing alongwith detail of porch has been prepared. Approval & feasibility awaited on 24/06/2015 |  |
| 28 | 4550 | Rest House at Jawali Additional accommodation  | Letter No. 181083 dated 11/2/2016 as per cm announcement  | Letter No. 1056-57 dated 25/07/2013 |  | Letter No. 437-39 dated 5/4/2016 |  Working drawings issued for feasibility & approval on dated 02/3/2016W/D issued vide letter No. 960-76 dated 17/6/2016 |  |
| 29 | 70967096 |  C/O Rest House Fatehpur.(proposal for additional accommodation | E.E Letter No. 8145-47 dated 16-11-15. |  |  | Letter No. 3501-03 dated 10/03/16 | Reminder sent to E.E. for getting the approval from the competent authority Letter No. dated 28/08/16 | .  |

**LIST OF WORK, 9th CIRCLE, NURPUR (MISC)**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 30 | 6634 | Jawalamukhi Temple(C/O Diyodhi ) |  | Dated 9/11/15 |  |  | Letter received from Temple Office for construction of Diyodhi in Jawalamukhi Temple as per CM Announcement.Dated 6-10-15 |  |
| 31 | 8216 | C/O Combind Office Building at Fatehpur Distt. kangra HP  | Letter No 1407-10 dated 06/07/2017 supplied by EE Fatehpur framed by Sub Divisional Officer Chamba | Revised site plan received from EE Fatehpur letter No.2131-32 dated 18/09/17 |  | Letter no. 2040 dated 01/09/17 from E.E Fatehpur | Letter issued to EE Fatehpur regarding to send the detailed site plan.Letter No. 2721-23 dated 7/10/17 | . |

Note :- Red portion shows deposit works Which are not counted in Total Projects