|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **List of Work College (Education )Nahan Circle** | | | | | | | |  |
| **Sr. No** | **Job No.** | **Name of Project** | **Date of requirement received** | Date of receiving site plan & details | **Date of approval** | **Date of feasibility** | **Status of project** | **Remarks.** |
| **Colleges In 12 Circle Nahan** | | | | | | | | |
|  |  |  |  |  |  |  |  |  |
| **1** | **8137** | **C/O Govt College (Anj Bhoj)At Bharli Distt Sirmour** | **EDN-H (9)1-Policy /2009 dated 31/10/2015** | 4613-14 Dated14/12/2015 | **Dated 30/1/2016** | **5152-53 dated25/2/2016**  **14745-48 dated 4/2/2016** | **Working drawing issued vide letter no 4606-09 dated 19-1-2016**  **Layout plan working drawing with specification issued vide letter no 97-99 dated 6-4-2016** | **40% work completed. (Block B Frame structure completed and Roofing & finishing works of block B is in progress and Block C columns raised upto first floor slab level).** |
| **2** | **7035** | **C/o Govt Degree**  **College Paonta Shahib (New Academic Block)** | **EDN-HE(9) 4-1/2007 GC (Paonta Sahib) dated 12/11/2014** | 5998-6000 dated 26/12/2014 | **EDN-H(9)4-1/2007 (build) paonta sahib dated 4/9/2015** | **1579 dated 3/6/2016** | **Sketch drawing along with layout plan issued vide letter no 2417-21 dated 28/8/2015** | **10 % work completed. RCC foundation and 16 nos column laid.** |
| **3** | **7848** | **C/O Govt Degree College Sangrah Distt Sirmour** | **Dated 11-5-2010**  **Dated 21-7-2015**  **EDN-HE (9) 4-51/2011 dated 21/10/2016 (Residential Accommodation )** | 1410-15 Dated 28-5-2015  10893-96 dated 16/11/2017 | **EDN-H (9)4-5/2007 Dated 13-9-2010** |  | **Revised layout plan at Sangrah of residential accommodation issued vide letter no 2069-73 dated 18/8/2010** | **Tender for one No Type V Qtr awarded to the contracto & site development work is in progress. where as the Hostel Type Accommodation requirement has been Submitted to the director of higher Education /Architect Shimla fpr Praparetion of Drawings /requirement vide this office Letter No 10893-96 dated 16.11.2017** |
| **4** | **8153** | **C/O Govt Degree College Kaffota Tehsil Paonta Sahib Distt Sirmour** | **EDN-H(9) 1-Polcy /2009 dated 20/10/2015** | 515-17 dated 19/4/2016 | **EDN –HE (9)4/18/ 2007 Dated 18/5/2016** | **7718-19 dated 27/12/2016** | **Working drawing issued vide letter no 624-27 dated 17-5-2016** | **Tender for one No Type V Qtr awarded to the contracto & site development work is in progress. where as the Hostel Type Accommodation requirement has been Submitted to the director of higher Education /Architect Shimla fpr Praparetion of Drawings /requirement vide this office Letter No 10893-96 dated 16.11.2017** |
|  |  |  |  |  |  |  |  |  |
| **5** | **7842** | **C/O Govt Degree College Shillai** | **dated 13/9/2010** | 4862-64dated 14-10-2005  2263-64 dated 17/6/2009 |  | **128-29 dated 7-4-2016** | **Working drawing issued with specification vide letter no 128-29 dated 7/4/2016** | **College building ,Type-V qtr & Canteen block Completed Type-IV Ground floor slab laid, Type- I & III 85% work complete finishing work is in progress** |



|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **List of Work Education(School) 12th Circle Nahan** | | | | | | | | |
| **8** | **6546** | **C/O Govt High School Mattar Distt Sirmour** | **Dated 29-12-2015** |  |  |  |  | **Contur site plan is being prepared which will be sent to Chief Archtect Shimla very shortly for evolving the working drawing.** |
| **9** | **6546** | **C/O Govt High School Maina Distt Sirmour** | **EDN-H (9)4-14 /2012Dated 18/1/2016** |  |  |  | **Letter issued for requirement vide letter no 2442-46 dated 1/9/2015** | **GAD is awaited** |
| **10** | **6546** | **C/O Govt Sr Sec School Gahanduri Distt Sirmour** | **EDN-H (9)4-14/2012 dated 23/6/2014** | 10177-82 dated 31/10/2013 | **EDN-H (9)4-14 dated 15/1/2015** |  |  | **75% work for two rooms and examination hall completed. Revised site/Contour plan is to be Submitted for Revised feasibility for balance Accommodation.** |
| **11** | **6546** | **C/ O Govt High School Madwach** | **EDN-H (9) 4/14/2012 Dated 8/5/2017** | 5355-58 dated 6/9/2016 |  |  |  | **Letter issued for requirement vide Chief Architect letter 2109-12 dated 21.09.2016** |
| **12** | **6546** | **C/o Govt sr sec school Nohradhar Distt Sirmour** |  | 29-31 dated 7/4/2017 | **EDN-H (9) 4-14/2012 dated 25/5/2017** |  | **Layout plan, working drawing along with specification issued for approval vide letter no 464-67 dated 12/5//2017** | **Estimate Prapared and is being submitted Sortly for Approval.** |
| **13** | **6546** | **C/o Govt Sr sec school at Sangrah distt Sirmour HP**  **(Additional 8 Room Govt. Sr. sec. School Sangrah )** | **No EDN-B-Ga (1)-5/2014 dated 2014&EDN-HE (9)1-2/2016 -17 dated 8/2016** | 8643-44 Dated 21/8/2017  10711-13 dated 26/10/17 |  |  |  | **Site development work is in progress & GAS awaited.** |