**Standard Bidding Document For**

**Pradhan Mantri Gram Sadak Yojana (PMGSY)**

# For

**Construction & Maintenance**

June, 2020

***National Rural Infrastructure Development Agency***

## Ministry of Rural Development

***Government of India***

# TABLE OF CONTENTS

**Standard Bidding Document for PMGSY for Construction and Maintenance**

### Section Description Page

[ExplanatoryNote 3](#_TOC_250003)

Section1 List of Dates, PressNotice,NIT 4

Section2 Instructions to Bidders & AppendixtoITB 11

[Section3 QualificationInformation 35](#_TOC_250002)

Section4 General Conditions of Contract, Part I,Contract Data 39

[Appendix to Part I General ConditionsofContract 77](#_TOC_250001)

[Part II Special ConditionsofContract](#_TOC_250000) 80

Section5 Specifications 81

Section6 Form of Bid 83

Section7 Bill ofQuantities 86

Section8 Standard Forms, Letter of Acceptance,

Notice to Proceed with theWork,Agreement 89

# EXPLANATORY NOTE

**Format of the Bidding Document**

The Standard Bidding Document for Pradhan Mantri Gram Sadak Yojana (PMGSY) follows the format of the MoRTH Bidding Document, which is similar to the format for National Competitive Bidding for Works (India Version) — as approved by the Ministry of Finance for World Bank aidedprojects.

The document has the added feature of maintenance of roads for five years by the contractor who constructs the road.

**SECTION 1**

### LIST OF IMPORTANTDATES

**e-procurement NOTICE NOTICE INVITINGTENDERS**

**SECTION 1**

*……………………………………………………………………………………………………… (Name of Authority inviting tenders)*

##### List of Important Dates of Bids for Construction/Upgradation of Roads under Pradhan Mantri Gram Sadak Yojana and their Maintenance for Five years

1. **Name ofWork**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl . no | District | Package no. | Name of the work | Period of completion | Estimated Cost (Rs. Lakh) | | Total Cost (Rs. Lakh) |
| Construction | Maintenance |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
|  |  |  |  |  |  |  |  |

1. **Maintenance Period is five years from the completiondate**
2. **Date of Issue of NoticeInviting Bid** Date…Month……Year……..

##### Period ofavailability

**of Bidding Documents on website**

[**www.pmgsytenders.gov.in**](http://www.pmgsytenders.gov.in/)**– From** Date….Month….Year………

**To** Date .… Month…… Year…… Timeupto Hours

1. **Time, Date and Place ofPre-bid Meeting** Date ….. Month…… Year…….

(ifso required) Time……… Hours, Place …

##### Deadline for receiving Bids online, including

##### on line payment of bid, security and

**cost of bid document from a scheduled Date ….. Month……Year…….**

**commercial bank and scanned copy of affidavit.**

**The on line payment of Bid security and Time upto Hours**

**cost of Bid document is to be done simultaneously**

**on e- tendering website along with the submission of Bids**

##### *Note: Wherever in the Bid document reference to Bid Security and Cost of Bid document is made the meaning is on line payment only instead of demand draft or any other instruments mentioned anywhere in the bid document. The word demand draft or other forms of submission, is deemed to be amended to on line payment only along with the on line submission of bid document.*

**6.2 Date of submission of original affidavit.**

(*This Date should be no later than three working days after the submission*

*of Technical Qualification part of the bid*).The cost of bid document Date ….. Month……Year…….

and Bid security is to be paid on line along with bid submission as mentioned

in clause 6.1 above. As such no other document is required to be submitted.

***Or***

***Till the online payment system is made functional, following Clauses shall be applicable for off-line submission, clause 6.1, 6.2 is deemed to be replaced as 6.1 (a), 6.2 (a)***

##### (a) Deadline for Receiving Bidsonline,

**including Scanned copyofdemand** Date ….. Month……Year…….

**draft of Bid Security andof Demand** Timeupto Hours

##### Draft towards cost of Bid Document from a Scheduled Commercial Bank and scanned copy of Affidavit.

* 1. **(a) Date of Submission of original documentssuchas** Date…….Month…….. Year

##### Bid Security, Cost of Bid document and Affidavit (this date should be no later than three working days after the submission of Technical Qualification

**part of the bid)**

1. **Opening of Bids: The Bids will be opened online by the authorized officer at the appointedtime**
   1. **7.1 Time and Date for opening of Part-I ofthe**

**Bid (The TechnicalQualificationPart)** Date …….Month……Year…….

Time ………Hours

##### 7.2 Time and Date of opening of Part-II of the Bid (The Technical-Financial Part) of theBidders

**who Qualify in Part I oftheBid.** Date …….Month……Year…….

Time ………Hours

1. **Last Date ofBidValidity** Date …….Month……Year…….

##### Officer invitingBids

……………..Designation:

………………..Address:

…………………………………………………………………………………………………………………

# PRADHAN MANTRI GRAM SADAK YOJANA (PMGSY)

e-Procurement Notice

The (Name of Authority inviting Bids) on behalf of invites the item / percentage rate bids in electronic tendering system for construction of roads under Pradhan Mantri Gram Sadak Yojana in thedistrictsof ,

………………….,……………..,….……………,…………………., for

………..numberofpackageswithestimatedcosttotalingtoRs. Crore

including their maintenance for five years from the eligible contractors registered with---

------------------------------------------ x

Date of release of Invitation for Bids through e-procurement: ……………………

(dd/mm/yyyy)

**Availability of Bid Documents and mode of submission:** The bid document is available online and should be submitted online in [www.pmgsytenders.gov.in.](http://www.pmgsytenders.gov.in/) The bidder would be required to register in the web-site which is free of cost. For submission of the bids, the bidder is required to have a valid Digital Signature Certificate (DSC) from one of the authorized Certifying Authorities. The bidders are required to submit (a) original Demand Draft towards the cost of bid document and (b) original bid security in approved formand

(c) original affidavit regarding correctness of information furnished with bid document as perprovisionsofClause4.4B(a)(ii)ofITBwith (*address anddetails*

*of office where to be submitted*) , on a date not later than three working days after the opening of technical qualification part of the Bid, either by registered post or by hand, failing which the bids shall be declared non-responsive.

##### Last Date/ Time for receipt of bids through e-procurement: ……………………

(dd/mm/yyyy)upto (time)

For further details please log on to [www.pmgsytenders.gov.in](http://www.pmgsytenders.gov.in/)

………………………………

….. ………………………… (Designation and address of Authority invitingbids)

x.*Non-registered bidders may submit bids; however, the successful bidders must get registered in appropriate class with appropriate authorities before signing the contract*

# SECTION 1

**…………………………………………………..…………………………………………………………**

(Name of Authority Inviting Bids)

### NOTICE INVITING TENDER (NIT)

1. The onbehalfof invites the percentage rate/item rate bids, in electronic tendering system, for construction of roads under Pradhan Mantri Gram Sadak Yojana for each of the following works including their maintenance for five years from the eligible and approved contractorsregisteredwith \*

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| District | Package no. | Name of the work | Estimated Cost (Rs. Lakh) | | Total Cost (Rs. Lakh) | Period of Completion | Bid Security  (Rs. Lakh) *The bid security is two percent of the total cost, rounded to the nearest thousand* |
| **Construction** | **Maintenance** |  |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
|  |  |  |  |  |  |  |  |

1. Date of release of Invitation for Bids through e-procurement:……………………

(dd/mm/yyyy)

1. **Cost of BidForm**: Rs per package (*non-refundable*) only in formof

Demand Draft in favour of ……………………………..

1. **Availability of Bid Document and mode of submission**: The bid document is available online and bid should be submitted online on website [www.pmgsytenders.gov.in.](http://www.pmgsytenders.gov.in/) The bidder would be required to register in the web-site which is free of cost. For submission of bids, the bidder is required to have valid Digital Signature Certificate (DSC) from one of the authorized Certifying Authorities (CA). “Aspiring bidders who have not obtained the user ID and password for participating in e- tendering in PMGSY may obtain the same from the website: [www.](http://www/)pmgsytenders.gov.in

Digital signature is mandatory to participate in the e-tendering. Bidders already possessing the valid digital signature issued from authorized CAs can use the same in this tender.

* *Non-registered bidders may submit bids; however, the successful bidders must get registered in appropriate class with appropriate authorities before signing thecontract.*

1. **Submission of Original Documents**: The bidders are required to submit (a) original Demand Draft towards the cost of bid document and (b) original bid security in approved form and (c) original affidavit regarding correctness of information furnished withbiddocumentasperprovisionsofClause4.4B(a)(ii)ofITBwith………………..

(*address and details of office where to be submitted*) , on a date not later than three working days after the opening of technical qualification part of the Bid, either by registered post or by hand.

##### 6. LastDate/Timeforreceiptofbidsthroughe-tendering:……………

(dd/mm/yyyy)up-to (time)

7. The site for the work isavailable.

8. Only online submission of bids is permitted, therefore; bids must be submitted online on website [www.pmgsytenders.gov.in.](http://www.pmgsytenders.gov.in/) The technical qualification part of thebids

will be opened onlineat

(time)on

(date) by the

authorized officers. If the office happens to be closed on the date of opening of the bids as specified, the bids will be opened online on the next working day at the sametime.

9. The bidder is not required to quote his rate for routine maintenance. The rates to be paid for routine maintenance are indicated in the Bill of Quantities. Further, the payment for routine maintenance to the contractor shall be regulated based on his performance of maintenanceactivities.

10. The bids for the work shall remain valid for acceptance for a period not less than ninety days after the deadline date for bidsubmission.

11. Bidders may bid for any one or more of the works mentioned in the Table above. To qualify for a package of contracts made up of this and other contracts for which bids are invited in the same NIT, the bidder must demonstrate having experience and resources sufficient to meet the aggregate of the qualifying criteria for the individual contracts.

12. Other details can be seen in the bidding documents. The Employer shall not be held liable for any delays due to system failure beyond its control. Even though the system will attempt to notify the bidders of any bid updates, the Employer shall not be liable for any information not received by the bidder. It is the bidders’ responsibility to verify the website for the latest information related to thetender.

Signatureanddesignationof the Authority Inviting Bids for and on behalfof

……………………………………………………….

……………………………………………………

# Section 2: Instructions to Bidders

#### Table of Clauses

|  |  |
| --- | --- |
| **A. General**   1. Scope ofBid 2. Source ofFunds 3. Eligible Bidders 4. Qualification of the Bidder 5. One Bid per Bidder 6. Cost of Bidding 7. SiteVisit   **B. Bidding Documents and Evaluation**   1. Content of BiddingDocuments 2. Clarification of Bidding Documents and Pre- Bid Meeting 3. Amendment of BiddingDocuments   **C. Preparation ofBids**   1. Language of Bid 2. Documents Comprising theBid 3. Bid Prices 4. Currencies of Bid 5. Bid Validity 6. Bid Security 7. Alternative Proposals byBidders | **E. Bid Opening**   1. Bid Opening 2. Process to be Confidential 24.Clarification of Bids and   Contacting theEmployer   1. Examination ofbids   and Determination of Responsiveness   1. Evaluation and Comparison of Bids   **F. Award of Contract**   1. Award Criteria 2. Employer's Right to Accept any Bid and to Reject any or all Bids. 3. Notification of Award and Signing ofAgreement 4. Performance Security 5. Advances 6. Corrupt or FraudulentPractices |
| **D. Submission ofBids**   1. Bidding Through e-Tenderingsystem 2. Electronic Submission ofBids 3. Deadline for Submission ofBids 4. Late Bids, Modification/Withdrawal |  |

**Section 2**

**Instructions to Bidders (ITB)**

***A. General***

1. **Scope ofBid**

1.1 The Employer as defined in the Appendix to ITB invites bids for the construction of Works and their maintenance for five years, as described in these documentsandreferredtoas“theWorks”.Thenameandidentificationnumberof theworksisprovidedintheAppendixtoITB.Thebiddersmaysubmitbidsforany oralloftheworksdetailedinthetablegivenintheNoticeInvitingTender.Bidfor each work should be submittedseparately.

1.2 The successful Bidder will be expected to complete the Works by the Intended Completion Date specified in the Part I General Conditions of Contract anddotheroutinemaintenanceofroadsforfiveyearsfromthedateofcompletion.

* 1. Throughout these documents, the terms “bid” and “tender” and their derivatives(bidder/tenderer,bid/tender,bidding/tenderingetc.)aresynonymous.

1. **Source ofFunds**
   1. TheGovernmentoftheStateasdefinedintheAppendixtoITBhasdecided to undertake the works of construction and up-gradation of selected rural roads of the State through State budget and funds received under Pradhan Mantri Gram SadakYojana,fromtheGovernmentofIndia,MinistryofRuralDevelopment,and other sources to be implemented through theEmployer.
   2. The Government of the State has decided to provide funds for the routine maintenance of theroads.
2. **EligibleBidders**
   1. ThisInvitationforBidsisopentoalleligiblebiddersmeetingtheeligibility criteria as defined in ITB. The applicant should be a private orgovernment-owned legal entity. For package size exceeding Rs. 10 crore, the Joint Ventures are allowed.
   2. Bidders shall not be under a declaration of ineligibility for corrupt and fraudulent practices by the Central Government, the State Government or any publicundertaking,autonomousbody,authoritybywhatevernamecalledunderthe Central or the StateGovernment.
3. **Qualification of theBidder**
   1. All bidders shall provide in Section 3, Forms of Bid and Qualification information, a preliminary description of the proposed work schedule, including drawings and charts, asnecessary.
      1. Bidder should have valid registration with Employees Provident Fund organization under EPF and Miscellaneous Provisions Act,1952.
   2. All bidders shall include the following information and documents with their bids in Section 3, Qualification Information unless otherwise stated in the Appendix toITB:
4. copies of original documents defining the constitution or legal status, placeofregistration,andprincipalplaceofbusiness;writtenpowerof attorneyofthesignatoryoftheBidtocommittheBidder;
5. totalmonetaryvalueofcivilconstructionworksperformedforeachof the last fiveyears;
6. experience in works of a similar nature and size for each of the last fiveyears,anddetailsofworksinprogressorcontractuallycommitted with certificates from the concerned officer not below the rank of Executive Engineer orequivalent;
7. evidence of ownership of major items of construction equipment named in Clause 4.4 B (b) (i) of ITB or evidence of arrangement of possessing them on hire/lease/buying as definedtherein.
8. details of the technical personnel proposed to be employed for the Contract having the qualifications defined in Clause 4.4 B(b) (ii) of ITB for theconstruction.
9. reports on the financial standing of the Bidder, such as profit and loss statements and auditor's reports for the past threeyears;
10. evidenceofaccesstoline(s)ofcreditandavailabilityofotherfinancial resources/ facilities (10 percent of the contract value) certified by banker(thecertificatebeingnotmorethan3monthsold.)
11. authority to seek references from the Bidder'sbankers;
12. information regarding any litigation or arbitration during the last five years in which the Bidder is involved, the parties concerned, the disputed amount, and thematter;
13. proposals for subcontracting the components of the Works for construction/up-gradation,aggregatingtonotmorethan25percentof theContractPrice;andsubcontractingofpart/fullroutinemaintenance of roads after completion of constructionwork.
14. the proposed programme of construction and Quality Management Plan proposed for completion of the work as per technical specificationsandwithinthestipulatedperiodofcompletion.
    1. Joint Ventures are allowed. Bids submitted by a Joint Venture (JV) of not morethanthreefirmsaspartnersshallcomplywiththefollowingrequirements:
15. There shall be a Joint Venture Agreement (Refer Annexure I to ITB) specific for these contract packages between the constituent firms, indicating clearly, amongst other things, the proposed distribution of responsibilitiesbothfinancialaswellastechnicalforexecutionofthe work amongst them. For the purpose of this clause, the most experienced lead partner will be the one defined. A copy of the Joint Venture agreement in accordance with requirements mentioned in Annexure - I shall be submitted before any award of work could be finalized.
16. The bid, and in the case of the successful bidder, the Form of Agreement,etc.,shallbesignedand/orexecutedinsuchamanneras may be required for making it legally binding on all partners (including operative parts of the ensuing Contract in respect of Agreement of Arbitration, etc.). On award of work, the Form of AgreementandContractDocumentsshallbesignedbyallpartnersof the Joint Venture to conclude ContractAgreement.
17. Lead partner shall be nominated as being partner-in-charge; and this authorization shall be evidenced by submitting a power of attorney signedbythelegallyauthorizedsignatoriesofallthepartners.
18. The partner-in-charge shall be authorized to incur liabilities and to receive instructions for and on behalf of the partners of the Joint Venture, whether jointly or severally, and entire execution of the Contract(includingpayment)shallbecarriedoutexclusivelythrough the partner-in-charge. A copy of the said authorization shall be furnished in thisBid.
19. All partners of the Joint Venture shall be liable jointly and severally for the execution of the Contract in accordance with the Contract terms, and a relevant statement to this effect shall be included in the authorization mentioned under sub clause (c) above as well as in the Form of Tender and the Form of Agreement (in case of a successful bidder).
20. In the event of default by any partner, in the execution of his part of Contract, the Employer shall be so notified within 30 days by the partner-in-charge, or in the case of the partner-in-charge being the defaulter, by the partner nominated as partner-in-charge of the remaining Joint Venture. The partner-in-charge shall, within 60 days of the said notice, assign the work of the defaulting partner to any other equally competent party acceptable to the Employer to ensure the execution of that part of the Contract, as envisaged at the time of bid. Failure to comply with the above provisions will make the Contractor liable for action by the Employer under the Conditions of Contract.IftheMostExperiencedi.e.LeadPartnerdefinedassuchin the Communication approving the qualification defaults, it shall be construed as default of the Contractor and Employer will take action under the Conditions ofContract.
21. Notwithstandingthepermissiontoassigningtheresponsibilitiesofthe defaulting partner to any other equally competent party acceptable to theEmployerasmentionedinsubclause(f)above,allthepartnersof the Joint Venture will retain the full and undivided responsibility for the performance of their obligations under the Contract and/ or for satisfactory completion of theWorks.
22. The bid submitted shall include all the relevant information as requiredundertheprovisionsofSub-Clause4.4ofITBandfurnished separately for eachpartner.
    1. **A** To qualify for award of the Contract, each bidder should have in the last fiveyears:
23. Achieved in any one year, a minimum financial turnover (as certified by Chartered Accountant, and atleast 50% of which is from Civil Engineeringconstructionworks)equivalenttoamountgivenbelow:
    1. 60%ofamountputtobid,incasetheamountputtobidisRs.200 lakhs andless.
    2. 75% of amount put to bid, in case the amount put to bid is more than Rs. 200lakhs.

The amount put to bid above would not include maintenance cost for 5 years and the turnover will be indexed at the rate of 8%per year.

If the bidder has executed road works under Pradhan Mantri Gram Sadak Yojana in originally stipulated completion period, the financial turnover achieved onaccountofexecutionofroadworksunderPMGSYshallbecountedas120%for the purpose of thissub-clause.

In Naxal/Left Wing Extremist Affected Districts, the figures of 60% and 75% in (i) and (ii) above would be replaced by 50%.

1. Satisfactorilycompleted,asprimeContractororsub-contractor,atleast one similar work equal in value to one-third (one-fourth in case of Naxal / LWE affected districts) of the estimated cost of work (excludingmaintenancecostforfiveyears)forwhichthebidisinvited, or such higher amount as may be specified in the Appendix to ITB. The value of road work completed by the bidder under PradhanMantri Gram Sadak Yojana in originally stipulated period of completion shall be counted as120% for the purpose of thisSub-Clause.
   1. **4.4 B (a)** Each bidder mustproduce:
      1. Copy of PAN Card issued by Income TaxAuthorities;
      2. An affidavit that the information furnished with the bid documents is correct in all respects;and
      3. SuchothercertificatesasdefinedintheAppendixtoITB.Failure toproducethecertificatesshallmakethebidnon-responsive.
2. Each bidder mustdemonstrate:
   1. availabilityforconstructionwork,eitherowned,oronleaseoron hire, of the key equipment stated in the Appendix to ITB includingequipmentsrequiredforestablishingfieldlaboratoryto perform mandatory tests, and those stated in the Appendix to ITB;
   2. availabilityforconstructionworkoftechnicalpersonnelasstated in the Appendix toITB.
3. The bidder must not have in hisemployment:
   1. the near relations (defined as first blood relations, and their spouses, of the bidder or the bidder’s spouse) of persons listedin the Appendix toITB.
   2. without Government permission, any person who retired as gazettedofficerwithinthelasttwoyearsoftherankandfromthe departments listed in the Appendix toITB.

**4.4 C** To qualify for a package of contracts made up of this and other contracts for which bids are invited in the Notice Inviting Tender, the bidder must demonstratehavingexperienceandresourcessufficienttomeettheaggregateofthe qualifying criteria for the individualcontracts.

**4.4 D** If bidder is a Joint Venture, the partners would be limited to three (including lead partner). Joint Venture firm shall be jointly and severally responsible for completion of the project. Joint Venture must fulfill the following minimum qualificationrequirement.

* + 1. The lead partner shall meet not less than 50% of qualification criteriagiveninsub-clause4.4A(a)&(b)ofITBabove.
    2. Each of the remaining partners shall meet not less than 25% of all the criteria given in sub-clause 4.4 A (a) & (b) of ITBabove.
    3. The Joint Venture must also collectively satisfy the subject of the criteria of Clause 4.4 B and 4.4 C of ITB for this purpose the relevant figuresforeachofthepartnersshallbeaddedtogethertoarriveattheJoint Venture total capacity which shall be 100% ormore.

iv.. In the event that the Employer has caused to disqualify under Clause

4.7 of ITB below all of the Joint Venture partners will be disqualified.

1. Joint Venture Applicants shall provide a certified copy of the Joint Venture Agreement in demonstration of the partners undertaking joint and several liabilities for the performance of any contract entered into before award ofwork.
2. TheavailablebidcapacityoftheJVasrequiredunderClause4.6of ITB below will be applied for each partner to the extent of his proposed participation in the execution of the work. The total bid capacity available shall be more than estimated contractvalue.
   1. The Sub-Contractors' experience and resources shall not be taken into account in determining the bidder's compliance with the qualifying criteria except to the extent stated in sub-clause 4.3Aabove.
   2. Bidderswhomeettheminimumqualificationcriteriawillbequalifiedonly if their available bid capacity for construction work is equal to or more than the totalbidvalueexcludingmaintenance.Theavailablebidcapacitywillbecalculated asunder:

Assessed Available Bid Capacity = ( A\*N\*M - B )

where

A = Maximum value of civil engineering works executed in any one year during the last five years (updated to the price level of the last year at therateof8percentayear)takingintoaccountthecompletedaswellas works inprogress.

N = Number of years prescribed for completion of the works for which bids are invited (period up to 6 months to be taken as ½ and more than 6 months as 1 in a year).

M = 2 or such higher figure not exceeding 3 as may be specified in the Appendix to ITB.

B = Value, at the current price level, of existing commitments andon-going workstobecompletedduringtheperiodofcompletionoftheworksfor which bids areinvited.

**Note**: The statements showing the value of existing commitments and on-going works as well as the stipulated period of completion remaining for each of the workslistedshouldbecountersignedbytheEngineerincharge,notbelowtherank of an Executive Engineer orequivalent.

* 1. Eventhoughthebiddersmeettheabovequalifyingcriteria,theyaresubject to be disqualified if theyhave:

1. made misleading or false representations in the forms, statements, affidavits and attachments submitted in proof of the qualification requirements;and/or
2. record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc; and /or
3. participatedinthepreviousbiddingforthesameworkandhadquoted unreasonably high or low bid prices and could not furnish rational justification for it to theEmployer.
4. **One Bid perBidder**
   1. EachBiddershallsubmitonlyoneBidforonework.ABidderwhosubmits more than one Bid for one work will cause the proposals with the Bidder's participation to bedisqualified.
5. **Cost ofBidding**
   1. The Bidder shall bear all costs associated with the preparation and submission of his Bid, and the Employer will, in no case, be responsible or liable for thosecosts.
6. **SiteVisit**
   1. The Bidder, at his own cost, responsibility and risk, is encouraged to visit, examine and familiarise himself with the Site of Works.The Bidderacknowledges that prior to the submission of the bid, the Bidder/Contractor has, after a complete and careful examination, made an independent evaluation of the Scope of the Project,SpecificationsandStandardsofdesign,constructionandmaintenance,Site, local conditions, physical qualities of ground, subsoil and geology, suitability and availability of access routes to the Site and all information provided by the Employer or obtained, procured or gathered otherwise, and has determined to its satisfaction the accuracy or otherwise thereof and the nature and extent of difficulties, risks and hazards as are likely to arise or may be faced by it in the course of performance of its obligations hereunder. The Employer makes no representation whatsoever, express, implicit or otherwise, regarding the accuracy, adequacy, correctness, reliability and/or completeness of anyassessment,

assumptions, statement or information provided by it and the Bidder confirms that it shall have no claim whatsoever against the Employer in this regard.

1. ***BiddingDocuments***
2. **Content of BiddingDocuments**
   1. The set of bidding documents comprises the documents listed below and addenda issued in accordance with Clause 10 ofITB.

1 Notice Inviting Tender

2.InstructionstoBidders

3 QualificationInformation 4 Conditions ofContract

(Part I General Conditions of Contract, and Contract Data; Part II Special Conditions of Contract)

1. Specifications
2. Drawings
3. Bill ofQuantities 8 Form ofBid
4. Form of Acceptance, Form of Agreement, Issue of Notice to Proceed with theWork,
5. Forms of Securities and Form of Unconditional BankGuarantee.

**8.2**. The bid document is available online on the website[http://www.pmgsytenders.gov.in.](http://www.pmgsytenders.gov.in/) The bid document can be downloaded free of cost, however, the bidder is required to submit Demand Draft towards cost of bid document in favour of the name given in the Bid Data Sheet.

**8.3** The bidder is expected to examine carefully all instructions, conditions of contract,contractdata,forms,termsandspecifications,billofquantities,formsand drawings in the Bid Document. Failure to comply with the requirements of Bid Documents shall be at the bidder’s own risk. Pursuant to clause 25 hereof, bids, which are not substantially responsive to the requirements of the Bid Documents, shall berejected.

1. **Clarification of Bidding Documents and Pre-bidMeeting**
   1. The electronic bidding system provides for online clarification. A prospectiveBidderrequiringanyclarificationofthebiddingdocumentsmaynotify onlinetheAuthorityinvitingthebid.TheAuthorityinvitingbidwillrespondtoany request (s) for clarification received earlier than 10 days prior to the deadline for submission of bids. Description of clarification sought and the response of the Authority inviting the bid will be uploaded for information of the public or other bidders without identifying the source of request forclarification.
   2. Ifapre-bidmeetingistobeheld,thebidderorhisauthorisedrepresentative isinvitedtoattendit.Itsdate,timeandaddressaregivenintheAppendixtoITB.
   3. Thepurposeofthemeetingwillbetoclarifyissuesandtoanswerquestions on any matter that may be raised at thatstage.
   4. Minutes of the meeting, including the text of the questions raised (without identifyingthesourceoftheenquiry)andtheresponsesgivenwillbeuploadedfor information of the public or other bidders. Any modifications of the bidding documents listed in Clause 8.1 of ITB, which may become necessary as a resultof thepre-bidmeetingshallbemadebytheEmployerexclusivelythroughtheissueof anAddendumpursuanttoClause10ofITBandnotthroughtheminutesofthepre- bidmeeting.
   5. Non-attendance at the pre-bid meeting will not be a cause for disqualification of abidder.
2. **Amendment of BiddingDocuments**
   1. Before the deadline for submission of bids, the Employer may modify the biddingdocumentsbyissuingonlinecorrigendum.Thecorrigendumwillappearon the web page of the website[www.pmgsytenders.gov.in](http://www.pmgsytenders.gov.in/)under the “Latest Corrigendum” and e-mail notification is also automatically sent to those bidders who have moved this tender to their “My tenders”area.
   2. Anyaddendumthusissuedshallbepartofthebiddingdocumentsandshall be deemed to have been communicated to all the bidders who have moved this tendertotheir“MyTenders”area.Incaseanyaddendum/Corrigendum,thesystem will automatically send e-mail to all bidders who have downloaded the bidding document.
   3. To give prospective bidders reasonable time in which to take anaddendum into account in preparing their bids, the Employer shall extend, as necessary, the deadlineforsubmissionofbids,inaccordancewithClause20.2ofITB.
3. ***Preparation ofBids***
4. **Language ofBid**
   1. All documents relating to the Bid shall be in the language specified in the Appendix toITB.
5. **Documents Comprising theBid**
   1. TheBidsubmittedbytheBiddershallbeintwoseparateparts:

**Part I** This shall be named Technical Qualification Part of Bid and shall comprise of:

1. Form of bid for Part I of the bid, as per format given in section 6 (to be submittedonline).
2. ScannedcopyoftheDemandDraftforthecostofthebiddingdocuments.
3. Scanned copy of the Bid Security in any of the forms as specified inclause

16.2 of ITB.

1. Authorized address and contact details of the Bidder having the following information:

Address of communication:

Telephone No.(s): Office:

Mobile No.:

Facsimile (FAX) No.:

Electronic Mail Identification (E-mail ID):

1. Qualification information, supporting documents, scanned copy oforiginal affidavitandundertakingasspecifiedinClause4ofITB.
2. Undertakingthatthebidshallremainvalidfortheperiodspecifiedinclause 15.1ofITB.
3. Any other information/documents required to be completed and submitted by bidders, as specified in the Appendix to ITB,and
4. Scannedcopyoftheaffidavitaffirmingthatinformationhehasfurnishedin the bidding document is correct to the best of knowledge and belief of the bidder.

**Part II.** It shall be named Technical-Financial Part of Bid and shall comprise of:

* 1. FormofBidforPart-IIofthebidasspecifiedinSection6;
  2. Priced bill of quantities for items specified in Section7;
  3. The documents and details mentioned in clause 12.1 Part I above shall be submitted online on website [www.pmgsytenders.gov.in.](http://www.pmgsytenders.gov.in/) Details and process of online submission of the tender and relevant documents are given in the website mentioned above. The above are to be submitted in the manner as prescribed below:

1. Thefollowingdetailsshallbeenteredonlineintheprescribedformats:
   1. FormofbidforTechnicalQualificationPartIofthebid,asperformat given in Section6.
   2. Form of bid for Technical-Financial Part II of the bid, as per format given in Section 6. The entry of rates for individual items of work/percentageratefortheworkshallbemadebythebidderonline.
2. Scanned copies of the following documents shall be uploaded on the website [www.pmgsytenders.gov.in](http://www.pmgsytenders.gov.in/) at the appropriateplace.
   1. DemandDrafttowardstheCostofBidDocument(Clause8.2ofITB)
   2. BidSecurityinanyoftheformsspecifiedinITB(Clause16ofITB)
   3. Copy of PAN Card issued by Income Tax Authorities (Clause 4.4 of ITB)
   4. Contractor Registration certificate (Clause 3 ofITB)
   5. Annual Turnover Certificate from Chartered Accountant for last five financial years with breakup of civil works and total works in each financial year. (Clause 4.4 ofITB)
   6. Affidavitregardingcorrectnessofcertificates(Clause4.4ofITB)
   7. AnyotherdocumentsasspecifiedbytheStateintheBidDataSheet
3. Scanned copies of the Certificates showing details of similar nature of works, work in hand and machineries owned or on lease or possessed on hire should be uploaded after converting the same toPDF.
   1. Similar nature of works executed (Clause 4.4 ofITB)
   2. Works in hand (Clause 4.4 ofITB)
   3. Machineries owned/brought on hire/ lease (Clause 4.4 ofITB)
4. Submission of Original Documents: The bidders are required to submit (i) original Demand Draft towards the cost of bid document and (ii) original bid security in approved form and (iii) original affidavit regarding correctness of information furnished with bid document as per provisions of Clause 4.4 B (a)(ii)ofITBwiththeofficespecifiedintheBidDataSheet,onadatenotlater thanthreeworkingdaysaftertheopeningoftechnicalqualificationpartofthe Bid, either by registered post or by hand. These documents must match the scanned copies submitted along with the bids online. In case, of any deficiency in this respect, it will be treated as mis-representation by such bidder. Such a bidder shall be liable to be debarred for participating in bids under PMGSY for fiveyears.
   1. The following documents, which are not submitted with the bid, will be deemed to be part of thebid.

Section Particulars

1. NoticeInvitingTender
2. InstructionstoBidders
3. ConditionsofContract
4. ContractData
5. Specifications
6. Drawings
7. **BidPrices**

13.1 The Contract shall be for the whole Works, as described in Clause 1.1 of ITB,basedonthepricedBillofQuantitiessubmittedbytheBidderonline.

13.2 The Bidder shall make online entries to fill the Percentage Rate or Item Rates in Bill of Quantities. as specified in the Appendix to ITB; only the same optionisallowedtoalltheBidders.TheBidderisnotrequiredtoquotehisratefor Routine Maintenance. The rates to be paid for routine maintenance by the Employer are indicated in the Bill ofQuantities.

PercentageRateMethodrequiresthebiddertoquoteapercentageabove/below/at parofthescheduleofratesspecifiedintheAppendixtoITB.

Item Rate Method requires the bidder to quote rates and prices for all items of the Works described in the Bill of Quantities. The items for which no rate or price is enteredbytheBidderwillnotbepaidforbytheEmployerwhenexecutedandshall bedeemedcoveredbytheotherratesandpricesintheBillofQuantities.

Upon numerical entry, the amount in words would automatically appear and upon entry of rates in items of work, or upon entering percentage rate, total bid price would automatically be calculated by the system and would be displayed.

* 1. While quoting rates, the GST component shall not be added in rates , while all other duties, taxes , royalties and other levies payable by the contractor under the contract, or for any other cause, shall be included in the rates, prices and total bid price submitted by the bidder.
  2. The rates and prices quoted by the Bidder shall be fixed for the duration of the Contract and shall not be subject toadjustment.

1. **Currencies ofBid**
   1. TheunitratesandthepricesshallbequotedbythebidderentirelyinIndian Rupees.
2. **BidValidity**
   1. Bids shall remain valid for a period of not less than ninety days after the deadline date for bid submission specified in ITB. A bid valid for a shorter period shall be rejected by the Employer asnon-responsive.
   2. In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that the bidders may extend the period of validity for a specified additional period. The request and the bidders’ responses shall be made in writing or by cable. A bidder may refuse the request without forfeiting his Bid Security. A bidder agreeing to the request will not be required or permitted to modify his bid, but will be required to extend the validity of his Bid Security for a period of the extension, and in compliance with Clause 16 of ITB in all respects. For the extended period, the bidder will be paid by the employer an interest onthe amount of bid security at the rate equal to base rate of State Bank of India applicable on the date of expiry of the original timelimit.
3. **BidSecurity**
   1. The Bidder shall furnish, as part of the Bid, Bid Security, in the amount specified in the Appendix toITB.
   2. The Bid Security shall be in the form of Fixed Deposit Receipt of a scheduledcommercialbank,issuedinfavourofthenamegivenintheAppendixto ITB. The Fixed Deposit Receipt shall be valid for minimum 45days beyond the validity of bid. Other forms of Bid Security acceptable to the Employer are stated in the Appendix toITB.
   3. Any bid not accompanied by an acceptable Bid Security, unless exempted intermsgivenintheAppendixtoITBandnotsecuredasindicatedinsub-clause
   4. and 16.2, shall be rejected by the Employer as non-responsive.

16.4 TheBidSecurityofunsuccessfulbidderswillbereturnedwithin28daysof theendoftheBidvalidityperiodspecifiedinClause15.1ofITB.

16.5 The Bid Security of the successful Bidder will be discharged when the BidderhassignedtheAgreementandfurnishedtherequiredPerformanceSecurity.

* 1. The Bid Security may beforfeited:
     1. if the Bidder withdraws the Bid after bid opening (technical qualification bid) during the period of Bidvalidity;
     2. in the case of a successful Bidder, if the Bidder fails within the specified time limitto
        1. sign the Agreement;and/or
        2. furnish the required PerformanceSecurity.

1. **Alternative Proposals byBidders**
   1. Bidders shall submit offers that comply with the requirements of the bidding documents, including the Bill of Quantities and the basic technical design as indicated in the drawings and specifications. Alternative proposals will be rejected asnon-responsive.
2. ***Online Submission ofBids***
3. **Bidding through E-TenderingSystem:**
   1. The bidding under this contract is electronic bid submission through website[www.pmgsytenders.gov.in.](http://www.pmgsytenders.gov.in/) Detailed guidelines for viewing bids and submission of online bids are given on the website. The Invitation for BidsunderPMGSYispublishedonthiswebsite.Anycitizenorprospective bidder can logon to this website and view the Invitation for Bids and can viewthedetailsofworksforwhichbidsareinvited.Theprospectivebidder can submit bids online; however, the bidder is required to have enrolment/registration in the website and should have valid Digital Signature Certificate (DSC) in the form of smart card/e- token. The DSC canbeobtainedfromanyauthorisedcertifyingagencies.Thebiddershould registerinthewebsite[www.pmgsytenders.gov.in](http://www.pmgsytenders.gov.in/)usingtherelevantoption available.ThentheDigitalSignatureregistrationhastobedonewiththee- token, after logging into the site. After this, the bidder can login the site through the secured login by entering the password of the e-token and the user id/ password chosen duringregistration.Aftergettingthebidschedules,theBiddershouldgothroughthemcarefully andthensubmitthedocumentsasasked,otherwise,thebidwillberejected.
   2. The completed bid comprising of documents indicated in ITB clause 12, should be uploaded on the website given above through e-tendering along with scanned copies of requisite certificates as are mentioned in different sectionsinthebiddingdocumentandscannedcopiesoftheBidDocument, Demand Draft and Bid Security in approvedform.
   3. The bidder shall furnish information as described in the Form of Bid on commissionsorgratuities,ifany,paidortobepaidtoagentsrelatingtothe Bid,andtocontractexecutionifthebidderisawardedthecontract.
4. **Electronic Submission ofBids:**
   1. The bidder shall submit online two separate files. Part I, marked as Part I: Technical Qualification Part and Part II; marked as Part II: Technical- FinancialPart.TheabovefileswillhavemarkingsasgivenintheBidData Sheet.

The contents of the Technical Qualification and Technical Financial bid shall be as specified in clause 12 of the ITB. All the documents are required to be signed digitally by the bidder. After electronic on line bid submission,thesystemgeneratesauniquebididentificationnumberwhich is time stamped. This shall be treated as acknowledgement of bid submission.

1. **Deadline for Submission ofBids**
   1. CompleteBidsintwopartsasperclause19abovemustbesubmittedbythe Bidder online not later than the date and time indicated in the Appendix to ITB.
   2. TheEmployermayextendthedeadlineforsubmissionofbidsbyissuingan amendment in accordance with Clause 10.3 of ITB. In such case all rights and obligations of the Employer and the bidders previously subject to the original deadline will then be subject to the newdeadline.
2. **Modification/ Withdrawal/LateBids**
   1. The electronic bidding system would not allow any late submission ofbids after due date and time as per servertime.
   2. Bidders may modify their bids by uploading their request for modification before the deadline for submission of bids. For this, the bidder need not make any additional payment towards the cost of tender document. For bid modificationand consequential re-submission, the bidder is not required to withdraw his bid submitted earlier. The last modified bid submitted by the bidder within the bid submission time shall be considered as the bid. For this purpose, modification/withdrawal by other means will not be accepted. In online system of bid submission, the modification and consequential re-submission of bidsis

allowedanynumberoftimes.Thebiddersmaywithdrawhisbidbyuploadingtheir request before the deadline for submission of bids; however, if the bid is withdrawn, the re-submission of the bid is notallowed.

* 1. No bid shall be modified or withdrawn after the deadline of submission of bids.
  2. Withdrawalormodificationofabidbetweenthedeadlineforsubmissionof bidsandtheexpirationoftheoriginalperiodofbidvalidityspecifiedinclause15.1 aboveorasextendedpursuanttoClause15.2mayresultintheforfeitureoftheBid Security pursuant to Clause16.

1. ***Bid Opening andEvaluation***
2. **BidOpening**
   1. TheEmployerinvitingthebidsoritsauthorisedrepresentativewillopenthe bids online and this could be viewed by the bidders also online. In the event ofthe specified date for the Opening of bids being declared a holiday for the Employer, theBidswillbeopenedattheappointedtimeandlocationonthenextworkingday.
   2. The file containing the Part-I of the bid will be openedfirst.
   3. In all cases, the amount of Bid Security, cost of bid documents, and the validity of the bid shall be scrutinized. Thereafter, the bidders’ names and such other details as the Employer may consider appropriate, will be notified as Part-I bid opening summary by the Authority inviting bids at the online opening. A separateelectronicsummaryoftheopeningisgeneratedandkepton-line.
   4. The Employer will also prepare minutes of the Bid opening, including the information disclosed in accordance with Clause 22.3 of ITB and upload thesame for viewingonline.
   5. Evaluation of Part-I of bids with respect to Bid Security, qualification information and other information furnished in Part I of the bid in pursuant to Clause 12.1 of ITB, shall be taken up and completed within five working days of the date of bid opening, and a list will be drawn up of the qualified bidders whose Part- II of bids are eligible foropening.
   6. The result of evaluation of Part-I of the Bids shall be made public on e- procurement systems following which there will be a period of five working days during which any bidder may submit complaint which shall be considered for resolution before opening Part-II of thebid.
   7. The Employer shall inform the bidders, who have qualified during evaluationofPartIofbids,ofthedate,timeofonlineopeningofPartIIofthebid, if the specified date of opening of financial bid is changed. In the event of the specifieddatebeingdeclaredaholidayfortheEmployer,thebidswillbeopenedat the appointed time and location on the next workingday.
   8. Part II of bids of only those bidders will be opened online, who have qualified in Part I of the bid. The bidders’ names, the Bid prices, the total amount of each bid, and such other details as the Employer may consider appropriate will benotifiedonlinebytheEmployeratthetimeofbidopening.
   9. The Employer shall prepare the minutes of the online opening of Part-II of the Bids and upload the same for viewingonline.
3. **Process to beConfidential**
   1. Information relating to the examination, clarification, evaluation, and comparison of bids and recommendations for the award of a contract shall not be disclosedtobiddersoranyotherpersonsnotofficiallyconcernedwithsuchprocess until the award to the successful Bidder has been announced. Any attempt by a Bidder to influence the Employer’s processing of bids or award decisions may result in the rejection of hisBid
4. **Clarification of Bids and Contacting theEmployer**
   1. NoBiddershallcontacttheEmployeronanymatterrelatingtoitsbidfrom thetimeofthebidopeningtothetimethecontractisawarded.Ifthebidderwishes to bring additional information to the notice of the Employer, it should do so in writing.
   2. Any attempt by the bidder to influence the Employer’s bid evaluation, bid comparisonorcontractawarddecisionmayresultintherejectionofhisbid.
5. **Examination of Bids and Determination ofResponsiveness**
   1. During the detailed evaluation of “Part-I of Bids”, the Employer will determine whether each Bid (a) meets the eligibility criteria defined in Clauses 3 and 4; (b) has been properly signed; (c) is accompanied by the required securities; and (d) is substantially responsive to the requirements of the bidding documents. During the detailed evaluation of the “Part-II of Bids”, the responsiveness of the bids will be further determined with respect to the remaining bid conditions, i.e., priced bill of quantities, technical specifications anddrawings.
   2. Asubstantiallyresponsive“FinancialBid”isonewhichconformstoallthe terms, conditions, and specifications of the bidding documents, without material deviationorreservation.Amaterialdeviationorreservationisone(a)whichaffects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the bidding documents, the Employer’s rights or the Bidder’s obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other bidders presenting substantially responsivebids.
   3. If a Bid is not substantially responsive, it will be rejected by theEmployer, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation orreservation.
6. **Evaluation and Comparison ofBids**
   1. The Employer will evaluate and compare only the bids determined to be substantially responsive in accordance with Clause 25 ofITB.
   2. In evaluating the bids, the Employer will determine for each Bid, the evaluated Bid price by adjusting the bid price through making an appropriate adjustment for any other acceptable variation, deviations or price modifications offered in accordance with sub-clause 21ofITB.
   3. IftheBidofthesuccessfulBidderisseriouslyunbalancedinrelationtothe Engineer’s estimate of the cost of work to be performed under the contract, the Employer may require the Bidder to produce detailed price analysis for any or all items of the Bill of Quantities, to demonstrate the internal consistency of those prices. After evaluation of the price analysis, the Employer may require that the amount of the Performance Security set forth in Clause 30 of ITB be increased at the expense of the successful Bidder to a level sufficient to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract.TheamountoftheincreasedPerformanceSecurityshallbedecidedatthe solediscretionoftheEmployer,whichshallbefinal,bindingandconclusiveonthe bidder.
7. ***Award ofContract***
8. **AwardCriteria**
   1. Subject to Clause 30 of ITB, the Employer will award the Contract to the Bidder whose Bid has beendetermined:
      1. tobesubstantiallyresponsivetothebiddingdocumentsandwhohasoffered the lowest evaluated Bid price, provided that such Bidder has been determined to be (a) eligible in accordance with the provisions of Clause 3 of ITB, and (b) qualified in accordance with the provisions of Clause 4 of ITB;and
      2. to be within the available bid capacity adjusted to account for his bid price whichisevaluatedthelowestinanyofthepackagesopenedearlierthanthe one underconsideration.
9. **Employer’sRighttoAcceptanyBidandtoRejectanyorallBids**
   1. NotwithstandingClause27above,theEmployerreservestherighttoaccept or reject any Bid, and to cancel the bidding process and reject all bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Employer’saction.
10. **Notification of Award and Signing ofAgreement**
    1. The bidder whose Bid has been accepted will be notified of the award bythe Employer prior to expiration of the Bid validity period by cable, telex orfacsimile confirmed by registered letter. This letter (hereinafter and in the Part I *General Conditions of Contract* called the “Letter of Acceptance”) will state the sum that theEmployerwillpaytotheContractorinconsiderationoftheexecution,

completion and the routine maintenance of the works for five years, bythe ContractorasprescribedbytheContract(hereinafterandintheContractcalledthe “ContractPrice”).

* 1. The notification of award will constitute the formation of the Contract, subject only to the furnishing of a Performance Security in accordance with the provisions of Clause30.

**29.3.** The Agreement will incorporate all agreements between the Employer and thesuccessfulBidder.ItwillbesignedbytheEmployerandthesuccessfulBidder after the Performance Security isfurnished.

**29.4** Upon the furnishing by the successful Bidder of the Performance Security, the Employer will promptly notify the other Bidders that their Bids have been unsuccessful.

1. **PerformanceSecurity**
   1. The successful bidder/Contractor shall provide to the Employer, a total Performance Security of 5% (five percent) of the Contract Price, for a period of 5 years and the time of completion of construction work plus additional security for unbalanced bids in accordance with clause 26.3 of ITB and Clause 46 Part-I General Conditions ofContract.

Within 10 days after receipt of Letter of Acceptance but before signing the contract, a Performance Security of two and a half percent of Contract Price plus additional security for unbalanced bids in accordance with clause 26.3 of ITB and Clause 46 Part 1 General Conditions of Contract shall be delivered by the successful bidder to the Employer.

The Employer shall retain remaining two and a half percent Performance Security from each payment due to the Contractor until completion of the whole of the construction works (except advance payment as per Clause 45 of General Conditions of Contract).

* 1. Performance Security of two and a half percent to be delivered by the successful bidder after the receipt of Letter of Acceptance shall be either in the form of a Bank Guarantee or Fixed Deposit Receipts in the name of Employer, from a scheduled commercialbank.

If the Performance Security is in the form of a Bank Guarantee, the period of validity of Bank Guarantee of two and a half percent of Contract Price couldbe one year initially, however, the Contractor shall get this Bank Guaranteeextended insuchawaythatanamountequaltotherequisitePerformanceSecurityisalways available with the Employer until 45 days after the lapse of Defects Liability Period. If the Contractor fails to maintain above Performance Security, the EmployerwouldrecoverthesamefromanyduespayabletotheContractor.

* 1. Failure of successful bidder to comply with the requirement of delivery of Performance Security of two and a half percent of Contract Price plus additional security for unbalanced bids as per provisions of Clause 30.1shallconstitute

sufficientgroundforcancellationofawardandforfeitureoftheBidSecurity.Such successful bidder who fails to comply with the above requirements is liable to be debarredfromparticipatinginbidsunderPMGSYforaperiodofoneyear.

1. **Advances**

TheEmployerwillprovideMobilizationAdvanceandAdvanceagainstthesecurity ofequipmentasprovidedinPartIGeneralConditionsofContract.

1. **Corrupt or FraudulentPractices**

32.1 The Employer requires the Bidders/Contractors to strictly observe thelaws against fraud and corruption in force in India, namely, Prevention of Corruption Act,1988.

* 1. It is required that each Bidder/Contractor (including their respective officers, employees and sub-contractors) adhere to the highest ethical standards, andreporttotheGovernment/Departmentallsuspectedactsoffraudorcorruption or coercion or collusion of which it has knowledge or becomes aware, during the tenderingprocessandthroughoutthenegotiationorawardofacontract.
  2. TheBidder(s)/Contractor(s)commithimselftotakeallmeasuresnecessary to prevent corruption. He commits himself to observe the following principles duringhisparticipationintheTenderprocessandduringtheContractexecution:

1. The Bidder(s)/Contractor(s) will not, directly or through any other person or firm, offer, promise or give to any employee of the Employer involved in the Tender process or execution of the Contract or to any third person any material or other benefit which he/she is not legally entitled to, in order to obtain in exchange any advantage of any kind whatsoever during the Tender process or during the execution of theContract.
2. The Bidder(s)/Contractor(s) will not enter with other Bidder(s) into any undisclosed agreement or understanding, whether formal or informal. This applies in particular to prices, specifications, certifications,subsidiarycontracts,submissionornon-submissionof bidsoranyotheractionstorestrictcompetitivenessortocartelizein the biddingprocess.
3. The Bidder(s)/Contractor(s) will not commit any offence under the relevant IPC/PC Act. Further the Bidder(s)/Contractor(s) will not useimproperly,(forthepurposeofcompetitionorpersonalgain),or pass on to others, any information or documents provided by the Employer as part of the business relationship, regarding plans, technical proposals and business details, including information contained or transmittedelectronically.
4. The Bidder(s)/Contractor(s) will, when presenting his bid, disclose any and all payments he has made, is committed to or intends to make to agents, brokers or any other intermediaries in connection with the award of theContract.
   1. The Bidder(s)/Contractor(s) will not instigate third persons to commit offences outlined above or be an accessory to suchoffences.
   2. TheBidder(s)/Contractor(s)willnot,directlyorthroughanyotherpersonor firm indulge in Fraudulent Practice, which means a willful misrepresentation or omissionoffactsorsubmissionoffake/forgeddocumentsinordertoinducepublic officialtoactinreliancethereof,withthepurposeofobtainingunjustadvantageby or causing damage to justified interest of others and/or to influence the procurement process to the detriment of the Government interests. And, this includes collusive practice among Bidders (prior to or after bid submission) designedtoestablishbidprocessatartificialnon-competitivelevelsandtodeprive the Employer of the benefits of free and opencompetition.The Employer reserves the right to disqualify a bidder for a suitable period who habitually failed to perform in time. The Employer reserves the right to disqualify a bidder for a suitable period who does not perform satisfactorily in the field in accordance with the specification laid down in the contract. The Employer reserves the right to disqualify a bidder for a suitable period who failed to honour the bid without  sufficient grounds.
   3. The Bidder(s)/Contractor(s) will not, directly or through any other person or firm use Coercive Practices (means the act of obtaining something, compelling an action or influencing a decision through intimidation, threat or the use of force directlyorindirectly,wherepotentialoractualinjurymaybefalluponaperson,his/ herreputationorpropertytoinfluencetheirparticipationinthetenderingprocess).
   4. WithoutprejudicetoanyrightsthatmaybeavailabletotheEmployerunder law or the Contract or its established policies and laid down procedures, the EmployershallhavethefollowingrightsincaseofbreachunderClauses32.1toabove by the Bidder(s)/Contractor(s) and the Bidder/ Contractor accepts and undertakes to respect and uphold the Employer absoluteright:
      1. If the Bidder(s)/Contractor(s), either before award or during execution of Contract has committed a transgression through a violation of Clauses 32.1 to 32.6 above or in any other form, such as to put his reliability or credibility in question, the Employer after giving proper opportunity to the Bidder(s)/Contractor(s) shall have powers to disqualify the Bidder(s)/Contractor(s) from the Tender process or terminate the Contract, if already executed or exclude the Bidder/Contractor from future contract awardprocesses.
      2. Forfeiture of Bid Security/Performance Security: If the Employer has disqualifiedtheBidder(s)fromtheTenderprocesspriortotheawardof the Contract or terminated the Contract or has accrued the right to terminate the Contract, the Employer apart from exercising any legal rights that may have accrued to the Employer, may in its considered opinion forfeit the entire amount of Bid Security and Performance Security of the Bidder/Contractor as the case maybe.

**Annexure I**

Provisions Required to be Included in the Joint Venture Agreement

If the application is made by a joint venture of two or more firms, the evidence of clear mandate (i.e. in the form of respective Board Resolution duly authenticated by competent authority\*) by such two or more firms willing to form JointVentureamongthemselvesforthespecifiedprojectsshouldaccompanyduly recognising their respective authorised signatories signing for and on behalf ofthe respective Firms for the purpose of forming the Joint Venture. A certified copy of the power of attorney to the authorized representatives, signed by legally authorized signatories of all the firms of the joint venture shall accompany the application. The JV Agreement shall be signed by the authorized representativeof the joint venture. The JV Agreement shall need to be submitted consisting but not limited to the followingprovisions:

1. Name, style and Project(s) specific JV with Head Officeaddress
2. Extent (or Equity) of participation of each party in theJV
3. Commitment of each party to furnish the Bond money (i.e. Bid Security, performanceSecurityandsecurityforMobilisationadvance)totheextentofhis participation in theJV
4. Responsibility of each Partner of JV (in terms of Physical and Financial involvement)
5. Working Capital arrangement ofJV
6. OperationofseparateBankaccountinthenameofJVtobeoperatedbyatleast one foreign partner and one local partner. In case of JV among local partners, both the partners are required tooperate.

g Provision for cure in case of non-performance of responsibility by any party of the JV.

1. ProvisionthatNEITHERpartyoftheJVshallbeallowedtosign,pledge,sellor otherwise dispose all or part of its respective interests in JV to any party including existing partner(s) of the JV The Employer derives right for any consequent action (including blacklisting) against any or all JV partners incase of any breach in thisregard.
2. Management Structure of JV withdetails
3. Lead Partner to be identified who shall be empowered by the JV to incur liabilities on behalf ofJV
4. Parties/firms committing themselves to the Employer for jointly and severally responsible for the intendedworks
5. The Power of Attorney shall be dulynotarized.
6. Any other relevantdetails

***Appendix to ITB***

TheEmployershouldfilloutthisAppendixtoITBbeforeissuingthebiddingdocuments. TheinsertionsshouldcorrespondtotheinformationprovidedintheInvitationforBids.

Instructions to Bidders Clause Reference

(1.1) TheEmployer

is

*[Insert designation of the Employer.]*

(1.1) TheWorksis *[nameandsummary description of theWorks.]*

(1.1) Identification No. of the Worksis:

(2.1) The Stateis

(3.1) Eligible Biddersare:

(4.4 **A**) (b)

*[inserttheamountifitismorethanone-thirdof the estimated cost ofworks.]*

(4.4.**B**)(b)(i) Thekeyequipmentsforroadworksandfieldtestinglaboratory Road Worksare:

**For Road Works**

Name oftheEquipment Quantity

**For field testing Laboratory**

Name oftheEquipment Quantity

Note:(a)Thebiddermustproducethefollowingdocumentary evidenceinsupportofhisavailabilityoftheaboveequipment:

----------------------------------------------------------------------

----------------------------------------------------------------------

(4.4 B)(b)(ii) TheNumberofTechnicalpersonnel,Qualificationsand Experience will be as follows:

* 1. The Technical Personnelare:

[Cl. 9.2 of General Conditions of Contract]

|  |  |  |
| --- | --- | --- |
| Technical Personnel | Number | Experience in RoadWorks |
| 1. DegreeHolderinCivil Engineering 2. DiplomaHolderinCivil Engineering 3. Others(Specify) |  |  |

* 1. For field testing laboratory;

---------------------------------

---------------------------------

(4.4 **B**)(c)(i) Thebiddermustproduceanaffidavitstatingthatthenear

relationsofthefollowingdepartmentalofficersarenotinhis employment:

(4.4 **B**)(c)(ii) The bidder must produce an affidavit stating the names of retired gazetted officer (if any) in his employment who retired within the last two years with the following ranks from the departments listedbelow:

---------------------------------------------

---------------------------------------------

In case there is no such person in his employment, his affidavit should clearly state this fact.

(4.6) M=

(7.1) The contact personis: Designation:

Address:

Telephone No.

(9.2) Place,TimeandDateforpre-bidmeetingare: Place: Time: Date:

(11.1) Language of the bidis:

(12.1) Part I (v)

(13.2.) Bidsmaybesubmittedonlyinoneofthefollowing: Percentage RateMethod

Item Rate Method

[Delete whatever is not applicable.]

(13.2)

(15.1)

ScheduleofRateapplicableforPercentageRateMethodis: Bid validitydate:............................

(16.1) TheamountofBidSecurityshallbeRs. *[insert theamountinfigureandwords.Note:Thisamountis2percent of estimated value of the Works, rounded off to the nearest thousand.Forreasonsofconfidentiality,afixedsumshouldbe specified,inpreferencetoapercentageofthebidprice.]*

(16.2) FixedDepositReceiptmustbedrawn: In favourof:

(16.2) OtheracceptableformsofBidSecuritypledgedinfavourof

are

(16.3) Exemption from Bid Security is grantedto:

(20.1) TheEmployer'saddressforthepurposeofBidsubmissionis

*[insertthe*

*receiving address provided in the Invitation for Bids.]*

(20.1) Thedeadlineforsubmissionofbidsshallbe: Time

Date

(22.1)&(22.6) The date and time for opening of the Bidsare:

1. Technical Qualification Part ofBid

Date Time

1. TechnicalFinancialPartofBid(Forqualifiedbidderas) Date

Time

1. PerformanceSecurityshallbevaliduntiladate45daysafter the expiry of Defects Liability Period of 5 years after intended completiondate.
2. Additional Performance Security for unbalanced Bid shall bevalidfor45daysplusintendedcompletionperiod.

##### Signature of Employer/ Authorised Signatory

Date

1.3 2

1.3 1

# Section 3 Qualification Information

**Notes on Form of Qualification Information**

The information to be filled in by bidders in the following pages will be used for purposes of post-qualification as provided for in Clause 4 of the Instructions to Bidders. This information will not be incorporated in the Contract. Attach additional pages as necessary.

##### 1. Individual Bidders

|  |  |  |
| --- | --- | --- |
| 1.1 | Constitution or legal status of Bidder  Place of registration: Principal place of business:  Power of attorney of signatory of Bid | *[attach copy]*  *[attach]* |
| 1.2 | Total annual volume of civil | **(Rs. In lakhs)** |
|  | engineering construction work | Year |
|  | executed and payments received | Year |
|  | in the last five years preceding the | Year |
|  | year in which bids are invited. | Year |
|  | (Attach certificate from Chartered | Year |
|  | Accountant) |  |

Work performed as prime Contractor (in the same name and style) on construction works of a similar nature and volume over the last five years. Attach certificate from the Engineer-in-charge

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name | Name of Employer | Description of work | Value of contract | Contract No. | Date of Issue of Work Order | Stipulated Date of Completion | Actual Date of Completion | Remarks explaining reasons for Delay, if any |
|  |  |  |  |  |  |  |  |  |

Work performed as Sub-Contractor (in the same name and style) on construction works of a similar nature and volume over the last five years. Attach certificate from the Engineer-in-charge

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name | Name of Employer | Descript ion of work | Value of contract | Contr act No. | Date of Issue of Work Order | Stipulated Date of Completio n | Actual Date of Compl etion | Remar ks explai ning reason s for Delay, if any |
|  |  |  |  |  |  |  |  |  |

1.3.3 Information on Bid Capacity (works for which bids have been submitted and works which are yet to be completed) as on the date of thisbid.

**Existing commitments and on-going construction works:**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Description of Work | Place & State | Contract No & Date | Name &Address of Employer | Value of Contract (Rs. In lakhs) | Stipulated period of completion | Value of works remaining to be  completed (Rs.  Lakhs) \* | Anticipated Date of completion |
| (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) |
|  |  |  |  |  |  |  |  |

* *Enclose certificate(s) from Engineer(s)-in-charge for value of work remaining to be completed.*
  1. Availability of Major items of Contractor's Equipment proposed for carrying out the Works. List all information requested below. Refer also to Clause 4.2(d) and Clause 4.4B (b) of the Instructions toBidders.

|  |  |  |  |
| --- | --- | --- | --- |
| Item of Equipment | Description, make, and age (Years), and capacity | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased |
|  |  |  |  |

* 1. Qualifications of technical personnel proposed for the Contract. Refer also to Clause 4.2(e) of the Instructions to Bidders and Clause 9.2 of Part-I General Conditions ofContract.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Position | Name | Qualification | Years of experience | | |
| Road Works | Building Works | Other |
|  |  |  |  |  |  |

* 1. Proposed sub-contractors and firms involved for construction. Refer to Clause 7 of Part I General Conditions ofContract.

|  |  |  |  |
| --- | --- | --- | --- |
| Sections of the Works | Value of subcontract | Sub- contractor(name and address) | Experience in similar work |
|  |  |  |  |

Note: The capability of the sub-Contractor will also be assessed (on the same lines as for the main Contractor) before according approval to him.

* 1. Financial reports for the last five years: balance sheets, profit and loss statements, auditors' reports, etc. List below and attachcopies.
  2. Name, address, and telephone, telex, and facsimile numbers of banks that may provide references if contacted by theEmployer.
  3. Information on current litigation in which the Bidder isinvolved.

|  |  |  |  |
| --- | --- | --- | --- |
| Name of Other party(s) | Cause of dispute | Litigation where (Court/arbitration) | Amount involved (Rs. In Lakh) |
|  |  |  |  |

* 1. Proposed Programme. Descriptions, drawings, and charts as necessary, to comply with the requirements of the biddingdocuments.

# Section 4 Conditions of Contract

### Part – I General Conditions of Contract

The Conditions of Contract, read in conjunction with Part II Special Conditions of Contract and the Contract Data and other documents listed therein, should be a complete document expressing fairly the rights and obligations of both parties. The conditions of contract provide for both construction and routine maintenance.

##### A. General

* + 1. Definitions
    2. Interpretation
    3. Language and Law
    4. Engineer'sDecisions
    5. Delegation
    6. Communications
    7. Subcontracting
    8. Other Contractors
    9. Personnel

# Table of Clauses

1. Correction ofDefects
2. UncorrectedDefects

##### Cost Control

1. Bill of Quantities
2. Variations
3. Payments forVariations
4. Cash FlowForecasts
5. PaymentCertificates
6. Payments
7. CompensationEvents
   1. Employer's and Contractor's Risks
   2. Employer'sRisks
   3. Contractor'sRisks
   4. Insurance
   5. Site Investigation Reports
   6. Queries about the Contract Data
   7. Contractor to Construct the Works and domaintenance
   8. The Works to Be Completed by the Intended CompletionDate
   9. Approval by the Engineer
   10. Safety
   11. Discoveries
   12. Possession of theSite
   13. Access to theSite
   14. Instructions
   15. Dispute RedressalSystem
   16. Arbitration

##### Time Control

* 1. Programme
  2. Extension of the Intended CompletionDate
  3. Delays Ordered by theEngineer
  4. ManagementMeetings

##### QualityControl

* 1. IdentifyingDefects
  2. Tests

1. Tax
2. Currencies
3. SecurityDeposit
4. LiquidatedDamages
5. AdvancePayment
6. Securities
7. Cost of Repairs

##### Finishing the Contract

1. Completion of Construction andMaintenance
2. TakingOver
3. Final Account
4. Operating and Maintenance Manuals
5. Termination
6. Payment uponTermination
7. Property

55 Release from Performance

##### Other Conditions ofContract

1. Labour
2. Compliance with Labour Regulations
3. Drawings and Photographs of theWorks
4. The Apprenticeship Act,1961

# Section 4

### Part I General Conditions of Contract

##### General

* 1. **Definitions**
     1. Terms which are defined in the Contract Data are not also defined in the Conditions of Contract but keep their defined meanings. Capital initials are used to identify definedterms.

**Bill of Quantities** means the priced and completed Bill of Quantities forming part of the Bid.

**Compensation Events** are those defined in Clause 40 hereunder.

**The Completion Date** is the date of completion of the Works as certified by the Engineer, in accordance with Clause 48.1.

**The Contract** is the Contract between the Employer and the Contractor to execute, complete, and maintain the Works. It consists of the documents listed in Clause 2.3.

**The Contract Data** defines the documents and other information which comprise the Contract.

**The Contractor** is a person or corporate body whose Bid to carry out the Works, including routine maintenance, has been accepted by the Employer.

**The Contractor's Bid** is the completed bidding document submitted by the Contractor to the Employer.

**The Contract Price** is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of theContract.

**Days** are calendar days; months are calendar months.

A **Defect** is any part of the Works not completed in accordance with the Contract.

**The Defects Liability Certificate** is the certificate issued by the Engineer, after the Defects Liability Period has ended and upon correction of Defects by the Contractor.

**The Defects Liability Period** is five years calculated from the Completion Date.

**Drawings** include calculations and other information provided or approved by the Engineer for the execution of theContract.

**The Employer** is the party as defined in the Contract Data, who employs the Contractor to carry out the Works, including routine maintenance. The Employer may delegate any or all functions to a person or body nominated by him for specified functions.

**The Engineer** is the person named in the Contract Data (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Engineer) who is responsible for supervising the execution of the Works and administering the Contract.

**Equipment** is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works.

**The Initial Contract Price** is the Contract Price listed in the Employer's Letter of Acceptance.

**The Intended Completion Date** is the date on which it is intended that the Contractor shall complete the Works. The Intended Completion Date is specified in the Contract Data. The Intended Completion Date may be revised only by the Engineer by issuing an extension of time.

**Materials** are all supplies, including consumables, used by the Contractor for incorporation in the Works.

**Plant** is any integral part of the Works that shall have a mechanical, electrical, electronic, chemical, or biological function.

**Routine Maintenance** is the maintenance of roads for five years as specified in the Contract Data.

The **Site** is the area defined as such in the Contract Data.

**Site Investigation Reports** are those that were included in the bidding documents and are reports about the surface and subsurface conditions at the Site.

**Specifications** mean the Specifications for Rural Roads of Ministry of Rural Development (2014).

The **Start Date** is given in the Contract Data. It is the date when the Contractor shall commence execution of the Works.

A **Sub-Contractor** is a person or corporate body who has a Contract with the Contractor to carry out a part of the construction work and/or routine maintenance in the Contract, which includes work on the Site.

**Temporary Works** are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works.

A **Variation** is an instruction given by the Engineer, which varies the Works.

The **Works,** as defined in the Contract Data, are what the Contract requires the Contractor to construct, install, maintain, and hand over to the Employer. Routine maintenance is defined separately.

##### Interpretation

* 1. In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter, and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract unless specifically defined. The Engineer will provide instructions clarifying queries about these Conditions ofContract.
  2. If sectional completion is specified in the Contract Data, references in the Conditions of Contract to the Works, the Completion Date, and the Intended Completion Date apply to any Section of the Works (other than references to the Completion Date and Intended Completion Date for the whole of theWorks).
  3. The documents forming the Contract are to be taken as mutually explanatory, and unless otherwise expressly provided elsewhere in the Contract, the priority of the documents, in the event of any ambiguity between them, shall be interpreted in the following order of priority:
     + 1. Agreement,
       2. Notice to Proceed with theWork,
       3. Letter ofAcceptance,
       4. Contractor'sBid,
       5. Contract Data,
       6. Special Conditions of Contract PartII,
       7. General Conditions of Contract PartI,
       8. Specifications,
       9. Drawings,
       10. Bill of Quantities, and
       11. Any other document listed in the ContractData.

##### Language and Law

* 1. The language of the Contract and the law governing the Contract are stated in the Contract Data.

##### Engineer'sDecisions

* 1. Except where otherwise specifically stated, the Engineer will decide contractual matters between the Employer and the Contractor in the role representing the Employer. However, if the Engineer is required under the rules and regulations and orders of the Employer to obtain approval of some other authorities for specific actions, he will so obtain the approval.

4.2 Except as expressly stated in the Contract, the Engineer shall not have any authority to relieve the Contractor of any of his obligations under theContract.

##### Delegation

* 1. The Engineer, with the approval of the Employer, may delegate any of his duties and responsibilities to other person, after notifying the Contractor, and may cancel any delegation after notifying the Contractor.

##### Communications

* 1. All certificates, notices or instructions to be given to the Contractor by the Employer/ Engineer shall be sent on the address or contact details given by the Contractor in Section 6 - Form of Bid. The address and contact details for communication with the Employer/ Engineer shall be as per the details given in Contract Data to GCC. Communications between parties that are referred to in the conditions shall be in writing. The Notice sent by facsimile (fax) or other electronic means shall be effective on confirmation of the transmission. The Notice sent by Registered post or Speed post shall be effective on delivery or at the expiry of the normal delivery period as undertaken by the postalservice.

##### Subcontracting

* 1. The Contractor may subcontract part of the construction work with the approval of the Employer in writing, up to 25 percent of the contract price, also part or full routine maintenance work after completion of construction work but will not assign the Contract. It is expressly agreed that the Contractor shall, at all times, be responsible and liable for all his obligations under this Agreement notwithstanding anything contained in the agreements with his Sub-contractors or any other agreement that may be entered into by the Contractor and no default under any such agreement shall exempt the Contractor from his obligations or liability hereunder.
  2. The Contractor shall not be required to obtain any consent from the Employerfor:

1. the sub-contracting of any part of the Works for which the Sub-Contractor is named in theContract;
2. the provision for labour, or labourcomponent.
3. the purchase of Materials which are in accordance with the standards specified in the Contract.
   1. Beyond what has been stated in clauses 7.1 and 7.2, if the Contractor proposes sub- contracting any part of the work or full routine maintenance for five years, during execution of the Works, the Employer will consider the following before accordingapproval:
4. The Contractor shall not sub-contract the whole of theWorks.
5. The Contractor shall not sub-contract any part of the Works without prior consent of the Employer. Any such consent shall not relieve the Contractor from any liability or obligation under the Contract and he shall be responsible fortheacts,defaultsandneglectsofanyofhissub-Contractor,hisagentsor

workmen as fully as if they were the acts, defaults or neglects of the Contractor, his agents and workmen.

* 1. The Engineer should satisfy himself before recommending to the Employer whether the Sub-Contractor so proposed for the Works possesses the experience, qualifications and equipment necessary for the job proposed to be entrusted to him in proportion to the quantum of Works to besub-contracted.
  2. Whilesub-contractingpartofconstructionworkasperprovisionsofClause7.1and

above, the Contractor shall enter into formal sub-contract with sub-contractor making provisions for such requirements as may be specified by the Engineer including a condition that to the extent of inconsistency, provision of the Contract shall prevail over the provisions of the sub-contract. A copy of document of formal sub-contract shall be furnished to the Employer within a period of 30 days from the date of such sub-contract. In all such cases, on completion of the Contract, the Engineer, unless for reasons recorded in writing decides otherwise shall issue a Certificate of Experience to the contractor and in such certificate, the experience of the sub-contractors shall also be mentioned. The Copy of such certificate would also be endorsed to thesub-contractor.

##### Other Contractors

* 1. The Contractor shall cooperate and share the Site with Other Contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the Contract Data. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors, and shall notify the Contractor of any suchmodification.
  2. The Contractor should take up the works in convenient reaches as decided by the Engineer to ensure there is least hindrance to the smooth flow of traffic including movement of vehicles and equipment of Other Contractors till the completion of theWorks.

##### Personnel

* 1. The Contractor shall ensure that the personnel engaged by it in the performance of its obligations under this Contract are at all times appropriately qualified, skilled and experienced in their respectivefunctions.
  2. The Contractor shall employ for the construction work and routine maintenance, the technical personnel named in the Contract Data or other technical persons approved by the Engineer. The Engineer will approve any proposed replacement of technical personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel stated in the ContractData.
  3. If the Engineer asks the Contractor to remove a person who is a member of the Contractor's staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the Works in the Contract. The Contractor shall then appoint (or cause to be appointed) areplacement.
  4. The Contractor shall not employ any retired Gazetted officer who has worked in the Engineering Department of the State Government and has either not completed two years after the date of retirement or has not obtained State Government’s permission for employment with the Contractor.
  5. The Engineer may require the Contractor to remove (or cause to be removed) any person employed on the Site or Works, including the Contractor's Representative, who in the opinion of theEngineer:

1. persists in anymisconduct,
2. is incompetent or negligent in the performance of hisduties,
3. fails to conform with any provisions of the Contract,or
4. persists in any conduct which is prejudicial to safety, health, or the protection of theenvironment.

##### Employer's and Contractor'sRisks

* 1. The Employer carries the risks which this Contract states are Employer's risks, and the Contractor carries the risks which this Contract states are Contractor'srisks.

##### 11. Employer's Risks

* 1. The Employer is responsible for the excepted risks which are (a) in so far as they directly affect the execution of the Works in the Employer’s country, the risks of war, invasion, act of foreign enemies, rebellion, revolution, insurrection or military or usurped power, civil war, riot commotion or disorder (unless restricted to the Contractor’s employees) and contamination from any nuclear fuel or nuclear waste or radioactive toxic explosive, or (b) a cause due solely to the design of the Works, other than the Contractor’sdesign.

##### Contractor's Risks

* 1. All risks of loss of or damage to physical property and of personal injury and death which arise during and in consequence of the performance of the Contract other than the excepted risks, referred to in clause 11.1, are the responsibility of theContractor.

##### Insurance

* 1. The Contractor at his cost shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the date of completion, in the amounts and deductibles stated in the Contract Data for the following events which are due to the Contractor'srisks:

1. loss of or damage to the Works, Plant andMaterials;
2. loss of or damage toEquipment;
3. loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract;and
4. Personal injury ordeath.
   1. Insurance policies and certificates for insurance shall be delivered by the Contractor to the Engineer for the Engineer's approval before the Start Date. All such insuranceshall provide for compensation to be payable in Indian Rupees to rectify the loss or damage incurred.
   2. **(a)** The Contractor at his cost shall also provide, in the joint names of the Employer and the Contractor, insurance cover from the date of completion to the end of Defects Liability Period, in the amounts and deductibles stated in the Contract Data for personal injury or death which are due to the Contractor'srisks:

**13.3 (b)** Insurance policies and certificates for insurance shall be delivered by the Contractor to the Engineer for approval before the completion date/start date. All such insurance shall provide for compensation to be payable in IndianRupees.

* 1. Alterations to the terms of insurance shall not be made without the approval of the Employer.
  2. Both parties shall comply with any conditions of the insurancepolicies.

##### Site Investigation Reports

* 1. The Contractor, in preparing the Bid, may, at his own risk, rely on any Site Investigation Reports if referred to in the Contract Data, supplemented by any other information available to him, before submitting thebid.

##### Queries about the Contract Data

* 1. The Engineer will clarify queries on the ContractData.

##### Contractor to Construct the Works and domaintenance

* 1. The Contractor shall construct, and install and maintain the Works and do the work of routine maintenance in accordance with the Specifications andDrawings.

##### The Works to Be Completed by the Intended CompletionDate

* 1. The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Programme submitted by the Contractor, as updated with the approval of the Engineer, and complete them by the Intended Completion Date.

##### Approval by the Engineer

* 1. The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Engineer, who is to approvethem.
  2. The Contractor shall be responsible for design and safety of TemporaryWorks.
  3. The Engineer's approval shall not alter the Contractor's responsibility for design and safety of the TemporaryWorks.
  4. The Contractor shall obtain approval of third parties to the design and safety of the Temporary Works, whererequired.
  5. All Drawings prepared by the Contractor for the execution of the temporary or permanent Works, are subject to prior approval by the Engineer before theiruse.

##### Safety

* 1. The Contractor shall be responsible for the safety of all activities on theSite.
  2. The Contractor shall be responsible for safety of all persons, employed by him on Works, directly or through petty contractors or Sub-Contractors, and shall report accidents to any of them, however, and wherever occurring on Works, to the Engineer or the Engineer’s Representative, and shall make every arrangement to render all possible assistance and to provide prompt and proper medical attention. The compensation for affected Workers or their relatives shall be paid by the Contractor in such cases expeditiously in accordance with the Workmen’s Compensation Act and other labour Laws andregulations.

##### Discoveries

* 1. Anything of historical or other interest or of significant value unexpectedly discovered on the Site shall be the property of the Employer. The Contractor shall notify the Engineer of such discoveries and carry out the Engineer's instructions for dealing withthem.

##### 21. Possession of theSite

* 1. The Employer shall handover complete or part possession of the site to the Contractor seven days in advance of construction programme. At the start of the work, the Employer shall handover the possession of at least 75% of thesite.

##### Access to theSite

* 1. The Contractor shall allow access to the Site and to any place where work in connection with the Contract is being carried out, or is intended to be carried out to the Engineer and any person/persons/agency authorizedby:

1. TheEngineer
2. TheEmployer
3. The Ministry of Rural Development, Government ofIndia.
4. The National Rural Roads Development Agency, Government ofIndia

##### Instructions

* 1. The Contractor shall carry out all instructions of the Engineer, which comply with the applicable laws where the Site islocated.

##### Dispute Redressal System

* 1. If any dispute or difference of any kind what-so-ever shall arise in connection with or arising out of this Contract or the execution of Works or maintenance of the Works there under, whether before its commencement or during the progress of Works or after the termination, abandonment or breach of the Contract, it shall, in the first instance, be referred for settlement to the competent authority within 45 days of arising of the dispute or difference, described along with their powers in the Contract Data, above the rank of the Engineer. The competent authority shall, within a period of forty-five days after being requested in writing by the Contractor to do so, convey his decision to the Contractor. Such decision in respect of every matter so referred shall, subject to review as hereinafter provided, be final and binding upon the Contractor. In case the Works is already in progress, the Contractor shall proceed with the execution of the Works, including maintenance thereof, pending receipt of the decision of the competent authority as aforesaid, with all duediligence.
  2. Either party will have the right of appeal, against the decision of the competent authority, to the Standing Empowered Committee within 90 days of decision of the competent authority if the amount appealed against exceeds 0.20 (zero point two zero) percent of the initial contractprice.
  3. The composition of the Empowered Standing Committee willbe:

1. One official member, Chairman of the Standing Empowered Committee, not below the rank of Additional Secretary to the StateGovernment;
2. One official member not below the rank of additional chief engineer;and
3. One non-official member who will be technical expert of Chief Engineer’s or Superintending Engineer’s level selected by the Contractor from a panel of three persons given to him by theEmployer.
   1. The Contractor and the Employer will be entitled to present their case in writing duly supported by documents. If so requested, the Standing Empowered Committee may allow one opportunity to the Contractor and the Employer for oral arguments for a specified period. The Empowered Committee shall give its decision within a period of ninety days from the date of appeal, failing which the Contractor can approach the appropriate court for the resolution of thedispute.
   2. The decision of the Standing Empowered Committee will be binding on the Employer for payment of claims up to five percent of the Initial Contract Price. The Contractor can accept and receive payment after signing as “in full and final settlement of all claims”. If he does not accept the decision, he is not barred from approaching the courts. Similarly, if the Employer does not accept the decision of the Standing Empowered Committee above thelimit

of five percent of the Initial Contract Price, he will be free to approach the courts applicable under the law.

##### Arbitration

* 1. In view of the provision of the clause 24 on Dispute Redressal System, it is the condition of the Contract that there will be no arbitration for the settlement of any dispute between theparties.

1. ***TimeControl***

**26. Programme**

* 1. Within the time stated in the Contract Data, the Contractor shall submit to the Engineer for approval a Programme showing the general methods, arrangements, order, and timing for all the activities in the Works, for the construction of works. After the completion of the construction works, the programme for the Routine Maintenance Work, showing the general methods, arrangements, order and timing for all the activities involved in the Routine Maintenance will also be submitted by the Contractor to the Engineer for approval. The programme for Routine Maintenance will be submitted in each year for the period of Maintenance.
  2. The Contractor shall submit the list of equipment and machinery being brought to site, the list of key personnel being deployed, the list of machinery/ equipments being placed in field laboratory and the location of field laboratory along with the Programme. The Engineer shall cause these details to be verified at each appropriate stage of theprogramme.
  3. An update of the Programme shall be a programme showing the actual progress achieved on each activity and the effect of the progress achieved on the timing of the remaining Works, including any changes to the sequence of theactivities.
  4. The Contractor shall submit to the Engineer for approval an updated Programme at intervals no longer than the period stated in the Contract Data. If the Contractor does not submit an updated Programme within this period, the Engineer may withhold the amount stated in the Contract Data from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Programme has been submitted.
  5. The Engineer's approval of the Programme shall not alter the Contractor's obligations. The Contractor may revise the Programme and submit it to the Engineer again at any time. A revised Programme shall show the effect of Variations and CompensationEvents.

##### Extension of the Intended CompletionDate

* 1. The Employer on recommendation of the Engineer shall extend the Intended Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining Works, which would cause the Contractor to incur additional cost.
  2. The Employer on recommendation of the Engineer shall decide whether and by how muchtimetoextendtheIntendedCompletionDatewithin21daysoftheContractoraskingthe Engineer for a decision upon the effect of a Compensation Event or Variation and submitting full supporting information. If the Contractor has failed to cooperate in dealing with a delay, the delay by this failure shall not be considered in assessing the new Intended CompletionDate.

##### Delays Ordered by theEngineer

* 1. The Engineer may instruct the Contractor to delay the start or progress of any activity within the Works. Delay/delays totalling more than 30 days will require prior written approval of theEmployer.

##### Management Meetings

* 1. The Engineer may require the Contractor to attend a management meeting. The business of a management meeting shall be to review the plans for theWorks.
  2. The Engineer shall record the business of management meetings and provide copies of the record to those attending the meeting. The responsibility of the parties for actions to be taken shall be decided by the Engineer either at the management meeting or after the management meeting and stated in writing to all those who attended themeeting.

1. ***QualityControl***
2. **Identifying Defects**
   1. The Engineer shall check the Contractor's work and notify the Contractor of any Defects that are found. Such checking shall not affect the Contractor's responsibilities. The Engineer may instruct the Contractor to search for a Defect and to uncover and test any work that the Engineer considers may have aDefect.

##### Tests

31.1 For carrying out mandatory tests as prescribed in the specifications, the Contractor shall establish field laboratory at the location decided by Engineer. The field laboratory will have minimum equipments as specified in the Contract Data. The Contractor shall be solely responsible for:

1. Carrying out the mandatory tests prescribed in the MoRD Specifications,and
2. For the correctness of the test results, whether preformed in his laboratory or elsewhere.
   1. If the Engineer instructs the Contractor to carry out a test not specified in the Specifications to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the test and anysamples.

##### Correction of Defects noticed during the Defects Liability Period and Routine Maintenance of Roads for fiveyears

32.1 The Engineer shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins from the Completion Date and ends after five years. The Defects Liability Period shall be extended for as long as the Defects remain to be corrected.

* 1. Every time notice of Defect/Defects is given, the Contractor shall correct the notified Defect/Defects within the duration of time specified by the Engineer’snotice.
  2. The Contractor shall do the routine maintenance of roads, including pavement, road sides and cross drains including surface drains to the required standards and in the manner as defined in clause 1.1 and keep the entire road surface and structure in Defect free condition during the entire maintenance period which begins from the Completion Date and ends after five years.

**32.4** In compliance to Programme of Routine maintenance work ( as per clause 26.1) submitted by the contractor, he shall carry out monthly inspection of roads under maintenance, based on which , he shall submit monthly bills , on line on e- Marg as detailed in subsequent clauses.

The routine maintenance standards shall meet the following minimum requirements:-

(i) Potholes on the road surface to be repaired soon after ( but not more than 15 days to rectify) these appear or brought to his notice either during the Contractor’s monthly inspection or by the Engineer.

1. Road shoulders to be maintained in proper condition to make them free from excessive edge drop offs, roughness, scouring orpotholes.
2. Cleaningofsurfacedrainsincludingreshapingto maintain free flow ofwater.
3. Cleaningofculvertsandpitsforfreeflowofwater.
4. Maintenanceofroadsigns,pavementmarkingsand other traffic controldevices
5. Any other maintenance operation required to keep the road traffic worthy at all times during the maintenance period.
6. Maintenance of Cross -Drainageworks.
7. Themaintenanceactivityincludesclearingoftree branchestokeepthesightdistancevisibleallthetime.
   1. To fulfil the objectives laid down in sub clauses 32.3 and 32.4 above, the Contractor shall undertake detailed inspection of the roads at least once in a month. The Engineer can increase this frequency in case of emergency. The Contractor shall forward to the Engineer, the record of inspection and rectification each month. The Contractor shall pay particular attention on those road sections which are likely to be damaged or inundated during rainy season.
   2. The Engineer may issue notice to the Contractor to carry out removal of defects or deficiencies in maintenance, if any, noticed in his inspection, or brought to his notice. The Contractor shall remove the defects and deficiencies within the period specified in the notice and submit to the Engineer a compliance report. In any case , the rectification shall be done within 15 days.

##### Uncorrected Defects

* 1. If the Contractor has not corrected a Defect pertaining to the Defects Liability Period under clause 32.1 and clause 32.2 of these Conditions of Contract, to the satisfaction of the Engineer, within the time specified in the Engineer's notice, the Engineer will assess the cost of having the Defect corrected, and the Contractor will pay this amount, on correction of the Defect.

1. ***CostControl***
2. **Bill ofQuantities**
   1. The Bill of Quantities shall contain items for the construction, installation, testing, and commissioning, maintaining works, and lump sum amount per km for yearly routine maintenance for each of the five years separately, to be done by theContractor.
   2. The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rate in the Bill of Quantities for each item for the construction of roads. The payment for routine maintenance of roads to the Contractor is performancebased.

##### Variations

35.1 The Engineer shall, having regard to the scope of the Works and thesanctioned estimated cost, have power to order, in writing, Variations within the scope of the Works, he considers necessary during the progress of the Works. Such Variations shall form part of the Contract and the Contractor shall carry them out and include them in updated Programmes produced by the Contractor. Oral orders of the Engineer for Variations, unless followed by written confirmation, shall not be taken intoaccount.

##### Payments for Variations

* 1. If the quantity of work for any BOQ item is varied, it will not constitute a variation for the purpose of payment to the contractor, at a rate other than the one mentioned in the Agreement.
  2. If the items for Variation are not specified in the Bill of Quantities, the Engineer shall derive the rate for such variation item from similar items in the Bill ofQuantities.
  3. If the rate for Variation item cannot be determined in the manner specified in Clause 36.2, the Contractor shall, within 14 days of the issue of order of Variation work, inform the Engineer the rate which he proposes to claim, supported by analysis of the rates. The Engineer shall assess the quotation and determine the rate based on prevailing market rates within one month of the submission of the claim by the Contractor. As far as possible, the rate analysis shallbebasedonthestandarddatabookandtherelevantscheduleofratesofthestate.Therecommendation of the Engineer on the rate so determined shall be submitted to the employer for approval. The decision of the employer shall be final and binding on the Contractor.

##### Cash FlowForecasts

* 1. When the Programme is updated, the Contractor shall provide the Engineer with an updated cash flow forecast.

##### Payment Certificates

**38.1The payment to the Contractor will be as follows for constructionwork:**

1. The Contractor shall submit to the Engineer monthly statements of the value of the work executed less the cumulative amount certified previously, supported with detailed measurement of the items of workexecuted.
2. The Engineer shall check the Contractor's monthly statement within 14 days and certify the amount to be paid to theContractor.
3. The value of work executed shall be determined, based on measurements by the Engineer.
4. The value of work executed shall comprise the value of the quantities of the items in the Bill of Quantitiescompleted.
5. The value of work executed shall also include the valuation of Variations and CompensationEvents.
6. The Engineer may exclude any item certified in a previous certificate or reduce the proportion of any item previously certified in any certificate in the light of later information.
7. The payment of final bill shall be governed by the provisions of Clause 50 of GCC.

**38.2 The payment to the Contractor will be as follows for routine maintenance:**

The payment for routine maintenance of roads to the Contractor is performance based and at per km per year rate as provided in the contract. For assessing performance of roads and payment , contractor to register and submit monthly bills on maintenance on web based utility called e- Marg [(www.](http://www/) emarg.gov.in).The performance of roads will be assessed on e-Marg , through regular routine inspection RI and Performance Evaluation PE by the engineer. The details of RI , marking system in PE and payment methodology is given in note below .The detailed marking system is given in contract data, clause 4(vi).

1. Payment for routine maintenance will be performance based. For certification of payment of routine maintenance, the engineer shall determine whether the contractor has actually achieved compliance to the Service Quality Level (and other requirements) specified in the Scope of Work, with reference to 100 point (hundred point) performance indexesassignedtovariousmaintenanceactivitiesas given in the contract data of GCC and the engineer shall certify the amount to be paid to the contractor. If contractor has not corrected a Defect pertaining to the Defects Liability Period or attendedmaintenance work under clause 32 of these conditions, to the requiredstandardandperformanceindexisbelow80 points(eightypoints)nopaymentwillbereleasedfor that period even if such maintenance is attended in subsequent months**.** If performance index is 100 points full payment, at the approved rate, shall be released. If performance index is between 80 to 100, proportionate deduction in payment will be madefor the works not attended during thatperiod.
2. For performance evaluation and payment of routinemaintenanceindividualroadshallbethe unit. Evaluation shall be done separately for every km or part thereof (segment wise) and weighted average of marks obtained shall beconsidered while makingpayment.
3. If any two segments get less than 80 marks or any particular segment continuously gets less than 80marks, the payment for whole road shall be denied. Details are asbelow.

Note: The Routine Inspection and performance evaluationofroadwillbedoneforeachKMorpartofit, as the rates for maintenance are per KM basis. . For details, bidders to refer the latest SOP issued byNRIDA on Performance Based Maintenance Contract as applicable on the day of bid submission .The PBMC system is a web based system called e-Marg of latest version. The bill submissions by the contractors, Performanceevaluation,photographicrecords,payment etc is on e-Marg and contractor is supposed to be well versed with the system. The performance evaluationand marking system is broadly as per the SOP issued by NRIDA and final marking is subject to the entire satisfaction of the engineer , who has full authority to asses and give marks inPE.

**ROUTINE INSPECTIONS**

1. Every road must be inspected for RoutineInspection(RI)atleastoncein two months. (Bi-monthly frequency)
2. Routineinspectioncanbecarriedoutby any of the PIU officers including Sub Engg/JE/AE/DE/AEE/EE orequivalent.
3. RIistobecarriedoutusingeMARGmobileapp only.
4. For the purpose of RI, each road shallbe divided into segments of one kilometre or part thereof. Complete road length shall be compulsorily inspected during a routineinspection.
5. For each segment two geo-tagged and time-stamped photographs shall be uploaded for each segment. The chainages for capturing photographs shall be system generated to ensurerandomness.
6. During RI, inspected segment shall be graded as Satisfactory(S), Satisfactory but requires improvement (SRI) and Unsatisfactory (U) as per the prescribed format ine-Marg.
7. The concerned officers and contractor can view the detailed report of the RI using their respective log-incredentials.

**PERFORMANCE EVALUATION**

1. Everyroadmustbeevaluatedatleastoncein two months. (Bi-monthlyfrequency)
2. PE can be carried out by any of thePIU officers including Sub Engg/JE/AE/DE/AEE orequivalent.
3. For the purpose of PE, each road shall be divided into segments of one kilometre or part thereof. Based on the grading of RI and photographs uploaded during RI, every segment is given marks out of 100 on the parameters fixed for PE. The weighted average marks are then evaluated for the entireroad.
4. All the PE conducted need to be finalized by the respective PIU-in- charge. While finalizing PE, PIU-in- charge may change the marks given to the road by the inspecting officer, along with mentioning the reasons for the changemade.
5. Criteria for Payment based on the marks obtained in PE is as follows:
6. If the weighted average marks for the entire road is 100 then full payment will be done.
7. If the weighted average marks for the entire road is between 80 and 100, then proportionate payment will be done. For e.g if the marks obtained is 88 out of 100 then 88% of the amount of bill raised will be paid.

If the weighted average marks for theentireroadislessthan80then no payment will be done for the entireroad.

1. If any two segments of a road get lessthan80marksinthesamePE, then no payment will be done for the entireroad.
2. Ifanyparticularsegmentofaroad gets less than 80 marks in two consecutive PE, then no payment will be done for the entireroad.
3. The Contractor shall submit to the Engineer a bill every month for the routine maintenance of the roads from the date the maintenance period starts i.e. from completion date as defined in Clause 1.1, it will be supported with a copy of the record of the Contractor’s monthly inspection and other instructions received from theEngineer.
4. The payment will be made Six monthly for the monthly bills received and as certified by the Engineer based on performance by theContractor.
5. The contractor shall submit monthly bills by the 10th day of the next month ( on web based software utility e- Marg) and If the bill for a month is not received from the Contractor , he forfeits his right for the payment and no payment shall be due to the contractor.

On submission of timely bills, engineer to certify the quality and actions taken as per clause 32.6 by the contractor, by way of Routine inspection andPerformance evaluation, marking system as explained herein before, the frequency of RI and PE is every two months and payment of bills is six monthly. Engineer can not delay RI and PE as these become due on e- Marg(a web based software utility as explained in succeeding paras and herein before.

g. If the Contractor has failed to carry out the maintenance within the period specified by the Engineer, no payment of any kind will be due to the Contractor for that month.

##### Payments

* 1. Payments shall be adjusted for deductions for advance payments, security deposit, other recoveries in terms of the Contract and taxes at source, as applicable under the law. The Employer shall pay the Contractor the amounts the Engineer has certified, within 15 days of the date of each certificate.
  2. The Employer may appoint another authority, as specified in the Contract Data (or any other competent person appointed by the Employer and notified to the Contractor) to make payment certified by theEngineer.
  3. Items of the Works for which no rate or price has been entered in the Bill of Quantities, will not be paid for by the Employer and shall be deemed covered by other rates and prices in the Contract.

**39.4** Payment for the routine maintenance of the roads will be made Six Monthly for the satisfactory maintenance of the Works and based on the monthly bills submitted by the Contractor as per Clause 38.2 above and certified by the engineer, within 15 days of the date of each certificate.

##### CompensationEvents

40.1 The following shall be Compensation Events unless they are caused by theContractor:

1. The Engineer orders a delay or delays exceeding a total of 30days.
2. The effects on the Contractor of any of the Employer'sRisks.
   1. If a Compensation Event would prevent the Works being completed before the Intended Completion Date, the Intended Completion Date shall be extended. The Engineer shall recommend to the Employer whether and by how much the Intended Completion Date shall be extended. Final approval shall rest with theEmployer.

##### Tax

* 1. The rates quoted by the contractor shall deemed to be exclusive of the Goods and Services Tax (GST) but including labour cess, other levies, duties, royalties, cess, toll, taxes of local bodies and authorities that the contractor will have to pay for the performance of this contract. The employer will perform such duties in regard to the deduction of such taxes including GST at source, require deductions in this reference will be made as per applicable law. GST as per prevailing rate at the time of payment/bill submission shall be made applicable presently @ 12%) and shall be paid on the whole work carried out as accepted by the engineer, while making the payment.

##### Currencies

* 1. All payments will be made in IndianRupees.

##### Security Deposit

* 1. The Employer shall retain security deposit of five percent and Performance Security of two and a half percent of the amount from each payment due to the Contractor until completion of the whole of the construction Work. No security deposit/ retention shall be retained from the payments for Routine Maintenance of works. In case, the Contractor furnishes bank guarantee for the amount equal to Performance Security of two and a half percent retained from each payment due to the Contractor, the same amount shall be repaid to the Contractor subject to condition that the validity of bank guarantee is as per provision of Clause 46.2 ofGCC.
  2. On the satisfactory completion of the whole of the construction work, half the total amount retained as security deposit is repaid to the Contractor, one-fourth of the total amount retained as security deposit is repaid to the Contractor at the end of 2nd year after completion of the construction work and balance of the amount retained as security deposit is repaid to the Contractor at the end of 3rd year after completion of the construction work subject to condition that the Engineer has certified that all defects notified by the Engineer tothe Contractor before the end of period prescribed for repayment have beencorrected.
  3. The additional Performance Security for unbalanced bids as detailed in Clause 46 of the Conditions of Contract is repaid to the Contractor when the construction work iscomplete.
  4. The Performance Security equal to five percent of the Contract Price as detailed in Clause 46 of Conditions of Contract is repaid to the Contractor when the period of five years fixed for Routine Maintenance is over and the Engineer has certified that the Contractor has satisfactorily carried out the Routine Maintenance of theworks.If the Routine Maintenance part of the contract is not carried out by the Contractor as per this Contract, the Employer will be free to get the Routine Maintenance work carried out from another source and the amount required for this work will be recovered from the amount of Performance Security available with the Employer and/ or from any amounts of the Contractor whatever is due along with additional 20 percent amount as penalty.
  5. If the Contractor so desires, then the Security Deposit can be converted into any interest bearing security of scheduled commercial bank in the name of the Employeror National Saving Certificates duly pledged in favour of the Employer for Defects Liability Period.

##### Liquidated Damages

* 1. In the event of failure on part of the Contractor to achieve timely completion of the project,includinganyextensionoftimegrantedunderClause27,heshall,withoutprejudice

to any other right or remedy available under the law to the Employer on account of such breach, pay as agreed liquidated damages to the Employer and not by way of penalty in a sum calculated at the rate per week or part thereof as stated in the Contract Data. For the period that the Completion Date is later than the Intended Completion Date, liquidated damages at the same rate shall be withheld if the Contractors fails to achieve the milestones prescribed in the Contract Data. However, in case the Contractor achieved the next milestone, the amount of the liquidated damages already withheld shall be restored to the Contractor by adjustment in the payment certificate. Both the Parties expressly agree that the total amount of liquidated damages shall not exceed 10% (ten percent) of Initial Contract Price and that the liquidated damages payable by the Contractor are mutually agreed genuine pre-estimated loss and without any proof of actual damage likely to be suffered and incurred by the Employer; and the Employer is entitled to receive the same and are not by way ofpenalty.

The Employer may, without prejudice to any other method of recovery, deduct the amount of such damages from any sum due, or to become due to the Contractor or from Performance Security or any other dues from Government or semi Government bodies within the state.

The payment or deduction of such damages shall not relieve the Contractor from his obligations to complete the Works, or from any other of his duties, obligations or responsibilities under the Contract.

The Contractor shall use and continue to use his best endeavours to avoid or reduce further delay to the Works, or any relevant Stages.

* 1. If the Intended Completion Date is extended after liquidated damages have been paid, the Engineer shall correct any such payment of liquidated damages by the Contractor by adjusting the next paymentcertificate.
  2. It is agreed by the Contractor that the decision of the Employer as to the liquidated damages payable by the Contractor under this Clause shall be final andbinding.

##### Advance Payment

* 1. On the request of the Contractor, the Employer will make the following advance payment to the Contractor against submission by the Contractor of an Unconditional Bank Guarantee from a scheduled Commercial bank acceptable to the Employer in amounts equal to 110% (one hundred ten percent) of the amount of the advance payment beingrequested:
     1. Mobilization advance up to 5% (five percent) of the initial contract price excluding the contract price for routinemaintenance
     2. Equipment Advance up to 90% (ninety percent) of the cost of the new equipment brought to the site, subject to a maximum of 10% ( ten percent) of the initial contract price excluding the contract price for routinemaintenance

The Bank Guarantee shall remain effective until the advance payment has been repaid, but the amount of the guarantee shall be progressively reduced by the amounts repaid by the

Contractor. Interest will not be charged on the advance payment. However, if the Contract is terminated due to default of the Contractor, the Mobilization Advance and the Equipment Advance shall be deemed to be an interest bearing advance at the base rate of the State Bank of India, as application on the date of such advancepayment.

* 1. The Contractor is to use the advance payment only to pay for Equipment, plant and Mobilization expenses required specifically for execution of the Works. The Contractor shall demonstrate that the advance payment has been used in this way by supplying copies of invoices or other documents to theEngineer.
  2. The advance payment shall be recovered by deducting proportionate amounts from payments otherwise due to the Contractor for the construction work, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, price adjustments, Compensation Events, or liquidateddamages.

##### Securities

* 1. The Performance Security equal to 5% (five percent) of the Contract Price and additional security for unbalanced bids shall be provided to the Employer. Out of total Performance Security equal to 5%(five percent) of Contract Price, half shall be delivered to the Employer no later than the dates specified in the Letter of Acceptance and shall be issued in the form given in Contract Data; however, balance half Performance Security shall be retained at the rate of two and a half percent of each payment due to the Contractor until completion of whole of the constructionwork.
  2. The Performance Security shall be valid until a date 45 days from the date of issue of certificate of completion of construction work and maintenance work subject to the condition that if the Performance Security is in the form of a Bank Guarantee, the period of validity of Bank Guarantee could be one year initially; however, the Contractor would get this Bank Guarantee extended in such a way that an amount equal to five percent of the Contract Price is always available with Employer until 45 days after the lapse of the Defects Liability Period. If the Contractor fails to maintain the above Performance Security, the Employer would recover the same from any dues payable to theContractor.

##### Cost ofRepairs

* 1. Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Liability Period shall be remedied by the Contractor at his cost if the loss or damage arises from the Contractor's acts oromissions.

1. ***Finishing the Contract***
2. **Completion of Construction andMaintenance**
   1. The Contractor shall request the Engineer to issue a certificate of completion of the construction of the Work and the Engineer will do so upon deciding that the Work is completed.
   2. The Contractor shall request the Engineer to issue the certificate of completion of the Routine Maintenance and the Engineer will do so upon deciding that the work of Routine Maintenance iscompleted.

##### Taking Over

* 1. The Employer shall take over the Works within seven days of the Engineer's issuing a certificate of Completion of Works. The Contractor shall continue to remain responsible for its Routine Maintenance during the maintenanceperiod.
  2. The Employer shall take over the maintained road within seven days of the Engineer issuing a certificate of completion of the work of RoutineMaintenance.

##### Final Account

* 1. The Contractor shall submit to the Engineer a detailed account of the total amount that the Contractor considers payable for works under the Contract within 21 days of issue of certificate of completion of construction of Works. The Engineer shall issue a Defects Liability Certificate and certify any payment that is due to the Contractor for Works within 42 days of receiving the Contractor's account if it is correct and complete. If theaccount submitted by the Contractor is not correct or complete, the Engineer shall issue a schedule to the Contractor, within 42 days, that states the scope of the corrections or additions that are necessary. If the revised account is still unsatisfactory, after it has been resubmitted by the Contractor, the Engineer shall decide on the amount payable to the Contractor and issue a payment certificate within 28 days of receiving the Contractor’s revised account. The payment of final bill for construction of Works will be made within 14 daysthereafter.
  2. In case the account for construction is not received within 21 days of issue of Certificate of Completion as provided in clause 50.1 above, the Engineer shall proceed to finalise the account and issue a payment certificate within 28 days. The payment of final bill for construction of Works will be made within 14 daysthereafter.
  3. The Contractor shall submit to the Engineer a detailed account of the total amount that the Contractor considers payable for maintenance of works under the contract 21 days before the end of the Routine Maintenance Period. The Engineer shall issue a Routine Maintenance Completion Certificate and certify any final payment that is due to the Contractor within 21 days of receiving the Contractor's account if it is correct and complete. If it is not,the Engineer shall issue within 21 days a schedule that states the scope of the corrections or additions that are necessary. If the revised account is still unsatisfactory after it has been resubmitted by the Contractor, the Engineer shall decide on the amount payable to the Contractor and issue a payment certificate within 28 days of receiving the Contractor’s revised account. The payment of final bill for routine maintenance will be made within 14 days thereafter.
  4. In case the account for routine maintenance is not received within 21 days of issue of Certificate of Completion as provided in clause 50.3 above, the Engineer shall proceed to finalise the account and issue a payment certificate within 28 days. The payment of final bill for routine maintenance will be made within 14 daysthereafter.

##### Operating and Maintenance Manuals

* 1. If "as built" Drawings and/or operating and maintenance manuals are required, the Contractor shall supply them by the dates stated in the ContractData.
  2. If the Contractor does not supply the Drawings and/or manuals by the dates stated in the Contract Data, or they do not receive the Engineer's approval, the Engineer shall withhold the amount stated in the Contract Data from payments due to theContractor.

##### Termination

* 1. The Employer may terminate the Contract if the Contractor causes a fundamental breach of theContract.
  2. Fundamental breaches of the Contract shall include, but shall not be limited to, the following:

1. the Contractor stops work for 28 days when no stoppage of work is shown on the current Programme and the stoppage has not been authorized by theEngineer;
2. the Contractor is declared as bankrupt or goes into liquidation other than for approved reconstruction oramalgamation;
3. the Engineer gives Notice that failure to correct a particular Defect whether pertaining to construction work or pertaining to defects liability period is a fundamental breach of the Contract and the Contractor fails to correct it within a reasonable period of time determined by theEngineer;
4. the Contractor does not maintain a Security, which isrequired;
5. the Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in clause 44.1;
6. the Contractor fails to provide insurance cover as required under clause13;
7. if the Contractor, in the judgement of the Employer, has engaged in thecorrupt, fraudulent or coercive practice in competing for or in executing the Contract. For the purpose of this clause, “corrupt practice” means the offering, giving, receiving, or soliciting of anything of value to influence the action of a public official in the procurement process or in Contract execution. “Fraudulent Practice” means a willful misrepresentation or omission of facts or submission of fake/forged documents in order to induce public official to act in reliance thereof, with the purpose of obtaining unjust advantage by or causing damage to justified interest of others and/or to influence the procurement process to the detriment of the Government interests.And, this includes collusive practice among Bidders (prior to or after bid submission) designed to establish bid process at artificial non-competitive levels and to deprive the Employerofthebenefitsoffreeandopencompetition.“Coercivepractice”meansthe

act of obtaining something, compelling an action or influencing a decision through intimidation, threat or the use of force directly or indirectly, where potential or actual injury may befall upon a person, his/ her reputation or property to influence their participation in the tendering process.

1. if the Contractor has not completed at least three-eighth of the value of construction Work required to be completed after half of the completion period haselapsed;
2. if the Contractor fails to set up a field laboratory with the prescribed equipment, within the period specified in the ContractData;
3. if the Contractor fails to deploy machinery and equipment or personnel as specified in the Contract Data at the appropriate time;and
4. if the Contractor fails to pay EPF/ ESI contribution as required under prevailinglaws;
5. if the Contractor engages child labour in violation of prevailinglaws;
6. if the Contractor fails to ensure that there is no gender bias in engagement of labour and other employees and in payment of wages and he discriminate against female workers.
7. any other fundamental breaches as specified in the ContractData
   1. Notwithstanding the above, the Employer may terminate the Contract forconvenience.

52.4If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonablypossible.

##### Payment upon Termination

* 1. **(i)** If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer shall issue a certificate for the value of the work done, less liquidated damages, less advance payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Contract Data. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be recovered from the Security Deposit, and Performance Security. If any amount is still left un-recovered it will be a debt payable to the Employer from State PMGSY works, any other State Government works including State Public Sector works executed by the Contractor.

**53.1(ii)** If the Contract is terminated because of a fundamental breach of contract by the Contractor due to non compliance of the requirements of clause 32 of GCC regarding defects liability period and routine maintenance of roads for five years, the Engineer will assess the cost of having the defect corrected. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be recovered from the Security Deposit and Performance Security. If any amount is still left un-recovered, it will be recovered from any dues payable to the Contractor from State PMGSY works, any other State Government works including State Public Sector works executed by the Contractor. If any amount still remains unrecovered, it shall be recovered as arrears of landrevenue.

* 1. 53.2 If the Contract is terminated at the Employer's convenience, the Engineer shall issue a certificate for the value of the work done, the reasonable cost of removal of Equipment, repatriationoftheContractor'spersonnelemployedsolelyontheWorks,andtheContractor's

costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the Contract, and less taxes due to be deducted at source as per applicable law.

##### Property

##### All Materials on the Site, Plant, Equipment, Temporary Works, and Works shall be deemed to be the property of the Employer for use for completing balance construction work if the Contract is terminated because of the Contractor's default, till the Works is completed after which it will be transferred to the Contractor and credit, if any, given for itsuse.

##### Release from Performance

* 1. If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of the Employer or the Contractor, the Engineer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment wasmade.
  2. Death or permanent invalidity of the Contractor: the Contractor shall indicate his nominee for the Contract at the time of signing of Agreement. If a Contractor dies during the currency of the Contract or becomes permanently incapacitated, and his/her nominee are not willing to complete the Contract, the Contract shall be closed without levying any damages/compensation as provided for in clauses 44 and 53 ofGCC.

However, if the nominee expresses his/her intention to complete the balance work and the competent authority is satisfied about the competence of the nominee, then the competent authority shall enter into a fresh agreement for the remaining work strictly on the same terms and conditions, under which the Contract was initially awarded.

1. ***Other Conditions ofContract***
2. **Labour**
   1. The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their safety, payment, housing, feeding andtransport.
   2. The Contractor shall, if required by the Engineer, deliver to the Engineer a return in detail, in such form and at such intervals as the Engineer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on the Site and such other information as the Engineer mayrequire.

##### Compliance with LabourRegulations

* 1. During continuance of the Contract, the Contractor and his sub Contractors shall abide at all times by all existing labour enactments and rules made thereunder, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour law (including rules), regulations, bye laws that may be passed or notification that may be issued under any labour law in future either by the State or the Central Government or the local authority. Salient features of some of the major labour laws that are applicable to construction industry are given in Appendix to Part I General Conditions of Contract. The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made there under, regulations or notifications including amendments. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated in thenotifications/bye laws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, the Engineer/Employer shall have the right to deduct any money due to the Contractor including his amount of Performance Security. The Employer/Engineer shall also have the right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by theEmployer.

The employees of the Contractor and the Sub-Contractor in no case shall be treated as the employees of the Employer at any point of time.

* 1. Full compliance of statutory requirements apart, the Contractor shall pay rates of wages and observe conditions of labour not less favourable than those established for the trade or the industry where the work is carried out. The Contractor shall make himself aware of all labour regulations and their impact on the cost and build up the same in the Contract Price. During the Contract Period, unless and otherwise provided in the Contract, no extra amount in this regard shall be payable to the Contractor, for whatsoeverreason.
  2. In the event of default being made in the payment of any money in respect of wages of any person employed by the Contractor or any of its sub-contractors of any tier in and for carrying out of this Contract and if a claim therefore is filed in the office of the Labour Authorities and proof thereof is furnished to the satisfaction of the Labour Authorities, the Employer may, failing payment of the said money by the Contractor, make payment of such claim on behalf of the Contractor to the said Labour Authorities and any sums so paid shall be recoverable by the Employer from theContractor.
  3. It shall be the responsibility of the Contractor to pay EPF/ESI contributions as required under prevailing laws. The Contractor shall bear all such cost and it would be deemed to be included in the ContractPrice.
  4. The employment of child labour is prohibited in the Contract. The Contractor shall comply with the Child Labour (Prohibition and Regulation) Act,1986.
  5. The Contractor shall ensure that there is no gender bias in engagement of labour and other personnel and shall not make any discrimination against female employees. The Contractor shall comply with the Equal Remuneration Act, 1979 and Maternity Benefit Act, 1961.
  6. The Contractor shall have a Labour Welfare Organisation which shall be responsible for labour welfare and compliance with prevalent labour laws, statutes and guidelines. In this context, the Contractor is also required to familiarize himself with Labour Welfare Rules of the state concerned and comply with the provisions of the Building and other Construction Workers (Regulation and Employment & Conditions of Service), Act 1996 and the Cess Act, 1996.
  7. The Contractor shall provide and maintain at his own expense, all necessary accommodation and welfare facilities as per prevailing labour and welfare laws for his (and his Sub-contractor’s) staff andlabour.
  8. The Contractor shall prepare and submit compliance reports of adherence to labour laws as and when directed by theEngineer.

##### Drawings and Photographs of theWorks

* + 1. The Contractor shall do photography/video photography of the site firstly before the start of the work, secondly mid-way in the execution of different stages of work and lastly after the completion of the work. No separate payment will be made to the Contractor forthis.
  1. The Contractor shall not disclose details of Drawings furnished to him and works on which he is engaged without the prior approval of the Employer in writing. No photograph of the works or any part thereof or plant employed thereon, except those permitted under clause 58.1, shall be taken or permitted by the Contractor to be taken by any of his employees or any employees of his sub-Contractors without the prior approval of the Employer in writing. No photographs/ Video photography shall be published or otherwise circulated without the approval of the Employer inwriting.

**59. The Apprentices Act,1961**

**59.1** The Contractor shall duly comply with the provisions of the Apprentices Act, 1961 (III of 1961), the rules made there under and the orders that may be issued from time to time under the said Act and the said Rules and on his failure or neglect to do so, he shall be subject to all liabilities and penalties provided by the said Act and saidRules.

# Contract Data to General Conditions of Contract

Except where otherwise indicated, the Employer prior to issuance of the bidding documents should fill in all Contract Data. Schedules and reports to be provided by the Employer should be annexed.

Clause Reference

##### Items marked “N/A” do not apply in this Contract.

1. TheEmployeris [Cl.1.1]

Designation:

Address:

Name of authorized Representative Telephone No.(s):Office:

Mobile No.:

Facsimile (FAX) No.:

Electronic Mail Identification (E-mail ID):

1. The Engineer is Designation:

Address: [Cl.1.1]

Telephone No.(s):Office:

Mobile No.:

Facsimile (FAX) No.:

Electronic Mail Identification (E-mail ID):

1. The Intended Completion Date for the whole of theWorksis months after start ofwork.

[Cl.1.1, 17&27]

1. Routine Maintenance during five years after the Completion Date is defined as follows:

Maintenance operations during the period of 5 years shall be based on Chapter 11 of Rural Roads Manual (IRC:SP:20:2002). Its specific provisions are:-

1. **Clause 11.2, *ibid***, explains the various types of distress/defects of pavements. For example, cracks, ravelling, rutting, pot holesetc.
2. **Clause 11.3, *ibid***, defines different maintenance activities. For example, fog seal, bituminous surface treatment,etc.
3. **Clause 11.4, *ibid***, suggests planning of routinemaintenance.
4. **Clause 11.5 and Clause 11.6 (a),** *ibid*, define preventive and corrective maintenance, and classify activities of routine maintenance andrepairs.
5. **Clause 11.7, *ibid***, discusses in detail the assessment of defects and maintenance measures for sealed roads, roads with rigid / RCCP and roads with specialpavement.

**(Note**: A periodical renewal is not part of routine maintenance).

**(vi)** The periodicity of routine maintenance activities shall be as follows, this is for guidance only , however , road is to be maintained in serviceable condition all the time and payment is performance based , as per performance evaluation and marks obtained.

**Routine Maintenance Activities and their frequency with performance index (PI) – BT/Gravel Road**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S.No.** | **Name of**  **Item/ Activities** | **Frequency**  **of operation in a year** | **PI** | |
| **Plain &Rolling Terrain** | **Hilly Terrain** |
| 1. | Maintenance of Bituminous surface road and / or gravel road and/or WBM road including filling potholes and patch repairs etc. As per clause 1904, 1906 of the MoRD Specifications ( As per Annexure- 14.10 of Operation manual) | As and when required | 50 | 40 |
| 2. | Restoration o rain cuts and dressing of side slopes/berms as per clause 1902 of the Specification (As per Annexure- 14.10 of Operation manual) | Once generally after rains (In case of areas having rainfall more than 1500 mm per year, as and when required). | 10 | 5 |
| **3.** | Making up of berms/shoulders as per clause1903 o the ( As per Annexure-  14.10 of Operation manual) | As and when required | 20 | 20 |
| **4.** | Maintenance of drains as per clause 1907 of the Specifications. ( As per Annexure-  14.10 of Operation manual) | Twice (In case of hill roads as and when required | 3 | 8 |
| **5.** | Maintenance of culverts an cause ways as per clause 1908 and 1909 of the MoRD (As per Annexure 14.10 of Operation manual) | Twice (In case of hill roads as and when required) | 4 | 10 |
| **6.** | Maintenance of guard rails and parapet rails as per clause 1911 the MoRD Specification ( As per Annexure-  14.10 of Operation manual) | Maintenance as and when required. Repairing once in a year | 1 | 1 |
| **7.** | Maintenance of road signs, speed breakers, standing tree adjacent to  road wherever required as per clause 1910 of the MoRD  Specification (As per Annexure- 14.10 of Operation manual). | Maintenance as and when required.  Repairing once in every two years | 2 | 4 |
| **8.** | Maintenance of 200 m and Kilo Meter stones as per clause 1912 the MoRD Specification ( As per Annexure-  14.10 of Operation manual). | Maintenance as and when required.  Repairing once in a year | 2 | 2 |
| **9.** | Cutting of branches of trees, shrubs and trimming of grass and weeds etc. A per clause 1914 of the MoRD Specification ( As per Annexure- 14.10 of Operation manual) | Once generally after rains (In case of areas having rainfall more than 1500 mm per year, as and when required. | 3 | 5 |
| **10.** | White washing parapets of Works including CD As per Annexure-14.10 of Operation manual) | Once in a year | 2 | 3 |
| **11.** | Painting of guard stones | Twice in a year | 2 | 1 |
| **12.** | Re-fixing displaced guard stones | Once in a year | 1 | 1 |
|  |  | **Total Marks** | **100** | **100** |
| **Routine Maintenance Activities and their frequency with performance index – CC Road** | | | | |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S.No** | **Name of Item/Activity** | **Frequency of operations in the year** | **Plain & Rolli ng Terrain** | **Hilly Terrain** |
| 1 | Maintenance of Concrete surface including crack sealing spot patching with  PCC or  bituminous concrete as per provisions of IRC SP83. | As and when required | 50 | 40 |
| 2. | Restoration of rain cuts and dressing of side slopes/berms as per clause 1902 of the Specifications. (As per Annexure-14.10 of Operation manual) | Once generally after rains or as and when required. | 10 | 5 |
| 3. | Making up of berms/shoulders as per clause1903 of the ( As per Annexure-14.10 of Operation manual) | As and when required | 20 | 20 |
| 4. | Maintenance of drains as per clause 1907 of the Specifications. (As per Annexure-14.10 of Operation manual) | Twice (In case of Hill roads as and when required | 3 | 8 |
| 5. | Maintenance of culverts and cause ways as per clause 1908 and 1909 of the Specifications. (As per Annexure-14.10 of Operation manual) | Twice (In case of Hill roads as and when required | 4 | 10 |
| 6. | Maintenance of guard rails and parapet rails as per clause 1911 of the MoRD Specifications ( As per Annexure-14.10 of Operation manual) | Maintenance e as and when required. Repairing once in a year | 1 | 1 |
| 7. | Maintenance of road signs, speed breakers, standing trees adjacent to road wherever required as per clause 1910 of the MoRD Specifications (As per Annexure- 14.10 of  Operation manual). | Maintenance as and when required. Repairing once in every two years | 2 | 4 |
| 8. | Maintenance of  200 m and kilo meter stones as per clause 1912 of the MoRD Specifications (As per Annexure- 14.10 of  Operation manual). | Maintenance as and when required. Repairing once in a year | 2 | 2 |
| 9. | Cutting of  branches of trees, shrubs and  trimming of grass and weeds etc. as per clause 1914 of the MoRD Specifications (As per Annexure-  14.10 of Operation manual). | Once generally after rains (In case of areas having rainfall more than 1500  mm per year, as and when required. | 3 | 5 |
| 10. | White washing parapet of of Works including CD (As per Annexure-14.10 of Operation manual) | Once in a year | 2 | 3 |
| 11. | Painting of guard stones | Twice in a year | 2 | 1 |
| 12. | Re-fixing displaced guard stones | Once in a year | 1 | 1 |
|  |  | Total: | 100 | 100 |

**(vii) Appendix 11.3, *ibid***, covers the special problems of Road Maintenance in HeavyRainfall

/ Snow fall areas.

(viii) **Appendix 11.4, *ibid***, explains the nature of duties in maintenance of shoulders, drainage structures andcauseways.

1. The Site is located at km ……………………tokm. ……………. [Cl.1.1]
2. The Start Date shall be days after the date of issue of theNoticeto [Cl.1.1] Proceed with the work.
3. (a) The name and identification number of the Contractis: [Cl.1.1]

(b) The Worksconsist of [Cl.1.1]

. The works shall, inter-alia, include the following, as specified or as directed.

Clause Reference

##### Road Works

Site clearance; setting-out and layout; widening of existing carriageway and strengthening including camber corrections; construction of new road bituminous pavements remodeling/construction of junctions, intersections, supplying and placing of drainage channels, flumes, guard posts and other related items; construction/extension of cross drainage works, bridge, approaches and other related items; road markings, road signs and kilometer/hectometer stones; protective works for roads/bridges; all aspects of quality assurance of various components of the works; rectification of the Defects in the completed works during the Defects Liability Period; submission of “As-built” drawings and any other related documents; and other item of work as may be required to be carried out for completing the works in accordance with the Drawings and provisions of the Contract and to ensure safety and planting of trees along theroads.

##### CD Works includingbridges

Site clearance; setting out, provision of foundations, piers, abutments and bearings; pre-stressed/reinforced cement concrete superstructure; wearing coat, hand railings, expansion joints, approach slabs, drainage spouts/down-take pipes, provision of suitably designed protective works; providing wing/return walls; provision of road markings, road signs etc.; all aspects of quality assurance; clearing the Site and handing over the works on completion; rectification of the Defects during the Defects Liability Period and submission of “As-built” drawings and other related documents; and other items of work as may be required to be carried out for completing the works in accordance with the Drawings and the provisions of the Contract and to ensure safety.

##### Maintenance and Other Items

As required to fulfill all the contractual obligations as per the Bid documents.

1. Sectioncompletion is [Cl 2.2]
2. The following documents also form part of theContract: [Cl.2.3(11)]
3. (a) The law which applies to the Contract is the law of UnionofIndia. [Cl.3.1]

(b) The language of the Contractdocuments is . [Cl.3.1]

1. The Schedule of Other Contractorsisattached. [Cl.8.1]

12 A. The Technical Personnel for construction work are: [Cl.9.2]

|  |  |  |
| --- | --- | --- |
| Technical Personnel | Number | Experience in Road Works |
| 1. Degree Holder in Civil Engineering 2. Diploma Holder in Civil Engineering |  |  |

For field testing laboratory ;

|  |  |
| --- | --- |
| Technical Personnel | Number |
|  |  |

B. For routinemaintenance

|  |  |  |
| --- | --- | --- |
| Technical Personnel | Number | Experience in Road Works |
| 1. Degree Holder in Civil Engineering 2. Diploma Holder in Civil Engineering |  |  |

13(a) Amount and deductible forinsurance are: [Cl. 13.1]

13(b) Amount and deductible forinsurance are: [Cl. 13.3 (a)

1. Siteinvestigationreport [Cl.14.1]
2. The key equipments/ machinery for construction of works shallbe:

|  |  |  |
| --- | --- | --- |
| *S.*  *No.* | *Name of Equipment/ Machinery* | *Quantity* |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

[Cl. 16.2]

1. (a) Competentauthoritiesare:: [Cl. 24.1] SuperintendingEngineer with powers upto

Chief Engineer with powers upto

1. (a) The period for submission of the programme for approvalofEngineer [Cl.26.1] shallbe days from the issue of Letter of Acceptance.
2. The updated programme shall be submitted atintervalof days. [Cl. 26.3]
3. The amount to be withheld for late submission ofan updated [Cl. 26.3] programme shallbeRs. lakhs.
4. The key equipments for field laboratory shallbe:

|  |  |  |
| --- | --- | --- |
| *S. No.* | *Name of Equipment* | *Quantity* |
|  |  |  |
|  |  |  |
|  |  |  |
|  |  |  |

[Cl. 31.1a]

.

1. The authorized person to make paymentsis

[ Cl.39.2]

1. (a) Milestones to be achieved during the contractperiod
   1. 1/8th of the value of entire contract work up to 1/4th of the period allowed for completion ofconstruction
   2. 3/8th of the value of entire contract work up to ½ of the period allowed for completion ofconstruction
   3. 3/4th of the value of entire contract work up to ¾th of the period allowed for completion ofconstruction
2. Amount of liquidateddamagesfor For Whole of work delay in completionofworks 1 percent of theInitial

Contract Price, rounded off to the nearest thousand, per week.

1. Maximum limit of liquidateddamagesfor 10 per cent of the Initial delay in completionofwork. Contract Pricerounded

off to the nearest thousand.

[Cl.44.1]

1. The standard form of Performance Security acceptable to the Employer shall be an unconditional Bank Guarantee of the type as presented in the Bidding Documents, or Fixed Deposit Receipt from ascheduled

Commercial bank. [Cl. 46.1]

1. (a) The Schedule of Operating andMaintenanceManuals . [Cl.51.1]

(b) The date by which “as-built” drawings (in scale as directed) in 2 sets are [Cl.51.1] required is within 28 days of issue of certificate of completion of whole

or section of the work, as the case may be.

1. The amount to be withheld for failing to supply“as-built”drawings [Cl.51.2] by the date requiredisRs. Lakhs.
2. (a) The period for setting up a field laboratory with the prescribedequipment

is days from the date of notice tostart work [Cl.52.2 (i)]

(b) The following events shall also be fundamental breach ofContract: [Cl.52.2 (k)] “The Contractor has contravened Clause 7.1 and Clause 9of

Part I General Conditions of Contract

1. The percentage to apply to the value of the work not completed representing the Employer’s additional cost for completing theWorks

shallbe percent. [Cl.53.1(i)]

# Appendix to Part I General Conditions of Contract

##### SALIENT FEATURES OF SOME MAJOR LABOUR LAWS APPLICABLE TO ESTABLISHMENTS ENGAGED IN BUILDING AND OTHER

**CONSTRUCTION WORK.**

1. **Workmen Compensation Act 1923**: - The Act provides for compensation in case of injury by accident arising out of and during the course ofemployment.
2. **Payment of Gratuity Act 1972**: - Gratuity is payable to an employee under the Act on satisfaction of certain conditions on separation if an employee has completed the prescribed minimum years (say, five years) of service or more or on death the rate of prescribed minimum days’(say, 15 days) wages for every completed year of service. The Act is applicable to all establishments employing the prescribed minimum number (say, 10) or moreemployees.
3. **Employees P.F. and Miscellaneous Provision Act 1952**: The Act Provides for monthly contributions by the Employer plus workers at the rate prescribed (say, 10% or 8.33%). The benefits payable under the Actare:
   1. Pension or family pension on retirement or death as the case maybe.
   2. Deposit linked insurance on the death in harness of theworker.
   3. Payment of P.F. accumulation on retirement/deathetc.
4. **Maternity Benefit Act 1961**: - The Act provides for leave and some other benefits to women employees in case of confinement or miscarriageetc.
5. **Contract Labour (Regulation & Abolition) Act 1970**: - The Act provides for certain welfare measures to be provided by the Contractor to contract labour and in case the Contractor fails to provide, the same are required to be provided, by the Principal Employer by Law. The Principal Employer is required to take Certificate of Registration and the Contractor is required to take license from the designated Officer. The Act is applicable to the establishments or Contractor of Principal Employer if they employ prescribed minimum (say 20) or more contractlabour.
6. **Minimum Wages Act 1948**: - The Employer is to pay not less than the Minimum Wages fixed by appropriate Government as per provisions of the Act if the employment is a scheduled employment. Construction of buildings, roads, runways are scheduledemployment.
7. **Payment of Wages Act 1936:** - It lays down as to by what date the wages are to be paid, when it will be paid and what deductions can be made from the wages of the workers.
8. **Equal Remuneration Act 1979**: - The Act provides for payment of equal wages for work of equal nature to male and female workers and for not making discrimination against female employees in the matters of transfers, training and promotionsetc.
9. **Payment of Bonus Act 1965**: - The Act is applicable to all establishments employing prescribed minimum (say, 20) or more workmen. The Act provides for payments of annual bonus within the prescribed range of percentage of wages to employees drawing up to the prescribed amount of wages, calculated in the prescribed manner. The Act does not apply to certain establishments. The newly set- up establishments are exempted for five years in certain circumstances. States may have different number of employmentsize.
10. **Industrial Disputes Act 1947**: - The Act lays down the machineryand procedure for resolution of industrial disputes, in what situations a strike or lock-out becomes illegal and what are the requirements for laying off or retrenching the employees or closing down theestablishment.
11. **Industrial Employment (Standing Orders) Act 1946**: - It is applicable to all establishments employing prescribed minimum (say, 100, or 50). The Act provides for laying down rules governing the conditions of employment by the Employer on matters provided in the Act and get these certified by the designated Authority.
12. **Trade Unions Act 1926**: - The Act lays down the procedure for registration of trade unions of workmen and Employers. The Trade Unions registered under the Act have been given certain immunities from civil and criminalliabilities.
13. **Child Labour (Prohibition & Regulation) Act 1986**: - The Act prohibits employment of children below 14 years of age in certain occupations and processes and provides for regulations of employment of children in all other occupations and processes. Employment of child labour is prohibited in building and construction industry.
14. **Inter-State Migrant Workmen’s (Regulation of Employment & Conditions of Service) Act 1979**: - The Act is applicable to an establishment which employs prescribed minimum (say, five) or more inter-state migrant workmen through an intermediary (who has recruited workmen in one state for employment in the establishment situated in another state). The Inter-State migrant workmen, in an establishment to which this Act becomes applicable, are required to be provided certain facilities such as Housing, Medical-Aid, Travelling expenses from home up to the establishment and backetc.
15. **The Building and Other Construction Workers (Regulation of Employment and Conditions of Service) Act 1996** and **the Cess Act of 1996**: - All theestablishmentswhocarryonanybuildingorotherconstructionworkand

employs the prescribed minimum (say, 10) or more workers are covered under this Act. All such establishments are required to pay cess at the rate not exceeding 2% of the cost of construction as may be notified by the Government. The Employer of the establishment is required to provide safety measures at the building or construction work and other welfare measures, such as canteens, first-aid facilities, ambulance, housing accommodations for workers near the work place etc. The Employer to whom the Act applies has to obtain a registration certificate from the Registering Officer appointed by the Government.

1. **Factories Act 1948:** - The Act lays down the procedure for approval of plans before setting up a factory, health and safety provisions, welfare provisions, working hours, annual earned leave and rendering information regarding accidents or dangerous occurrences to designated authorities. It is applicable to premises employing the prescribed minimum (say, 10) persons or more with aid of power or another prescribed minimum (say, 20) or more persons without the aid of power engaged in manufacturingprocess.

# Section 4

### Conditions of Contract

**Part – II Special Conditions of Contract**

These conditions vary and add to the Conditions of Contract set out in Part I General Conditions of Contract

Note: The State Government may refer to Clause 34 of GCC and add here the procedure that it would like to adopt for assessing the performance of the Contractor in execution of works / activities relating to Routine Maintenance for five years post construction.

# Section 5

### Specifications

##### Note: The following are the guidelines for framing the specifications and, therefore, will not be part of the contract. These should be excluded from the bidding document.

1. The MoRD Specifications for Rural Roads published by the IRC (1st Revision) shall apply.
2. For items not covered in the MORD Specifications, the Ministry of Road Transport & Highways (MoRTH) Specifications for Road and Bridge Works (5th Revision) shall be followed.
3. Particular specifications:-

For items whose specifications given in MoRD Specifications or in MORTH specifications for road and bridge works need changes partly or wholly due to local conditions, the respective clauses are to be suitably modified to the extent felt necessary giving clause wise description of modifications under this head.

1. MoRD Specifications (1stRevision)

Clauses…………………………………………………………………

1. MoRTH Specifications for Road & Bridge Works (5th Revision) Clauses…………………………………………………………………
2. For purposes of quality control, the MoRD Specifications for Rural Roads (1st Revision) and those covered by the Quality Assurance Handbook of the NRRDA shall apply.

**Section 5 (Cont’d)**

### Drawings

**Note:** The design, drawings, standards and guidelines of the Rural Roads Manual (IRC: SP: 20-2002) and other relevant IRC Standards, Codes etc. are to be followed for all- weather ruralroads.

##### The guidelines will not be part of the Contract. These should be excluded from the bidding document.

**List of Drawings**:-

1. Key Map
2. Road Alignment including crosssections
3. PavementDrawings
4. Surface and sub surface drains with fulldetails
5. Culverts and Bridgesdrawings
6. Drawings for any other Roadstructure.
7. Drawings for road signs, pavement markings and other traffic controldevices
8. Drawings to be followed for actual execution of work should bear the stamp “Good for construction”.
9. Any revision of working drawings should be indicated by pre-fixing R1, R2….. etc. after original reference number. Reasons for each revision should be clearly noted in the drawing.
10. Complete set of drawings should be issued along with other tender documents so as to form part of theAgreement.

# Section 6

### FORM OF BID FOR PART I OF THE BID

##### Technical Qualification Part I of Bid

*The Bidder shall fill in and load this form for Part I of Bid separately from the form for Part II of the Bid.*

To [Name ofEmployer]....................................................................................................

Address [insert address]...................................................................................................

...................................................................................................

Identification Number of Works....................................................................................

Description of Works .......................................................................................................

Dear...................

1. Having read the Bidding Documents, Requirements for submission of documents in ITB Clause 12, and acceptance of provisions for Fraud and Corruption in the Bidding Document, I/we submit in attachment all documents required in the Bidding Document together with all the Affidavits regarding the correctness of information/documents for the above statedbid.
2. I/we confirm that the Bid fully complies with all the requirements including the Bid Validity and Bid Security as required and specified by the biddingdocuments.
3. I/we certify that the information furnished in our bid is correct to the best of our knowledge and belief.
4. I/we undertake to carry out the works of Routine Maintenance for five years after the completion date as per the rates offered by the Employer in the biddocuments.

Authorised Signatory...............................................

Name and Title of Signatory......................................

Name of Bidder.......................................................

Authorised Address of Communication........................

.......................................................................................

Telephone Nos (Office)………………………………

Mobile No.……………………………………………

Facsimile (Fax) No.…………………………………..

Electronic Mail Identification (Email ID) ………………

# Form of Bid for Part II of the Bid

### Technical - Financial Part II of Bid

*The Bidder shall fill in and load this form for Part II of Bid separately from the form for Part I of the Bid*

To [Name ofEmployer]....................................................................................................

Address [insert address]...................................................................................................

Identification Number of Works ....................................................................................

Description of Works ...................................................................................................

Dear...................

1. With full understanding that Part II of our bid will be opened only if I/ we qualify on the basis of evaluation in Part I of the Bid, we offer to execute the works described above, remedy any defects therein, and carry out the routine maintenance in conformity with the Conditions of Contract, Specifications, Drawings and Bills of Quantities accompanying in Part II of theBid.
2. This Bid and your written acceptance of it shall constitute a binding contract between us. I/ we understand that you are not bound to accept the lowest or any bid you receive.
3. I/ we undertake to commence the works on receiving the Notice to Proceed with the Work in accordance with the ContractConditions.
4. As mentioned in Part-I of my/our bid, I/we undertake to carry out the works of Routine Maintenance for five years after the Completion Date as per the rates offered by the Employer in the biddocument.

Signature of Authorised Signatory ...............................................

Name and Title of Signatory......................................

Name of Bidder.......................................................

Authorised Address of Communication........................

.......................................................................................

Telephone Nos (Office)………………………………

Mobile No.……………………………………………

Facsimile (Fax) No.…………………………………..

Electronic Mail Identification (Email ID) ………………

.

# FORMAT FOR THE AFFIDAVIT

(NOTE: This affidavit should be on a non-judicial stamp paper of Rs.10/- and shall be attested by Magistrate/ Sub-Judge/ Notary Public)

I, ……………………………………………………….… (name of the authorised representative of the bidder)son/daughterof residentof

…………………………………………………………………………. (full address), aforesaid solemnly affirm and state as under:

* 1. I hereby certify that all the information furnished with the bid submitted online in response to notice inviting bidnumber

……………….…………………… date issued by

…………………………………………….. (authority inviting bids ) for……………………………………………………………………………

(name and identification of work ) are true and correct.

* 1. \*IherebycertifythatIhavebeenauthorisedby……………………………

…………..……..……………………………………… (the bidder) to sign on their behalf, the bid mentioned in paragraph 1above.

Deponent

Place: ……………..

Date: ………………

* not applicable if the bidder is an individual and is signing the bid on his ownbehalf.

# Section 7

### Bill of Quantities Preamble

1**.** The Bill of Quantities shall be read in conjunction with the Instructions to Bidders, Conditions of Contract, Specifications andDrawings.

* 1. 2. For the construction of works, the quantities given in the Bill of Quantities are estimated, and are given to provide a common basis for bidding. The basis of payment will be the actual quantities of work ordered and carried out, as measured by the Contractor and verified by the Engineer and valued
     1. at the rates and prices tendered in the Bill of Quantities in the case of item rate tenders;and
     2. at percentage rate above or below or at par of the Schedule of Rates as tendered by theContractor.
  2. For the routine maintenance of roads, there is lump sum amount for each year of maintenance per km. The payments will be based on satisfactory performance of routine maintenanceactivities.

3. The rates and prices tendered in the priced Bill of Quantities shall, except in so far as it is otherwise provided under the Contract, include all constructional plant, labour, supervision, materials, erection, maintenance, insurance, profit, taxes (other than GST , as applicable) and duties, together with all general risks, liabilities and obligations set out in the Contract.

4. When percentage rate tenders are invited, the Bill of Quantities will show in the bidding documents, the quantities and rates used for differentitems.

***Bill of Quantities for item rate bids***

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl.  No. | Description of item (with brief specification and reference to book of specifications) | Quantity | Unit | Rate | | Amount |
| In figures | In words |
|  | **Routine Maintenance\*\* after completion of construction works (Lump-sum Amount for each year PerKm.)**  **For 1st year For 2nd year For 3rd Year For 4th Year For 5th Year** |  |  |  |  |  |

##### \*\* The per km amount for each year should be pre-specified by the Authority and the figure inserted here before inviting the Bid.

**Total Bid Price (in figures)-------------------------------------------------------**

**(in words)-------------------------------------------------------**

**Signature**

**Notes:**

1. The item for which no rate or price has been entered in will not be paid for by the Employer when executed and shall be deemed to be covered by the other rates and prices in the Bill of Quantities (Refer: ITB Clause 13.2 and Part I General Condition of Contract 39.3).
2. Unit rates and prices shall be quoted by the bidder in Indian rupees [ITB Clause 14.1].
3. For Routine Maintenance, the unit rate indicated by the Authority shall apply. The Bidder is required to accept these rates. Further, the payment shall be performance based.

***Bill of Quantities for Percentage rate bids***

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| S.l  No. | SOR  No. | Description of item (with brief specification and reference to book of  specifications) | Quantity | Unit | Rate | | Amount |
| In Figures | In words |
|  |  | **Routine Maintenance\*\* after completion of construction works (Lump-sum Amount for each year Per Km)\***  **For 1st year For 2nd year For 3rd Year For 4th Year For 5th Year** |  |  |  |  |  |

##### \*\* The per km amount for each year should be pre-specified by the Authority and the figure inserted here before inviting the Bid.

**\*Employer to fill in the per km amount for maintenance in rate column only**

Signature

Notes:

1. The Schedule of Rate is ……………………………….
2. Wherever there is any discrepancy between the rate entered in the Bill of Quantities and the Schedule of Rates as per Note 1 above, the rate given in the Schedule of Rates willapply.
3. For Routine Maintenance, the unit rate indicated by the Authority shall apply. The Bidder is required to accept these rates. Further, the payment shall be performance based.

# Section 8

### Standard Forms

**Letter of Acceptance and Other Forms**

1. **Letter ofAcceptance**

**Standard Forms**

*[*Letter head *paper of the Employer]*

**Notes on Standard Form of Letter of Acceptance**

The Letter of Acceptance will be the basis for formation of the Contract as described in Clauses 29 and 30 of the Instructions to Bidders. This Standard Form of Letter of Acceptance should be filled in and sent to the successful Bidder only after evaluation of bids has been completed and approval of the competent authority has been obtained.

*[Date]*

To:

*[Name of the Contractor]*

*[Address of the Contractor]*

This is to notify you that the Employer,namely,

has accepted your Bid dated for execution of the

*[name of the Contract and identification number, as given in the Contract Data] and Routine Maintenance of the works for five years* for the Contract Price ofRupees

*[amount in figures and words]* is hereby accepted by our Agency.

You are hereby requested to furnish Performance Security, (and additional security for unbalanced bids in terms of ITB Clause 26.3) *[where applicable]* in the form detailed in Cl. 30 of ITB for an amount of Rs.————— within 10 days of the receipt of this Letter of Acceptance valid up to 45 days from the date of expiry of Defects Liability Period i.e. up to ............ and sign the Contract. If the Performance Security is in the form of a Bank Guarantee, the period of validity of Bank Guarantee could be one year initially, however, the Contractor would get this Bank Guarantee extended in such a way that an amount equal to the requisite Performance Security is always available with the Employer until 45daysafterthelapseofDefectsLiabilityPeriodfailingwhichactionasstatedinCl.

30.3 of ITB will be taken.

2. You are also requested to indicate your nominee as required under Clause 53.2 of theGCC.

Yours faithfully,

AuthorizedSignature:

Name and Title ofSignatory:

Name ofAgency:

Attachment:

# Issue of Notice to Proceed with theWork

(Letter head of the Employer)

———— (Date)

To

—————————————— (Name and address of the Contractor)

——————————————

——————————————

Dear Sirs:

Pursuant to your furnishing the requisite Performance Security as stipulated in ITB Clause 30 and signing of the Contract for the construction of ———————————

———— and routine maintenance for five years after completion of construction, you are hereby instructed to proceed with the execution of the said works in accordance with the contractdocuments.

Yours faithfully,

(Signature, name and title of signatory, authorized to sign on behalf of

Employer)

# Standard Form ofAgreement

#### Standard Form: Agreement

##### Agreement

This Agreement,madethe dayof 20 , between

[name and address of Employer]

(hereinafter called “the Employer”) of the one part, and

[name and address of Contractor] (hereinafter called “the Contractor” of the other part). Whereas the Employer is desirous that the Contractor execute

[name and identification number of Contract] (hereinafter called “the Works”) and the Employer has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein at a cost ofRupees...............................

NOW THIS AGREEMENT WITNESSETH as follows:

1. In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.
2. In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all aspects with the provisions of theContract.
3. The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and remedying the defects within the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by theContract.
4. The following documents shall be deemed to form and be read and construed as part of this Agreement,viz:
   1. Letter of Acceptance;
   2. Notice to Proceed with theworks;
   3. Contractor’s Bid;
   4. Contract Data;
   5. Special Conditions of Contract and General Conditions ofContract;
   6. Specifications;
   7. Drawings;
   8. Bill of Quantities;and
   9. Any other document listed in the Contract Data as forming part of the Contract.

In witness whereof, the parties thereto have caused this Agreement to be executed the day and year first beforewritten.

The Common Sealof

was hereunto affixed in the presence of:

Signed, Sealed and Delivered by thesaid

in the presence of:

Binding Signature ofEmployer

Binding Signature of Contractor

# Form of unconditional Bank Guarantee from Contractor for [To be specified byState]

# 