|  |  |  |
| --- | --- | --- |
|  |  | **LIST OF WORKS JOGINDERNAGAR (EDUCATION)** |
| **Sr.No** | **Job No.`** | **Name of Project** | **Date of** **Requirements received** | **Date of receiving plans & details** | **Date of approval** | **Date of feasibility** | **Status of project** | **Physical status** | **Likely date of completion** | **Remarks** |
|  |  |  |  |  |  |  |  |  |  |  |
|  | 6593 | Govt.Sr.Sec. School at KutheratehJogindernagardisttMandi | 22.6.09 from e.e | 22.6.09From e.e |  | 3-8-09. from e.e | 28-8-09layout& sketch drg. issued10.6.15working drawing issued | 90% work completed | 30/06/2018 |  |
|  | 6593 | Govt.Sr.Sec. School at DrubbletehJogindernagardisttMandi | 25.4.08 from e.e | 26.11.08 from e.e |  | 3.8.09 | 6.10.09 sketch drg.issued | Work completed | - | - |
|  | 6593 | Govt.Sr.Sec. School at BassitehJogindernagardisttMandi | 18.8.09 from e..e | 18.8.09 from e.e |  | 6-1-10 from e.e6.1.10 from e.e | 9-11-09 layout &sketch drg. Issued10.11.09 drg. Issued to director | Work not started | Site not handed over by the Education department. |  |
|  | 6593 | Govt.Sr.Sec. School at Alipabu (Dhar) tehJogindrnagardisttMandi | 14.12.09 from e.e | 14-12-09 from e.e |  | 7.1.10. from e.e | 6-1-10layout plan issued28.1.10 Working drawing issued | Work completed | - | - |
|  | 6593 | **GSS School Chauntra ( extension of play ground)** | 21.8.13 19-5-14 20.12.14 from e.e | 16.8.12.from e.e |  | 21.9.12 from e.e | 13.2.14 letter issued to e.e22-3-14.sketch drawing issued30.8.14.&.25-02-15.Working drawing issued | Work of site development is in progress. | 06/2018. | - |
|  | **Mz-361** | **Govt. Degree College at LadbhharolDisttMandi** | 22 Mar. 2014.From director31.7.15 from Principal.02.02.17 from e.e | 7.9.12 &19.12.12 &27-06-2014 from e.e | 20-6-15 from director | 18.4.15.from e.e | 11.10.12,11.1.13,6.2.14 Letter issued to director &e.e26-12-14.drg.issued23-01-15.sketch drg. issued24-03-15letter to e.e.30.5.15.drg.issued18.9.15 drgs.Issued06.02.17 drg.issued. | 90% site development work completed. | 31/12/2019. | - |
|  | **Mz-251** | **Govt. degree college at jogindernagardistt. Mandi(master plan for accommodation,canteen,multipurpose hall)** | 1.4.2009from e.e5/12/2013. From s.e21.4.15.from e.e | 8.10.13 from e.e | 11.-2.15 from director | 22.5.15From e.e | 25.9.14 lay out &sketch drawing issued14-10-14.letter to principal25-02-15.letter to director26.9.15 drgs. Issued. | Work of Multipurpose hall is in progress and tender for canteen received. | 30/06/2019 | - |
|  | 6593 | **Govt.sen .sec. school (Girls)AT Jogindernagar****Distt. Mandi (H.P)** | 10.4.14 from e.e | 10-4-14 from e.e |  | 23-6-14From e.e incomplete feasibility | 19-5-14 sketch drawing issued | Work completed | - | - |

 Executive Engineer, B&R Division, HPPWD., Joginder Nagar.