|  |
| --- |
| **List of Work Juciciary 12th Circle Nahan** |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval**  | **Date of feasibility** | **Status of project** | **Remarks.** |
| 1 | 4721 | Additional accommodation in sub judge court at Rajgarh.  |  | From E.E.Rajgarh Division, Vide lt. No 20683-86 dt. 30/03/2016 |  | Vide letter no 5567-70 dt. 31/07/2017 | W/Drawings issud to The Distt. & Session judge Sirmour vide letter no 2219-22 dt. 04/09/2017 | Estimate submitted vide 12th Circle office letter No.3076-78 dated 27.12.2017 for amounting to Rs 56.28 Lakhs. For accord of A/A & E/S. |
| 2 | 3704 | C/O Addl. Court building and residences for judicial officers at Nahan.  |  | From EE, vide letter no 784-87 dated 30/07/15. |  |  | Site plan awaited vide letter no 758-60 dated 31/05/2017 Requirement awaited vide letter no 3318-20 dt. 02/12/17 | Now, fresh contour site plan requirement along with cross sections and Photographs of the site have been submitted to Chief Architect Shimla vide EE Nahan letter No.784-87 dated 30-7-2015 for preparation of lay out sketch Drawings & other drawings. |
| 3 | 3704 | ADR Centre at Nahan Distt. Sirmour |  | Vide letter no 1381-82 dated 18/03/2013. | Vide letter no 2364 dated 3 september 2013. |  | Layout Plan,Revised working drawings with revised specification sent to EE, nahan vide letter no 1942-43 dated 05/09/16. | Finishing work in progress. |
| 4 | 3704 | C/O residential colony for judicial staff at paonta Sahib.  |  |  |  |  | EE, Paonta Sabib requested for Working drgs. Vide letter no 2337-A dated 13/06/13. | Ground floor slab laid , columns for 12st floor casted shuttering for 1st floor slab in progress (30% work completed). |
| 5 | 3704 | Estimate for raising Fire residence wall around the Judicial Court complex land at Nahan.  |  |  | Vide letter no 3125 dt. 23/10/2017 |  | EE, Nahan Division. Requested to supply design of fire residence wall vide letter no 1680-81 dated 13/12/13. | E.E. Nahan as requested to Chief Archtect P.PWD., Shimla for evolving the drawings for fire residence wall around the judicial court complex but the same is still awaited from Chief Architect HP.PWD., Shimla shown in the absence of the same estimate could not be prepared. |
| 6 | 3704 | C/O Office-cum-residential Accommodation for the Asstt. Distt. Attorney and staff at Rajgarh regarding requirements thereof.  | Vide letter no 6423 dated 12/08/2014. | Vide letter no 8718-21 dated 09/09/2014. |  | Vide letter no 8443-45 dt. 06/10/17 | Letter issued to EE, Rajgarh to supply the W/drawings issued to The Director of prosecution HP. Shimla -9 vide letter no 2223-25 dt. 04/09/2017 | Estimate submitted vide 12th Circle office letter No.3073-75 dated 27.12.2017 for amounting to Rs 142.86 Lakhs. For accord of A/A & E/S. |
|  |  |  |  |  |  |  |  |  |
| 7 | 3704 | C/O Judiciary staff colony at Nahan.  |  | Vide letter no 1108 dated 28/07/2015. |  |  | Detailed requirement may kindly be forwarded vide letter no 1614-17 dt. 26/07/17 from The district & Session Judge, Sirmour, Nahan HPSite visited on dt. 14/12/17 Drgs. U/Preparation.  | The Contour site plan , along with accommodation requirement of Judiciary Staff Quarters was submitted to Chief Architect. HP PWD Shimla vide EE Nahan office letter No. 1110-13 dated 10-10-2012. The observations received from Chief Architect Shimla vide letter No. 3215-19 dated 26-11-2012. Now, fresh contour site plan requirement along with cross sections and Photographs of the site have been submitted to Chief Architect Shimla vide EE Nahan letter No.784-87 dated 30-7-2015. |
| 8 | 3704 | C/O Office Accommodation for District Attorney, Sirmour at Nahan- Reg. Preparing estimated cost and layout plan.  | Vide letter no DPr-B(Office Accom.)Nahan/2017-689 dated 03/02/2017 | Vide letter no .DA/SRM/NHN/2016-1453 dated 01/03/2017Vide letter no .DA/SRM/NHN/2016-225 dated 08/05/2017 |  |  | Layout plan, and working drawings sent to The Director of Prosecution HP Shimla-9 vide letter no 389-92 dated 06-05-2017Working drawing &layout plan sent to The Director of prosecution, HP, Shimla 9 vide letter no 850-53 dt. 06/06/17 | Tender opened on dated 1.2.2018 and is being scrutinized in division office which will be sent to higher authority very shortly for finalizing. |
| 9 | 3704 | Preparation of contour site plan for the C/O Office Accommodation for district Attorney, sirmour at nahan.  |  |  |  |  | Director of Prosecution, HP, Shimla-9 requested to CA, for preparation of contour site plan vide letter no 1979 dated 09/03/2017. | Tender opened on dated 1.2.2018 and is being scrutinized in division office which will be sent to higher authority very shortly for finalizing. |