**List of works Mandi (GAD) 1st circle**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr.No** | **Job no.** | **Name of Work** | **Date of requirements received** | **Date of receiving site plan & details** | **Date of approval** | **Datof feasibility** | **Status of projrct** | **Status Supplied by SE.** |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  | 7130 | Residence for mentally challenged children at sundarnagar |  | \*30.3.17 |  |  | \*letter issued to EE Sundarnagar for the detailed contour site plan and requirements from the concerned department on dt. 7.4.17 |  - |
|  | Mz-380 | Beautification and improvement of roundabout at Gandhi chowk & development of Chowk & Park near ITI Mandi  |  |  |  |  |  | Work is in progress. |
|  | MZ-299 | Landscaping development plan at Shiv-Mandir at Nagchala  | 31.5.2008 | 31.5.2008 | --- | --- | Drg. Issued on dt5/6/08 |  - |
|  | CZ-146 | M.c toilet block and rain shelter for M.C Mandi near new Suketi bridge. | 21.9.2010 | 21.9.2010 | -- | -- | Drg. Issued. On 30.10.10  | Work completed. |
|  | 3927 | Mini secretariat Sundarnagar Litigant cell  | 29-5-2012 | 29-5-2012 | 6-7-2013 | 7-12-2012 | Drg issued in dt 7.6.11 \*issued on dated 6.7.11 \*drgs issued on dt.19.7.11 |  |
|  | 6609 | Sunken Garden (Shopping Complex ) at Mandi H.P\* Planning of shops | 23-1-2012 |  |  |  | Letter issued to Executive officer Municipal Council Mandi H.P vide letter no 2583-86 dt 15.2.12 for the detailed site planDrg.issued.\*sketch drgs issue dt. 9.2.17 | Work completed. |
|  | Cz-342 | Provision of Electronic Voting Machine (E.V.M) ware-house. | 27-1-2011 | 27-1-2011 |  |  | \*issued on dt.7.02.2011 in person. | Approval awaited . |
|  | 3251 | Deputy commissioner building Mandi  |  |  |  |  |  |  |
| \* provision of Parking | 28.08.2009 | 28.08.2009 | --- | -- | \*re issued on.dt7.2.10 | Feasibility & approval awaited |
| c/o of light weight pre- fabricated structure and multipurpose hall Over DC OFFICE  | 5-3-10 | 5-3-10 | -- | -- | \*Drgs alreadyissued vide letter no 27.7.10 \*drgs reissued on dt. 26.2.13 \*drgs issued vide on dt. 7.6.14 | Feasibility & approval awaited |
| \*Rehri Market and unloading yard at By-Pass (NH) Mandi |  | 17.4.13 |  |  | \*sk drg issued on dt. 26.4.13 vide letter no84-89\*sk drgs reissued on dt 20/5/13 vide letter no. 127-32 |  - |
|  | Cz-123 | REST HOUSE AT SANDHOLE | 28.03.2006 | 28.03.2006 |  | 23.1.2007 | Working dwg Issued on dt 14.3.07 | Pertain to Joginder Nagar Circle.  |
|  | Mz-191 | \*Zila Sainik Welfare Mandi.\* Office building and living accommodation for Army recruitment office Mandi.  | 21.07.200018.10.2011 | ---- | --- | --- | -- | Requirement & site data awaited from director sainik welfare deprt. Hamirpur vide office dt 2.11.11 |
|  | Mz-353 | New Bus Stand Complex at Karsog (HP) | --- | 28.12.11 | ----- | ----- | Letter issued to The Managing Director H.R.T.C. Shimla HP dt 15.2.12 | \*\*\*\*\*\*\*\*Requirement awaited |
|  | Mz-359 | C/o community hall at Kangoo in Gram Panchayat Kangoo. | **22.6.12** | **22.6.12** | **--** | 21.3.13  | sketch. 12.7.12 vide Working drgs issued to EE Sundarnagar on dt. 23.4.13 |  |
|  | Mz-102 | Food and supply Deptt.(standard laboratories) | 8.1.13 |  9/1/13 | **---** | **----** | sketch. drgs issued wide letter no. 388-93 on dt. 23.8.13  | Feasibility & approval awaited |
|  | CZ-363 | Multi-purpose hall in the premises of paddal stadium ground. | 6.3.13. | 6.3.13. |  |  | \* drgs issued on dated 7.3.13 vide letter no. 2291-96. | \*\*\*\*\* |
| \*development of paddal ground | 6-01-2015 | In person dt6-01-2015 |  |  | \*drawing issued vide letter no. 1303-1307 dt. 16.01.15 | Work completed. |
|  | Mz-367 |  Balh sadhan at Dadour. | 9.5.13 | 9.5.13 |  |  | \*drgs issued vide letter no. 390-93 on dt. 4.7.14 | \*\*\*\*\*Approval & feasibility awaited |
|  | 4578 | Sub-Jail at Mandi |  |  |  |  |  |  |
| \* Type-II Qtrs. |  |  |  |  | \*Drawing issued on dt 20-5-10 | Work completed. |
| \*construction of parking-cum-commercial complex. |  |  |  |  | \*letter issued to the Director General Of Prisoners(H.P) vide letter no. 1748-55 dt.28.7.11\*letter issued to E.E Mandi div.II mandi vide letter no 2786-90 dt 26.3.12\*letter issued to EE Mandi-II on dt. 26.4.13 vide letter no. 79.83 | Site not handed over. |
|  | \*Sub-jail Behna | 12-6-2012 | 1.8.12 vide 4-11-2011 |  |  | \*letter issued to Chief Architect HPPWD Mandi on dt.11.9.12\*conceptual drg issued for approval on dt. 24.9.12 vide letter no.\*letter issued to EE Mandi –II vide letter no 953-60 on dt. 9.11.12\*letter issued to the Additional Director General (prisos) HP Shimla vide letter no. 2079-84 dt. 11.1.13\*drgs issued on dt. 1.2.13 vide letter no. 4298-4307 form the office of chief architect Shimla. | Shifted at Batahalari near Ner-Chowk.  |
|  | \*Central jail Mandi at Batahalari near Nerchowk |  | \*New. site plan 26.6.14 & re submitted dt.20-01-2015 |  |  | 2\*letter issued to EE Mandi-II for the complete site data of the proposed site vide letter no. 365-69 on dt. 3.7.14\*letter issued to EE Mandi-II vide letter no. 733-36 on dt. 10.9.14.\*letter issued to The Deupty Commissioner, Mandi vide letter no. 831-35 on dt. 14.10.14 ( contoured site plan still awaited.)\*Letter issued to The Sr. EE Elect. Div. HPSEB , Ltd. Sundarnagar vide letter no. 1060-63 dt. 15.11.14.\*letter issued to The Deputy Commissioner Mandi on dt. 6.7.15decision of the land. | Site not handed over by the client department.  |
|  | Cz-123 | Add. Accommodation on first Floor of rest house at Chatri distt Mandi | 8-9-2008 | 8-9-2008 |  | 16-6-2009 | Drawing issued on dt 09-6-09 | Detailed estimate under process.  |
|  | Cz-123 | Rest House/Gang hut at Galma distt Mandi | 23.2.2010\*11.5.17 | 23.2.2010\*11.5.17\*7.7.17 |  | 29.3.2010 | Drawing issued on dt 17.11.11 vide letter no 2190-95 | Roofing work is in progress.  |
|  | Cz-123 | Rest house at thachi distt. Mandi. | 07.10.2009 | 07.10.2009 | ----- | 21.10.13\* | Issued on dt dt. 28.2.13\*Revised drgs issued on dt. 4.2.14 | Work is in progress and all drawings received.  |
|  | Cz-162 | Existing type-IV qtrs near vishwakarma temple Mandi | 23-10-2011 | 23-10-2011 |  | .6.7.11. | Working dwg issued on 26.4.11. | A/A & E/S awaited.  |
|  | Mz-348 | A.E OFFICE & TREASURY BUILDING AT BALI CHAWKI. | 21.04.2011 | 21.04.2011 | 21-02.2012 | 29.7.2011  | \*working dwg issued on 6.2.14 | Structure drawing of first floor top beam & slab and second floor trusses with joinery details required.  |
|  | 5009 | Add.acc. for Circuit house Mandi | 12-05.2015 | 12-05.2015\*14.7.15\*13.7.15 (guard hut & store) | Yet not recieved | 7.10.15 | Working Drgs. Issued on dt. 25.6.14\*drgs issued dt. 29.6.15.\*letter issued to EE mandi on dt. 20.11.15\*letter issued to EE Mandi-II on dt. 12.5.17 | Work awarded to the contractor and site development work is in progress.  |
|  | 5009 | NEW SITE FOR CIRCUIT HOUSE AT KANGNI, DISTT. MANDI | 12.7.13 | 12.7.13  |  |  | Scheme under consideration  | \*\*\*\*\* |
|  | Cz-162 | Transit accommodation for PWD staff at Paddle Mandi | 12.4.12 | 12.4.12 | -- | 29.10.14  | Skt drgs issued on dt. 23.9.14\*working drs issued dt. 3.9.15 | Land dispute.  |
|  | Cz-298 | Divisional office bldg at Karsog HP.PWD. Karsog Distt. Mandi. | 13.05.08 | 13.05.08 | Std drawings adopted | 09.09.2008 | Working Drg. Issued on dt 19/7/08 | Work is in progress.  |
|  | Mz-128 | Additional. Accommodation. For inspection hut/ rest house at Dehar | 29.6.12 | 29.6.12 | --- | 4.10.12 | \*drgs issued on dt.30.8.12 vide letter no.753-56 | Approval awaited |
|  | MZ-295 | Construction of div. office building gohar. | 21-5-2008 |  |   | 10-2-2009 | \*issued on dt. 9.7.13  | Completed.  |
|  | Cz-262 | Construction of type-II quarter for PWD staff at Sundarnagar  |  |  1.8.13 |  |  | \* LAYOUT PLAN on 19.3.14\*drgs (type-II) issued vide on 29.3.14 | Work in progress. |
|  | MZ-258 | Mini-sectt. At karsog | 19-03-2015\*2.11.15\*1.2.2016\*04.01.2016 | 19-03-2015In person\*22.4.2015\*7.10.2015\*section received dt. 28.11.15 | **\*16.04.2016** | **\*8.4.16** | **\*layout plan & sketch drgs on dt. 25.4.15.****\*letter issued to Ee Karsog on dt 19.05.15 for the complete site plan of the site.****\*letter issued on dt. 4.6.15 for the complete site information.****\*letter issued on dt. 4.7.15 for the detailed site plan and branch wise requirements of accommodation.****\*letter issued on dt. 12.10.15 for the detailed site plan still awaited.****. sketch drgs issued on dt. 9.2.2016****\*working drg issued dt. 25.4.16** | \*\*\*\*\* |
|  | 7085 | State vigilance and anti corruption bureau office building at ram nagar Mandi (hp) | **2.1.14** | 2.1.14  | **---** | 27-8-14 | **Sketch drgs issued dt. 29.1.14****Working drgs issued on dt. 14.3.14** | A/A & E/S awaited. |
|  | Mz-375 | Mini secretariat building at Nerchowk Mandi H.P. | 8.1.16\*9.5.16 |  4-1.2014\*10.2.14\*revised dt. 13.01.16\*revised dt. 17.6.16 | **31.3.17** | **21.2.17** | **\*letter issued 13.2.14 for the requirements.****\*drgs issued on dt. 17.2.16****Drgs. Issued to d.c for approval on dt14.2.17** | A/A & E/S awaited.  |
|  | Mz-204 | Office building for SMS /HDO and HEO at Sundarnagar. | 21-10-2013 | 03.2.14 5.7.16 from e.e | **5.11.15** | **22.8.15** | **sketch drgs drgs issued vide letter no. 1036-40 on dt. 10.2.14****drgs.issued for approval on dt. 9.10.15.****working drgs. Issued on dt. 10.6.16** **& also on 16.7.16** | Work is in progress. |
|  | Mz-379 | Shri Panchvaktra temple Mandi  | 23-04-2014 | 23.4.14  |  |  | **Sketch drg.issued vide letter no. 247-52 dt. 19.6.14.** | **\*letter issued to EE Mandi-II vide letter no. 443-47 on dt 11.7.14 ( for marking HFL on the proposed site)** |
|  | Mz-381 | Parking near Tehsil office building at Mangwain Mandi | 29-04-2014 | 29-04-2014  |  | \*feasibility received from EE Mandi-II vide letter no. 6200-01 dt. **23.6.14** & dy. No. 133 dt. 27.6.14. | **\*drg issued vide letter no. 205-209 dt. 16.6.2014** | Land not available.  |
|  | 7045 | C/O Kids swimming pool at Bhiuli ,Mandi | 16-06-2014 | 27-05-2014 |  | **Sketch drg.** | \* drg issued vide letter no. 215-219 dt. 17.6.2014 | Work completed.  |
|  | 7085 | C/O S.P.SV & ACB Central Range Mandi (Residence Building) |  | 23.6.14  |  | **\*3.6.17** | \*letter issued to S.P SV & ACB Central Rande Mandi vide letter no. 190-94 dt. 12.6.14 (site plan still Awaited)\* drgs issued dt. 31.7.14\*letter issued to EE Mandi-II dt. 02.09.2014\*drg issued dt2.2.17 | Working estimate is under preparation.  |
|  | Mz-363 | Sanskriti sadan at Motipur Mandi  | 20.3.14  | 20.3.14  | **22.12.16** | **26.7.15****\*25.5.16** | **\*drgs issued dt. 29.7.15****\*w/drg. Issued dt. 15.2.17** | Work awarded to the contractor by the EE Mandi Division No.II vide letter No. 23751-59 dated 04-10-2017. Structural drawings submitted to the Chief Engineer on dated 07-03-2018 for approval. Revised Tatima of land domarcated at site and revised digital map under preparation for correction in FCA case. |
|  | Mz-363 | Indoor Stadium at Motipur Paddel Mandi | 10.10.14  | 20.3.14  |  | **Sketch drawing** | **\*drawings iddued vide letter no. 1259-63 on dt. 7.1.2015** | \*\*\*\*\* |
|  | 385 | MT Godown under MANREGA at Thunag | 10-09-2014 | 10-09-2014 |  |  | **\*letter issued to Chief Architect vide letter no. 420-23 on dt. 9.7.14 ( request for the supply of standard drgs. Of 200 MT Godowns )** |  - |
|  | Mz-386 | Stadium at Baldah village Chaloh P.O Saigalu Kotli | 20.11.14 | 20.11.14  |  |  | **Layout plan** | Insufficient site. FRA under process.  |
|  | 7640 | Sub-Tehsil Building at Bhadrota , Sarkaghat. | 7.8.14 | 7.8.14 |  | **17.8.16**  | **Drgs issued on dt. 11.5.15 vide letter no. 84-88.****5.7.16 letter issued****28.7.16 drgs. Issued for approval** | A/A & E/S received.  |
|  | CZ-229 | BUS-STAND MANDI TOILET BLOCK. | 24.6.14**\*18.4.17 (color scheme)** | 24.6.14 | 17-07-2014 | \*feasibility received from Ee Mandi-II vide letter no. 8821-22 dt. 17.7.14 & dy. No. 184 dt. 19.7.14. | DRG HandedoverOVER TO A.E CONCERN IN PERSON ON DT. 16.6.13 & 17.9.13\*drgs issued vide letter no. 394-99 on dt. 4.7.14.\*drawings issued vide letter no. 1072-77 on dt. 18.11.14.\*working drgs issued dt.9.9.15**\*detail of flooring pattern issued dt. 25.4.17** | Not pertain to this department.  |
|  | 4850 | Divisional commissioner office Mandi (type qtrs) | 23.4.15 | 23.4.15  | **--** | **---** | Letter issued on dated 12.03.15 along with cross sections. | A/A & E/S awaited.  |
|  | 8058 | Stadium at Sandhol. | 29.10.14 |  29.10.14  | **16.5.16** | 30.12.14 | \*Sketch drg issued in dt. 18.11.14.\*working issued drawings dt. 21.5.15 | Pertain to Joginder Nagar Circle. |
|  | 7085 | C/O Police VHF Repeater Station at Naina-Deviji Tehsil Balh , Distt. Mandi. |  | **23.10.17** |  | 21.1.15 | w.DRGS ISSUED DT. 21.11.15 | Work is in progress.  |
|  | Cz-289 | Fire station at Jhamar , Mandi | 18.4.15 | 18.4.15 | **---** | **4.2.16** |  **Sketch drgs** issued on dt. 24.4.15 \*letter issued to The Commander (Home Guard) 6th Battalion Mandi. On dt. 23.2.16\* working drgs issued vide letter no. 121-125 dt. 28.4.16 | Work is in progress.  |
|  | Mz-395 | Company commander home guard and fire brigade office at Karsog. | **----** | 20.6.15. | **---** | **---** | --- | Does not pertain to Karsog Division. It pertain to BDO office Karsog.  |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 48 | 4403 | c/o AE office at Kotli | 11-06-2015 | 11-06-2015 | **---** | **---** | W.drgs issued |  Land is not available.  |
| **49** | **Mz-403** | **S**ainik sadan Sainik Rest House complex Mandi. | **\_** | **7.04.2016** | **\_** | **-** | \*letter issued to EE Mandi-II for the Appropriate site data as well as requirements . | Land is not available. |
| 50 | Cz-146 | Shelter for Urban Homeless in Mandi. | **27.5.16** | **27.5.16** | **21.7.16****\*19.7.17** |  | **Sketch drgs issued dt. 1.6.16** | Site not handed over.  |
| 51 | Cz-231 | Bus stand sarkaghat | **18.1.16** |  |  |  | **Lettr issued to Chief Architect** regarding status of the project in dt. 19.01.16 |  |
| 52 | MZ-399 | Panchayt Ghar Sehali | **1.10.15****\*19.10.15** | **29.8.15** | **25.2.16 from Distt. Panchayat officer Mandi** |  | **Letter issued to EE Mandi-II for the requirements and photograph of the site on dt. 29.9.15****\*drgs issued dt. 1.02.2016****\*joinery detail issued dt. 12.4.16** | 90% work is completed and finishing work is in progress.  |
|  | MZ-399 | Panchayt Ghar Bhargoan | **1.10.15****\*19.10.15** | **29.8.15** | **25.2.16 from Distt. Panchayat officer Mandi** |  | **Letter issued to EE Mandi-II for the requirements and photograph of the site on dt. 29.9.15****\*drgs issued dt. 1.02.2016****\*details issued dt. 22.4.16** | Work completed.  |
|  | 6609 | Re-construction of Kargil Park Mandi | **22.6.15** | **22.6.15** |  | **3.5.15** | **\*drgs issued dt. 30.1.16****\*working drg issued dt. 28.5.16****\*drgs re-issued dt. 8.7.16****\*letter issued to D.C Mandi dt. 30.11.16** | Approval awaited from client department.  |
|  | CZ-230 | A.E Office cum Residence at Rewalser. | **4.9.15** | **4.9.15** |  |  | **Std . drgs issued****In person**  | Land is not available.  |
|  | Cz-265 | HPPWD Sub-Division at dehar. |  | **15.12.15** |  |  | **\*letter issued to EE Sundarnagar for the photographs and drawings of the existing JE Residence on dt. 19.12.15** | Estimate under process.  |
|  | 4792 | Type-III or Type-II residential building district treasury office Mandi. | **6.7.15****\*** | **6.7.15****\*1.11.16** |  | **8.01.16****\*29.2.16****\*7.9.16** | **Layout and sketch drgs issued on dt. 24.11.15****\*working drgs issued dt. 2.2.16****\*revised drgs issued dt. 9.6.16** | Feasibility report submitted by the EE Mandi-II vide letter No. 3712-13 dated 06-05-2016. |
|  | 4792 | Sub treasury office at Chachiot , Gohar | **28.11.15** | **28.11.15** | **29.2.16** | **8.3.16** | **Sketch drgs issued dt. 21.1.16****\*w/drg issued dt. 7.3.17** | Work awarded to the contractor.  |
|  | 4792 | Departmental building at Deputy Director / Distt./ Sub-Treasury Offices. | **7.12.15** | **7.12.15** |  | **6.5.16** | **Sketch drgs issued dt. 2.2.16** | Working drawing awaited.  |
|  | 415 | Hot water pool near Laxmi Narayan Temple at Tatapani , Karsog | **25.7.16** | **25.7.16** | **6.2.17** | **10.3.17** | **Drg issed dt. 20.1.17****\*working drgs issued dt. 21.6.17** |  - |
|  | 7526 | Additional accommodation at SE Office 1st circle HPPWD mandi | **2.7.16** | **2.7.16** |  |  |  | Preliminary estimate submitted to the E-in-C office vide CE(MZ) office letter No. 22437-40 dated 02-02-2018 amounting to Rs. 71,05,000/-. |
|  | 162 | Type-II Qtrs PWD Colony rewalsar |  |  |  |  | **\*joinery detail issued dt. 7.11.14** | Work is in progress.  |
|  | 162 | Zila parishad office building Jail road mandi (conversion into residential purpose)  |  |  |  |  | **Sketch drg issued dt. 28.8.15** | Not constructed by this department.  |
|  | 424 | Press club building Nerchowk | **23.12.16** | **26.12.16** **Letter no. 31297-99 dt 23.12.16****\*existing plan and photographs letter no. 35753-54 dt. 4.1.17****\*9.1.2017** |  |  | **\*drgs issued 31.01.2017** | Preliminary estimate submitted DPRO vide EE Mandi-II office letter No. 19051-54 dated 29-08-2017 for Rs. 24,23,300/-. |
|  | 7085 | TYPE-II QUARTERS AT POLICE RESIDENTIAL COLONY AT DHANGSIDHAR MANDI | **11.1.16****21.1.16** | **8.11.16** |  |  | **Drgs issued.** | Work completed. |
|  | 4792 | Treasury office building at baldwara disstt. Mandi | **18.2.2****017** | **27.02.2017** | **12.6.17** | **21.4.17** | **Letter issued for requirements on dt. 4.3.17****Drgs issued dt. 28.3.17****\*letter issued to EE Sarkaghat on dt. 4.5.17****Working drgs. Issued on dt. 6.10. 17.** |  - |
|  | Mz-399 | Panchayat Bhawan at Sarkaghat |  | **23.5.17** |  |  | **\*letter issued by EE Sarkaghat on dt. 2.6.17 for the requirements to be housed in the building.** |  - |
|  | 6609 | Municipal Committee office building Mandi |  | **02.01.17** | **13.2.17** | **14.2.17** | **\*drgs issued dt. 09.2.17****\*drgs reissued dt. 17.2.17****\*drg issued dt. 25.5.17** | Approval of drawings awaited from the client department.  |
|  | 6609 | 2 NOS. SHOPS AT SERI BAZAR MANDI | **3.12.16** | **3.12.16** |  |  | **DRG ISSUED DT. 2.8.17** | Not pertain to this department.  |
|  | MZ-431 | Residential building for mentally challenged children s/nagar distt mandi (HP) |  | **29.7.17** |  |  |  |  |
|  | Mz-427 | Excise and taxation office at sarkaghat distt. Mandi (HP) | **19.1.17** | **19.1.17** |  | **2.5.17 &22.5.17** | **Drgs issued dt. 24.4.17** | Work is in progress.  |
|  | MZ-123 | Rest house at Janjehli | **24.8.17** | **24.8.17** |  |  |  |  |
|  | MZ-123 | Rest house at sarkaghat(additional accommodation) | **19.7.17** | **19.7.17** |  |  | **\*letter issued to EE sarkaghat for the detailed plan of existing rest house.dt. 3.6.17** | Contour site plan sent to the Senior Architect Mandi Zone and necessary working drawing awaited.  |
|  | MZ-123 | Rest House at Sudhar(additional Accommodation) | **6.7.17** |  |  |  | **\*drgs issued dt. 4.9.17** | Working drawing has been prepared and estimate is under preparation.  |
|  | MZ-123 | Rest House Gulma | **7.7.17** | **7.7.17** |  |  | **\*letter issued to EE Mandi-II dt. 11.9.17 for the existing roof plan.** | Roofing work is in progress. |