LIST OF WORK, 11th  CIRCLE RAMPUR – EDUCATION

| Sr. NO. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Status report by SE. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1 | 6432 | Govt. Sr. Sec. School at Barach | No. E.D.N.-11(9)3-19/2008, D.H.E., Dated: 09/09/2010 |  | No. 5676-79, dated: 26/03/2012 | No. E.D.N.-H (9) 3-18/2008, D.H.E., dated: 26 April, 2012 | No./ 2014-15-14731, dated: 21/01/2015 |  | Funds not available |
| 2 | 6432 | Govt. Sr. Sec. School at Khammadi | No. E.D.N.-H (9)3-6/2004, dated: 4,06,2005 | No./10-6412-14, dated: 20/08/2009 & No./05-1254-56, dated: 27/04/2005 | No. 2011/- 1298-1301, dated: 07/07/2012 & No. 4407-10, dated: 17/01/2006 | No. E.D.N.-H (9)3-5/2005-D.H.E., dated: 2/06/2006 | No. 15638-40, dated: 19/01/2013 & NO. 2014-15-10641, dated: 03/11/2014 | Working drawing issued vide letter no 1060-63 dated 16/6/2014 | Available funds are too meager to start the work. |
| 3 | 6432 | Govt. Sr. Sec. School Khunni | No. 2/2005, 273, dated: 26/02/2005 | No. 14-15, 10256, dated: 27/10/2014 |  |  | No. / 05-13530-32, dated: 31/10/2005 | Drawing issued | School building completed during March, 2014. Science Block work is in progress. |
| 4 | 6432 | C/o Science Lab. Govt., Sr. Sec. School (Girls)at Rampur |  | No. /13-14-10005-07, dated: 9/9/13 & No. 07-1246-47, dated: 24/04/2007 | No. / 2703-06, dated: 08/11/2013 | No. EDN-H(9)-1/2006 Sc. Lab, DHE. Dated: 30/11/2013 | No. / 06-23130, dated: 12/03/2007 | Working drawing along with specification issued vide letter no 4404-06 dated 4/3/2017 Colour Scheme issued vide letter issued vide letter no 3237-39 dated 28/11/2017 | Work is near completion. |
| 5 | 6432 | Govt. Sr. Sec. School Taklech |  |  |  | EDN-H (9)3-18 /2008 dated 29-3-2017 |  | Layout plan ,working drawing along with specification issued vide letter no 4619-22 dated 18/3/2017 | Multipurpose hall work is in progress. |
| 6 | 6432 | C/o Govt. Sr. Sec. School building at Babli |  |  |  |  |  | Drawing issued vide letter no 269-71 dated 29/4/2005 | Not pertain to this Circle |
| 7 | 6432 | C/O Govt Sr Sec Sechool Taklech in tehsil Rampur Distt Shimla |  | 3076-77 Dated 4/6/2016 |  | EDN-h (9)3-18/2008 dated 29-3-2017 |  |  | Multipurpose hall work is in progress |
| 8 | 6432 | C/o Govt Sr sec school Sholi Tehsil Rampur |  | 4805 dated 20/7/2017 |  |  |  |  | In sufficient funds available to start the work. |

LIST OF WORK, 11th  CIRCLE RAMPUR , KUMARSAIN Div.– EDUCATION

| Sr. NO. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 9 | 6432 | C/o Additional accommodation of Govt. High Sr. Sec. School bldg. at Chanewag | No.EDN-H (9)3-19/2018 26/ Revised requirement recived From E.E Shimla Letter No 24119-20 Dated 19/10/2015 | No. 12011-16150-51, dated: 03/01/2012 & No. 10701-02, dated: 05/09/2012 | No. 2322-25, dated: 13/09/2013 & No. 4131-34, dated: 04/02/2014 | No. E.D.N.-H (9)3-18/2008, DHE, dated: 16/06/2014 | No. / 2013-11231-32, dated: 19/10/2013 | Working drawing issued vide letter no 1174-76 dated 20/6/2014 | Not pertain to this Circle |
| 10 | 6432 | Govt. High School at Barubag, (Thenedar) |  | 16654-56 dated 23/12/2016 |  | EDN-H (9) 3-18/2008 dated 29/3/2017 |  | Letter issued for requirement vide letter no 3980-81 dated 30/12/2014 &2216-18 dated 19/8/2015 Layout plan ,working drawing along with specification issued vide letter no 4615-18 dated 18/3/2017 | Tender opened & under process. |
| 11 | 6432 | C/o Govt. High building at Bharaidi |  | No./ 2010-484-85, dated: 26/04/2010 |  |  |  |  | Not pertain to this Circle |
| 12 | 6432 | C/O (Newly Upgraded) Govt Sr Sec School Kotighat Tehsil Kumarsain |  | 2930-31 dated 27/6/2015 |  |  | Feasibility report received from E,E, Kumarsain vide letter no 17604-05 dated 10/3/2016 | Letter issued for requirement vide letter no 1949-52 dated 3/8/2015 Layout Plan ,working drawing along with specification issued vide letter no 4841-43 dated 4/2/2016 | A/A & E/S awaited. |
| 13 | 6432 | C/O Govt. Sr. Sec. school Baragaon Tehsil Kumarsain | No Shiksha –SS(Baragaon) /2016 dated 31/12/2016 | 17200-02 dated 6/1/2017 |  |  |  |  | RCC frame structure completed. Masonary work of ground & first floor has been completed. |

LIST OF WORK, 11th  CIRCLE RAMPUR , BHAWA NAGAR– EDUCATION

| Sr. NO. |  | Job No. | Name of Project | Date of Requirement received |  | Date of receiving site plan & details |  |  | Date of Sketch drawing issued |  | Date of approval |  | Date of feasibility |  | Status of project |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | 2 | 3 | 4 |  | 5 |  |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |
| 14 |  | 6432 | C/o Mini Stadium at Govt. High School Chhitkul |  |  | No. PW-BhNR-2014-15-326, dated: 22/04/2014 & No. 2013-14, 11408, dated: 07/02/2014 |  |  |  |  |  |  |  |  |  |  | Work is in progress |
| 15 |  | 6432 | C/o Govt. Sr. Sec. School at Rakchham |  |  |  |  |  |  |  |  |  | 4784 dated 1/9/2017 |  | W/Drg. Issued |  | Working estimate under preparation |
| 16 |  | 6432 | C/o Govt. High School Brua | 4616-17 dated 11/8/2016 |  | No. Brual/12-5640-41, dated: 21/09/2012 |  |  |  |  |  |  |  |  | W/Drg. Issued |  | Work completed |
| 17 |  | 6432 | C/o Sr. Sec. School building at Sapni | No. 252-255, dated: 05/03/2013 135-36 Dated 01/06 /2016 4618-19 dated 11/8/2016 |  | No. Sapni/ 12-5642-43, dt.21/09/12 |  |  |  |  | Approval Letter No EDN-H(9) 4-35/2010 Dated 9/3/2010 |  |  |  | Layout plan & working drawing issued vide letter no 5134-39 dated 27/2/2016 Revised working drawing issued |  | Tender under process of award. |
|  |  |  | ---do---- | No-GSSS,SAPNI(4) 2014/103 DATED 22/8/2015 Requirement received from Assistant Engineer. Dated 16-9-2015 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 |  | 6432 | C/O Govt Sr Sec School Building At Nigulsari |  |  | 5614 Dated 25/8/2015 Received From E.E. Bhabanagar |  |  |  |  |  |  |  |  | W/Drg. Issued |  | (10% work completed) Work is in progress. |
| 19 |  | 6432 | C/O Govt Sr Sec School Chagaon in distt Kinnaur HP |  |  | 3660 dated 8/7/2016 |  |  |  |  |  |  |  |  | W/drg issued |  | Tender under process |
| 20 |  | 6432 | C/O Govt High School Themgarang Tehsil Sangla Distt Kinnaur |  |  | 1828 dated 22/6/2017 |  |  |  |  |  |  | EDN-HE(9) 4-35 /2010 dated 24/8/2017 |  | W/Drg. Issued |  | Working estimate under preparation |
| 21 |  | 6432 | C/o Govt sr. sec. school at Chansu |  |  |  |  |  |  |  |  |  |  |  | W/Drg. Issued |  | Working estimate under preparation |
| 22 |  | 6432 | C/o Eakalvya model Residential school Nichar |  |  |  |  |  |  |  |  |  |  |  | Revised layout plan issued |  | Work is in progress. |
| 23 |  | 6432 | C/o Govt High School at Sangla Distt Kinnaur |  |  |  |  |  |  |  |  |  |  |  | 4787 dated 01/09/2017 |  | Funds not available |
| 24 |  | 6432 | C/o Govt sr. sec. school Chansu Distt Kinnaur |  |  |  |  |  |  |  |  |  |  |  | W/Drg. Issued |  | Working estimate under preparation |
| 25 |  | 6432 | C/o Govt sr. sec. school Kilba Distt Kinnaur |  |  |  |  |  |  |  |  |  |  |  | Detailed drawing of doors and windows issued vide letter no 2684-85 dated 4/10/2017 |  | Working estimate under preparation |
| # List of Works 11th circle Rampur (Kalpa Division ) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sr. No. | Job No. |  | Name of Project |  | Date of requirement received |  | Date of receiving site plan & details | Date of approval |  | Date of feasibility |  | Status of project |  | Remarks. |  |  |  |
| 1 | 2 |  | 3 |  | 4 |  | 5 | 6 |  | 7 |  | 8 |  | 9 |  |  |  |
| 26 | -do- |  | Playground at RIBBA |  |  |  | Site plan vide letter No.1106-10 dt.21.5.05 |  |  | Vide letter No.6-8 dt. 02.4.05 |  | W/drawings issued vide letter No.357-59 dt. 08.7.05 |  | On going work |  | Work yet not started. |  |
| 27 | -do- |  | C/O Permanent building for J.N.V. R/Peo,Kinnaur |  |  |  | Site plan (in duplicate) vide letter No.3031-35 dt.26.7.05 Site plan vide letter No.7542-43 dt.22.9.05 |  |  | Feasibility vide letter No. 7542-43 dt. 22.9.05 Approved structural drawing received E,E, (D) Shimla |  | W/drawings issued vide letter No.2939-40 dt.6.10.06 W/drawings of all blocks 218-20 dated 12/6/2017 |  | On going work |  | 6Nos. Ty-III qtrs completed. 2Nos. Dormitory completed. School building work is in progress. |  |
| 28 | -do- |  | Science block at Sr. Sec. School Pooh, Kinnaur |  |  |  | Site plan received vide letter No. 990-94 dt. 19.5.05 (in duplicate) |  |  |  |  |  |  | On going work |  | Work awarded to the contractor. |  |
| 29 | -do- |  | Govt. Sr. Sec. School at Pangi, Kinnaur |  | Requirements received vide letter No.(4)42/ 2007 dt.02.3.09 |  |  | Approval received vide letter No.5715-19 dt. 5.8.05 |  | Feasibility vide letter No.8932-37 dt. 01.10.09 |  | Layout plan & sketch drawings issued vide letter No.900-02 dt. 8.6.2009 Drawing issued vide letter no 4819-20 dated 31/3/2017 |  | On going work |  | Attic floor slab laid and masonry work is in progress. |  |
|  | 6432 |  | C/o Govt Sr. Sec. school at Kalpa |  |  |  |  |  |  |  |  |  |  | W/drg. Issued |  | On going work |  |
| 30 | -do- |  | Govt. Sr. Sec. School LIPPA (Kinnaur) |  | Requirements received vide letter No.6725-27 dt.2.3.09 by the Dy.Director Edu. Kinnaur |  | Site plan received vide letter No. 6777-79 dt. 24.10.08 | -do- |  |  |  | Layout plan & sketch drawings issued vide letter No.897-99 dt. 8.6.2009 |  | On going work |  | Masonry work completed and further work is in progress |  |
| 31 | -do- |  | Playground at Govt.Sr sec School at Rarang/High School Rarang. --Do—Govt Sr sec School Rarang |  | 166-170 dated 18/11/2016 No EDN-H (9) 5-3/2010 dated 25/11/2016 |  | Site plan vide letter No.3170 dt.10.7.08 (in continuation office letter No.6528-29 dt. 27.4.06) | Approval Received from Director Letter no EDN- HE(9) 4/35/2010 dated 27/12/2016 |  | 1658-60 dated 11-8-2016 2642-46 dated 4/8/2016 6108 dated24/11/2016 6100-01 Dated 24/11/2016 |  | Revised layout plan vide letter No.5968-70 dt.12.11.2009 Layout plan & Working drawing issued. |  | On going work |  | Leveling of ground & R/Wall is in progress. |  |
| 32 | -do- |  | High School at Hango, Kinnaur *----DO------ |  | Requirement received vide letter No.2603- 05 dt.18.3.13 |  | Site plan received vide letter No.15018-19 dt. 01.1.13 Site Plan received from E.E. Kalpa vide Letter No 6752-55 Dated9/11/2015 |  |  |  |  | Lay out Plan ,Working drawing, along with specification issued vide this office letter no 5542-44 dated 28/3/2016 *Supply the contour plan along with. Cross Section |  | On going work |  | Work is in progress. |  |
| 33 | -do- |  | New building to be constructed in GCPS |  | Requirement received vide letter No.2448- 50 dt.07.7.14 |  |  |  |  |  |  |  |  | On going work |  |  |  |
| 34 | -do- |  | High School building at Asrang, Kinnaur |  | Requirement received vide letter No. 15574-76 dt. 11.2.13 |  | Revised site plan received vide letter No.15016-17 dt.01.1.13 | Approval vide letter No.17877-78 dt.16.2.15 |  |  |  | Layout plan & Sketch drawings issued vide letter No.2306-08 dt. 27.8.14 Revised layout plan & sketch drgs. issued vide letter No.3122 dt. 01.11.14 Requirement for drawing Approved structural drawing received |  | On going work |  | Work is in progress. |  |
| 35 | -do- |  | Primary School & Middle School at Kalpa |  |  |  | Site plan received vide letter No.2781 dt. 19.6.14 |  |  | Feasibility report received from E.E.Kalpa vide letter no 9290-91 Dated 3/2/2016 |  | Layout plan & sketch drawings issued vide this office letter No.3042-44 dt. 05.12.14 Layout plan,working drawing & specification issued vide this office letter no 5191-92 dated 2/3/2016 |  | On going work |  | Middle school completed and primary School yet not started |  |
| 36 | -do- |  | Govt. Middle School, Vety. Disp. & Ayurvedic Disp. at Charang |  |  |  | Site plan received vide letter No. 17717 dt. 07.2.15 |  |  |  |  | Layout plan & sketch drawings issued vide letter No.803-05 dt.26.5.15 |  | On going work |  | Work awarded to the contractor. |  |
| 37 | 6432 |  | Jawahar Navodya Vidyalaya (JNV) R/Peo (School Bolck) |  |  |  | Site plan received vide letter No.2639-41 dt. 11.5.06 | Approval received vide letter No.87-NVS dt.8.9.06 |  | Feasibility received vide letter No.87-NVS(W) dt.6.6.06 Feasibility received. vide letter No. 4041-42 dt. 7.7.06 |  | Sketch drawings issued& W/drawings & layout plan issued vide letter No.2210-11 dt.23.8.06 Layout Plan, working drawing specification issued |  | On going work |  | School building work is in progress |  |
| 38 | -do- |  | J.N.V. Gurukul Awas Yojna at Nako(Kennard) |  |  |  | Site plan received vide letter No.5959-63 dt. 20.11.05 |  |  |  |  | Layout plan & w/drawings issued vide letter No.354-56 dt. 4.5.06 |  | On going work |  | Not pertain |  |
| 39 | -do- |  | Jawahar Navodays Vidyalaya R/Peo (School block & Type-III) |  |  |  |  |  |  |  |  | Detail of door & windows drawings issued vide letter No.709-10 dt.24.5.12 |  | On going work |  | 6Nos. Ty-III qtrs completed. |  |
| 40 | -do- --do-- |  | Jawahar Navodays Vidyalaya (Hostel Block) (Dormitories RCC beds C/O MP. Hall |  |  |  |  |  |  | 678-80 dated 16/12/2016 6534-36 dated 7/12/2016 |  | Issued vide letter No. 1631-33 dt.22.7.13 Drawings issued vide letter no.1979-81 dt. 22.8.13 Approved structural drawing received Letter recived from E.E. Kalpa |  | On going work |  | 6Nos. Ty-III qtrs completed. 2Nos. Dormitory completed. 1No. is in progress |  |
| 41 | 6432 |  | C/O Govt Sr Sec School Brooa |  |  |  |  |  |  |  |  | Received From Principal Lett er no 124-dated 3/12/2015. |  | On going work |  | Drawing awaited. |  |
| 42 | 6432 |  | C/O School /Play field cum Basket ball court at Kanam and Science Block |  |  |  |  |  |  | 769-70 dated 4-6-2016 |  | Drawing issued for Approval & Feasibilityvide letter no 6540 dated 16/2/2017 |  | On going work |  | Work is in progress. |  |
|  |  |  |  |  |  |  | Education Bhabanagar Division (Karcham ) |  |  |  |  |  |  |  |  |  |  |
| Sr. NO. | Job No. |  | Name of Project |  | Date of Requirement received |  | Date of receiving site plan & details | Date of Sketch drawing issued |  | Date of approval |  | Date of feasibility |  | Status of project |  | Remarks |  |
| 1 | 2 |  | 3 |  | 4 |  | 5 | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  |
| 43 | 6432 |  | C/o Govt. Sr. Sec. School at Rakchham |  |  |  | Contour site plan recived E.E. Karcham letter no 9288 dated 11/1/2017 |  |  | EDN-HE (9) 4-35 dated 2/5/2017 |  |  |  | Layout plan working drawing along with specification issued vide letter no 156-58 dated 18/4/2017 |  | Drawings are being revised as per revised requirement. |  |
| 44 | 6432 |  | C/o Govt. High School Brua |  | 4616-17 dated 11/8/2016 |  | No. Brua/12-5640-41, dated: 21/09/2012 5622 dated 17/9/2016 |  |  | EDN-H (9) 4-35/2010 dated 6/1/2017 |  | Feasibility report received E.E.Karchh am Letter no 9466-68 dated 13/1/2017 |  | Layout plan ,Working drawing & Specification issued vide letter no 3376-78dated 19/12/2016 |  | Working estimate under preparation. |  |
| 45 | 6432 |  | C/o Sr. Sec. School building at Sapni |  | No. 252-255, dated: 05/03/2013 135-36 Dated 01/06 /2016 4618-19 dated 11/8/2016 |  | No. Sapni/ 12-5642-43, dt.21/09/12 |  |  | Approval Letter No EDN-H(9) 4-35/2010 Dated 9/3/2010 No EDN HE (9)4-35/2010 dated 17/11/2016 |  |  |  | Layout plan & working drawing and specification issued vide Layout plan working drawing alongwith specification issied vide letter no 303-05 dated 25/4/2016 |  | Work under award. |  |
|  |  |  | ---do---- |  | No-GSSS,SAPNI(4) 2014/103 DATED 22/8/2015 Requirement recived from Assistant Engineer. Dated 16-9-2015 |  |  |  |  |  |  |  |  |  |  |  |  |
| 46 | 6432 |  | Rashtriya Madhyamik Shiksha Abiyan |  |  |  |  |  |  |  |  |  |  |  |  | On going work |  |
| 47 | 6432 |  | Eklavya Model School at Nichar ----d0--- |  |  |  | ----d0---- |  |  |  |  | ---do--- Feasibility received 111 dated 6/4/2017 |  | Drawing issued vide letter no 4806-08dated 6/2/2007 Colour Scheme issued vide letter no 5935 dated 31-8-2015 |  | Work is in progress |  |
| 48 | 6432 |  | Govt. High School building Chansu |  |  |  |  |  |  | EDN-HE (9) 4-35/2010 dated 19/4/2017 |  |  |  | Layout plan ,working drawing along with specification issued vide letter no 4772-74 dated 30/3/2017 |  | Tender under process of award. |  |
| 49 | 6432 |  | C/O Govt Sr Sec School Building At Nigulsari |  |  |  | 5614 Dated 25/8/2015 Recivd From E.E. Bhabanagar |  |  |  |  |  |  |  |  | 10% work completed & further work is in progress. |  |
| 50 | 6432 |  | C/O Govt Sr Sec School Chaigaon in distt Kinnaur HP |  |  |  | 3660 dated 8/7/2016 |  |  |  |  |  |  |  |  | Revised A/A & E/S awaited. |  |
| 51 | 6432 |  | C/O Govt SR Sec School Chagaon Distt Kinnaur |  |  |  | 5620 dated 17/9/2016 | Approval No EDN-HE(9) 4-35/2010 dated 17/11/2016 |  |  |  |  |  | Layout plan & sketch drawing issued vide letter no 2489-91 dated 22/11/2016 Working drawing and Specification issued |  | Revised A/A & E/S awaited. |  |
| 52 | 6432 |  | C/O Govt Sr Sec School Kilba Distt kinnaur |  |  |  | 5621 dated 17/9/2016 |  |  | No EDN-HE (9)4-35/2010 dated 6/1/2017 |  |  |  | Layout plan ,Working drawing and specification issued vide letter no 3502-04 dated 28/12/2016 |  | On going work |  |
| 53 | 6432 |  | C/O Govt High School Building chansu Sangla Valley Kinnaur |  |  |  | 9288 dated 11/1/2017 |  |  |  |  |  |  | Layout plan ,working drawing along with specification issued vide letter no 4772-74 dated 30/3/2017 |  | Work under process of award. |  |
| 54 | 6432 |  | C/O Middle School Building at Yangpa -2 |  |  |  |  |  |  |  |  |  |  | Drawing issued vide letter no 4545-46 dated 16/3/2017 |  | On going work |  |
| 55 | 6432 |  | C/o Govt High School Building at Themgarang Tehsil Sangla Distt Kinnaur |  |  |  |  |  |  |  |  |  |  | Layout plan, working drawing along with specification issued vide letter no 1886-88 dated 8-8-2017 |  | On going work |  |

LIST OF WORK, 6th  CIRCLE KULLU – EDUCATION(OUTER SERAJ DIVISION)

| Sr. NO. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 56 | 6432 --Do-- | C/O Govt Sr sec School Anni (Science Lab) |  | No./05-26699, dated: 27/01/2006 &9098-9100 dated 16/11/2005 |  |  |  |  | 50% work completed. |
| 57 | 6432/6568 --Do- | C/O Science Block Govt Sr. Sec. School Khun Additional accommodation | No. EDN-KLU-GII build. (science) 2009-10-19509-11, dated: 08/03/2013 No EDN-HE (9) 1-2/2016 dated 5/8/2016 | No./2013-6693-95, dated: 23/07/2013 &17485-87 dated 13/1/2014 & 7238-39 dated 27/9/2016 | No. 4898-4901, dated: 25/03/2014 |  | No./2014-162-63, dated: 09/04/2014 | 4898-4901 dated 25/3/2014 & Drawing issued vide letter no 1875-78 dated 31/7/2014 | 80% work completed |
| 58 | 6568 | C/O Govt High School Jana Kullu |  |  |  |  |  | Letter recived from SA Mandi vide letter no 1188-93 dated 11/3/2016 | Not pertain to this Circle |
| 59 | 6568 | C/O Govt Sr Sec School Thirot Distt L&S |  |  |  |  |  | Working drawing &Specification issued SA Mandi vide letter no 1355-59 dated 20/1/2017 | Not pertain to this Circle |
| 60 | 6568 | C/O Govt Sr Sec S chool Udaipur Distt L&S |  |  |  |  |  | Layout plan & working drawing issued vide letter no 341-45 dated 24-6-2016 | Not pertain to this Circle |
| 61 | 6567 | C/O Science Block Govt Sr Sec School Dalash Distt Kullu | No EDN HE (9)1-2/2016 dated 5/8/2016 | 1673-75 dated 12/5/2016 |  |  |  | Layout plan working drawing & specification issued vide letter no 931-34 dated 15-6-2016 | 70% work completed. |
| 62 | 6567 | C/O Govt Sr Sec School Ladhagi Distt Kullu |  | 1676-78 dated 12/5/2016 |  |  |  | Working drawing along with specification issued vide letter no 1328-31 dated 15-7-2016 Revised working drawing issued vide letter no 2066-68 dated 17/9/2016 | Work is being executed by HUMDA. |
| 63 | 6567/6568 | C/O Govt Sr Sec School Baalyani Distt Kullu |  |  |  |  |  | Layout plan & working drawing along with specification issued SA Mandi vide letter no 497-502 dated 25/7/2016 | Not pertain to this Circle |
| 64 | 6568 | C/O Govt High School Hallan Distt Kullu | No EDN-H(9) 5-3/2010 dated 25-4-2016 |  |  |  |  | Layout plan & sketch drawing issued for Approval SA Mandi vide letter no 1526-30 dated 20/2/2017 | Not pertain to this Circle |
| 65 | 6568 | C/O Govt Sr Sec School Dughilag Distt Kinnaur | No EDN (9) 5-3/2010 dated 5-8-2016 |  |  |  |  |  | Not pertain to this Circle |
| 66 | 6568 | C/O Govt Sr Sec School Chowai Distt Kullu (Principal room, Staff room , office room and toilet) |  | 7059-61 dated 21/9/2016 & 7059-61 dated 21/10/2016 |  | No EDN-H(9)5-3/2010 dated 6/3/2017 No EDN-H (9) 5-3/2010 dated 6/3/2017 | 13834 dated 21/2/2017 | Layout plan , Working drawing & Specification issued vide letter no 3645-48 dated 7/1/2017 | Work awarded to the contractor. |
| 67 | 6568/6432 | C/o Govt Sr sec school Building Khunag Distt Kullu |  | 11791-93 dated 20/1/2017 |  |  |  | Layout plan and working drawing alongwith specification issued vide letter no 3097-3100 dated 15/11/2017 | Tender being called |
| 68 | 6568/6432 | C/O Govt Sr sec School Sarai Building at Trilokinath |  |  |  |  |  |  | Not pertain to this Circle |
| 69 | 6432 | C/o Govt Sr Sec School Samej Distt Kullu (Four Rooms) | EDN-HE (9) 1-2/2016 dated 5/8/2016 | 8587-88 dated 10/11/2016 & 1105-07 dated 6/5/2017 |  |  |  | Letter issued for requirement vide letter no 727-29 dated 30/5/2017 | Drawing awaited. |
| 70 | 6568/6432 | C/O Govt Sr Sec School Luhri | 439 dated 13/5/2016 | 2811-12 dated 3/6/2015 |  |  |  |  | Drawing awaited. |
| 71 | 6568/6432 | C/O Govt sr sec school Kalwari tehsil Banjar Distt Kullu |  |  |  |  |  | Layout Plan Working drawing issued vide letter no 1764-68dated 1/3/2017 | Not pertain to this Circle |
| 72 | 6568/6432 | C/o Govt Sr sec school at Bahang Distt Kullu HP |  |  |  |  |  |  | Not pertain to this Circle |
| 73 | 6568 | C/o Govt Sr sec school Raison Distt Kullu |  |  |  |  |  |  | Not pertain to this Circle |
| 74 | 6568 | C/O Govt High School Palchan Distt Kullu |  |  |  |  |  |  | Not pertain to this Circle |
| 75 | 6568 | C/ O Govt Sr sec School Digerh Tehsil Anni distt Kullu |  | 1322-23 Dated 15/5/2017 |  |  |  |  | Work could not be executed due to insufficient fund. |
| 76 | 6568/6432 | C/O Govt Sr sec school Kothi Distt Kullu | No EDN – HE (9) 1-2/2016 dated 5/8/2016 |  |  |  |  |  | Work could not be executed due to insufficient fund. |
|  |  | Science Lab Kibber |  |  |  |  |  |  | Frame structure competed & further work is in progress. |

List of Work Education 11th Circle Rampur

| Sr. No. | Job No. | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued | Date of approval | Date of feasibility | Status of project | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 77 | 8054 | C/o Govt. Degree College building at Kumarsain | No. EDN-H (9)4-63/2012 (Bldg) D.H.E., dated: 08, 2014 & EDN- H (9) 4-63/2012, DHE, dated: 02/2014 | No. 7649, dated: 30/09/2014 & No./ 2013-22613-14, dated: 19/02/2014 & No. 3220-21, dated: 10/07/2014 |  | EDN-HE (9) 3-18-2008(Drawing )Dated 23-11-2015 |  | Revised Layout plan & working drawing with specification issued vide this office letter no 5039-41 dated20/2/2016 | Footing work in basement floor is in progress. |
| 78 | 4556 | Govt. Degree college Rampur | No. EDN 130-133, dated: 06/05/2015 & No. EDN-c-2(B) 6-1371, dated: 01/09/2014 | No. / 06-2113-15, dated: 19/05/2006 & No. 1015-18183, dated: 25/03/2015 & No./ 07-5013-15, dated: 26/06/2007 | No. / 05-4367-70, dated: 16/01/2006 No. EDN.H.(9)3-8/2007(GC –Rampur) Dated 17-8-2015. |  | No. / 06- 22375, dated: 28/02/2006 & No./ 07-18303-04, dated: 04/03/2008 Feasibility Report Received from E.E.Rampur vide letter no 8357 Dated 3/9/2015 |  | 15% work completed. |
| 79. | 8046 | Govt. Degree College at Nankhari | No. EDN- H(9)330/2010, D.H.E., dated: 21/01/2014 | No. 21212-13, dated: 24/01/2014 | No./ 2013/-4039-42, dated: 30/01/2014 & No./ 14-2439-41, dated: 06/09/2014 | NO. EDN, (9) 3-18/08, DHE., dated: 01/10/2014 | No./14-240 40-42, dated: 04/03/2014 | Working drawing issued vide letter no 163-65 dated 13/4/2017 | 40% work completed. |

| List of Work Technical Education - 11th Circle Rampur |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No. | Job No. | Name of Project | Date of requirement received | Date of receiving site plan & details | Date of Sketch Drawing | Date of approval | Date of feasibility | Status of project | Remarks |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 80 | 7927 | I.T.I at Rongtong | STV(IT)HG(I)SNR- BLD/07/8135 dt.20.6.2009 from the Director of Tech. Edu. S/nagar Letter received regarding space provided for Plumber trade from Director Tech. Edu. S/nagar vide letter No.30381 dt.5.8.11 Letter received regarding area as per N.C.V.T. Norms vide letter No. 38679 dt.26.9.11 Revised requirements vide letter No.27680 dt. 13.05.13 from Director of Tech. Edu. S/nagar | Letter No. 8827 dt. 1.10.2008 cross sections & photographs received vide letter No.497- 99 dt.8.5.09 |  | Approval received letter No. 8284 dt. 29.2.12 received from Director Tech. Edu. S/nagar Approval received vide letter No. 11265 dt. 20.2.14 received from Director Tech. Edu. S/nagar | EE Kaza Divn. vide letter No. 5187-89 dt. 30.7.2011 Feasibility received vide letter No. 7943-45 dt. 24.9.13 as per revised proposal | Layout plan & sketch drawings issued vide letter No.1233-36 dated 25.06.2011 Drawings issued vide letter No.2356-58 dt. 27.8.2011 Revised sketch drawings issued vide letter No.3913-15 dt. 21.12.2011 Working drawings issued vide letter No. 2448-50 dt. 21.9.12 Revised sketch drawings issued vide letter No. 1663-68 dt. 25.7.13 W/drawings issued vide letter No. 5144-46 dt. 14.01.2015 | 35 % work completed. |
| 81 | 7927 | Govt. Polytechnic at Udaipur Distt.-L&P | Requirements received vide letter No. 18649-53 dt. 7.5.12 from Director of Tech. Edu. S/nagar Revised requirements vide letter No.49505 dt. 15.11.12 from Director of Tech. Edu. S/nagar Revised requirements vide letter No. 32002 dt. 6.6.13 | Site plan received vide letter No. 18649-53 dt. 7.5.12 |  | Approval received vide letter No. 75821 dt. 25.12.13 from Director Tech. Edu. S/nagar |  | Sketch drawings issued vide letter No. 2784-89 dt. 18.10.12 Revised sketch drawings issued vide letter No. 4575-80 dt. 15.2.13 Revised sketch drawings issued vide letter No. 3004-06 dt. 30.11.13 | Not pertain to this Circle |
| 82. | 4309 | Examination Hall cum Auditorium over shed for Motor Mechanic (under const.) for ITI at R/Peo | Requirements received vide letter No. 30198 dt. 26.10.06 from Director Tech. Edu. S/nagar | Letter received vide letter No. 10835-37 dt. 25.02.05 Letter received vide letter No. 15004-06 dt. 07.1.09 |  | Approval received vide letter No. 5363 dt. 19.2.09 reced. from Director Tech. Edu. S/nagar | Feasibility received from EE Kalpa vide letter No. 1929-30 dt. 21.5.10 | Letter to EE Kalpa regarding addition of addl. floor vide letter No.2236-38 dt. 22.9.2005 Sketch drawings issued vide letter No.4294-98 dt.10.2.09 W/drgs. issued No. 2726-29 dt.25.9.10 | 55% work completed |
| 83 | 4309 | C/O Work-shop building at ITI complex at R/Peo | Requirement received vide letter No.617-18 dt. 27.5.09 from Principal, ITI R/Peo | Site plan received vide letter No.978-81 dt.15.5.09 |  | Approval received vide letter No. 36083 dt. 10.12.09 from Director Tech. Edu. S/nagar | Feasibility received vide letter No. 13242-44 dt. 28.01.10 | Layout plan & sketch drawings issued vide letter No.3943-47 dt.9.12.09 Working drawings issued vide letter No. 7709-10 dt. 19.11.2011 | 85% work completed |
| (II) | -do- | Polytechnic at Kalpa | Requirement received vide letter No.41372 dt. 20.10.11 from Director Tech. Edu. S/nagar Letter received vide letter No.36940-43 dt. 21.08.12 from Director Tech. Edu. S/nagar | Site plan received vide letter No.7725-26 dt.19.11.11 |  | Approval received vide letter No. 32323 dt.18.07.13 from Director Tech. Edu. S/nagar Revised approval received vide letter No. 53169 dt. 24.12.2012 from Director Tech. Edu. S/nagar | Feasibility received vide letter No. 2872-75 dt. 05.06.12 Revised feasibility received vide letter No. 17681-83 dt. 19.03.2013 | Sketch drawings issued vide letter No.689-92 dt.22.05.12 Revised sketch drawings issued vide letter No.3335-37 dt.04.12.2012 | Yet not started |
| 84 | 7872 | C/o I.D.S.M.T. project at Narkanda |  |  | NO./ 12-1056-59, dated: 16/06/2014 & 27/08/2014 | No./ 2014-261 office N.P.N. | No./ 2014-3817, dated: 19/07/2014 | Drawing issued vide letter no 4052-54 dated 14/12/2006 & submitted drawing no 2006-4178 dated 18/7/2006 & issued no 1979-81 dated 7/8/2007 & working drawing no 2920-22 dated 28/9/2007 & working drawing issued vide letter no 3611-13 dated 3/12/2014 dated 9/4/2017 | Work is being awarded. |
| 85 | 8141 | C/O Mulitipurpose Complex at Thanadhar Distt Shimla | 2027-28 dated 11/5/2016 | Recived Site Plan From E, E, Kumarsain Vide Letter no 14825-26 Dated22/12/2015 |  |  |  |  | Site details submitted vide letter No. 2026-27 dated 11-5-2016. |
| 86 | 8128 | C/O I.T.I.Khadhan (Nankhri) Rampur Distt Shimla | NO STV (IT) H-G(1) 102065 dated 24/10/2016 | No PW-RMP-ITI –Kherahan/SP-1 dated 12/10/2015 |  |  |  | Layout Plan ,working drawing along with specification issued for approval vide letter no3111-15 dated 31/10/2015 &676-79 dated 27/5/2017 | 5% work completed |
| 87 |  | C/O Mahatma Gandhi Govt. Engineering College at Kotla |  |  |  |  |  |  | 5 % work completed |

Note :- Red portion shows  deposit works Which are not counted in Total Projects