**LIST OF WORK (OTHER) 14TH CIRCLE REST HOUSE AT ROHRU**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Status of Projects Supplied by SE.** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
|  |  |  |  |  |  |  |  |  |  |
| 1 |  | C/O additional accommodation to rest house Tikkar. |  |  |  |  |  | W/drgs & specifications A/W layout plan asready issued to EE, Rohru div. vide letter no 2479-81 dt. 16/09/2017 | Land available funds not available/ received from Govt. |

**REST HOUSE AT CHAMBI, CHOPAL**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | 7919 | Contour site plan for C/o P.W.D., rest House at Chambi, Teh., Chopal, Distt. Shimla, H.P. |  | No. / 08-2808-10, dated: 26/06/2008 |  |  | No. /08-5175-76, dated: 19/08/2008 | Layout plan & working drawing issued vide letter No./ 08-2016-19, dated: 06/08/2008 | Insufficient fund. |

**REST HOUSE AT DODRA KAWAR, ROHRU**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | 7788 | C/o Rest House at Dodra Kawar | Requirement & site plan received before 2005 | No. 2014-11902, dated: 28/03/2014 |  | Working drgs. Have been revised as RCC Framed Structure converted into load bearing structure. Vide let. No. 1486-88 dt. 23/07/16 | Work is in progress at present and completed upto sill level. |

**REST HOUSE AT MANDAL**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |

**SAINIK REST HOUSE AT ROHRU**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Remarks** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| 5 | 7866 | C/o Sainik Rest House at Rohru at Kh. No. 58/1 | Revised letter No. 1611, dated: 31/01/2012 | Revised site plan vide letter No. 5392-93, dated: 11/07/2007 | Sketch drawing issued vide letter No. 319-22, dated: 26/04/2013 |  |  | Letter issued regarding requirements on 26/05/2012 | Funds have not been received from the concerned deptt/ Govt. |
| 6 |  | C/O rest house at Kuttara, Tehsil, Rohru, distt. Shimla, HP. |  |  |  |  |  | Layout plan ,Working drawings alongwith specifications sent to EE, Rohru division vide letter no 2139-41 dated 26/08/2017 | Land is available. Tender has been fleeted which is to be opened on dated. 25.1.18 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10 | 7941 | C/O Vikas Bhawan at Kotkhai |  |  |  |  |  | Working drawings of roof plan supplied to EE Jubbal vide lt. no. 5086-88 dt. 25-02-2016 | 6th floor slab laid |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **List of Work (Other) Veterinary 14th Circle Rohru** | | | | | | | | | |
| **Sr. NO.** | **Job No.** | **Name of Project** | **Date of Requirement received** | **Date of receiving site plan & details** | **Date of Sketch drawing issued** | **Date of approval** | **Date of feasibility** | **Status of project** | **Remarks** |
| 11 | 6366 | C/o Veterinary Hospital at Kutara in Tehsil Rohru Distt Shimla |  |  |  |  |  | Layout plan, working drawing alongwith Specification issued Vide letter no 1416-19  dated 13/7/2017 | Land available tender called to be opened on 25.1.18. |
| 12 | 6366 | C/o Veterinary Hospital building at Chopal Tehsil Chopal Distt Shimla |  | 8102 dated 27/9/2017 |  |  |  | Layout plan, working drawing along with Specification issued Vide letter no 3543-44  dated 18/12/2017 | Deposit= 15.15 lacs AA&E/S=15.15 lacs Land is available . Tender is being called. |

**LIST OF WORK 14TH CIRCLE, ROHRU**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Remarks** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 13 | 3183 | C/o A.E. Residence at Rohru |  | No. 23053-54, dated: 28/03/2009 |  |  |  | Issued the drawing No.2518-20, dated: 12/10/2009 | Work is in progress. |
|  |  |  |  |  |  |  |  |  |  |
| 14 | 3183 | C/o A.E. office cum residence at Kotkhai |  |  |  |  |  | Issued the drawing No. 080-1594-95, dated: 28/07/2012 | Building roofed , masonry and plastering work completed. |
| 15 | 3183 | S.E residence and complex at Rohru, distt. Shimla |  |  |  |  |  | Specifications sent to EE, Rohroo Division vide letter no 2085-87 dated 19/09/16. | In progress Ist slab laid |
| 16 | 3183 | C/o AE office cum residence building at HPPWD, sub Division Nerwa. |  | Received from EE b&R div. HPPWD Chopal on dt. 22/08/16 vide lt. no 4172 |  |  |  | Layout plan, key plan& elevations being the standard working drgs. With specifications sent to EE, Chopal Div. vide letter no 3023-25 dated 26/11/2016. | Awarded 37 lacs Work is in progress. |
| 17 | 3183 | C/O A E Office & store at hatkoti, Jubbal distt. Shimla. |  |  |  |  |  | Layout plan & working drgs. with specificatiosns sent to EE, Jubbal Division vide letter no 2189-91 dt. 01/09/2017 | Work started recently |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **List of Work(Other)Stadium 14th Circle Rohru** | | | | | | | | | |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of Requirement received** | **Date of receiving site plan & details** | **Date of Sketch drawing issued** | **Date of approval** | **Date of feasibility** | **Status of project** | **Remarks** |
| 17 | 8165 | C/O Devta Khantu Stadium at Devidhar Tehsil Rohru Distt Shimla |  | 5524 dated 23-6-2016 |  |  |  |  | Counter site plan submitted to Chief Architect for preparation of Drawing. |

**List of Work Police & Mini Sectt. 14th Circle Rohroo**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Remarks** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
|  |  |  |  |  |  |  |  |  |  |
| 18 | 7506 | Standard design of Modern Police Post building | No. 31144, dated: 16/09/2006 |  |  |  |  | Issued the drawing No. / 06-3094-96, dated: 19/10/2006 | No funds received |
| 19 | 7506 | Contour site plan X-section for type I &II qtr at Police coloney Gangtoli in Teh. Rohru, Distt. Shimla, HP. |  | No. 4962, dated: 12/07/2006 |  |  |  | Issued the standard designs No. / 2010-4068-70, dated: 20/12/2010 | Type-I qtrs completed & type-II qtrs held up0to for want of funds. |

**Police Post Nerwa**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Remarks** |
| 20 | 4628 | C/o Police Station building with 2 Nos. Type-III qtr & 8 Nos. Type –II, qtr at Nerwa |  | Vide letter No. 7353-54, dated: 27/10/2006    No. 10614-15, dated: 16/01/2007 |  |  |  | Working drawing issued vide letter No. / 08-4544-46, dated: 18/02/2009 | Finishing work in Progress . |
| 21 | 4628 | C/O Police post building at Baghi, Kotkhai, Shimla, HP. |  |  |  |  |  | Revised layout plan supplied vide letter no 4225-27 vide letter no 18/02/2017 | Site not available |
| 22 | 4628 | C/o Police Post Kupvi with residence barracks mess dining & Two Nos. type-II, qtrs |  | Revised Site plan received vide letter No./ 08-5353-54, dated: 22/08/2008 |  |  |  | Standard working drawing issued vide letter No. / 05-2446-48, dated: 01/09/2007 | Site not available |
| 23 | 7957 | C/o Mini Sectt. Sub divisional level at Chopal | Still awaited | No. /3669-70, dated: 06/08/2009 |  |  |  | Letter issued for approval vide lt. no 4918-21 dt. 09/02/16 | Site not available |
| 24 | 7050 | C/O Tehsil building at Nerwa. |  | Vide letter no 7590 dated 07/12/2016 |  |  |  | Site plan referred back to The EE, Chopal for correction amendments vide letter no 3354-57 dt. 17/12/2016 | Counter site plan being submitted. |
| 25 | 8169 | C/O Vocational training centre & Hostel at Dodra-Kawar. |  |  |  | Vide letter No. SML-Mise(768)/95-134276 dated 29/03/2017 |  | Revised Working drawing(Hostel-II) sent to EE, Dodra Kawar vide letter no 4780 dated 30/03/2017 | Funds not received. |

**SDPOS RESIDENCE AT ROHRU.**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Remarks** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 26 | 7506 | C/o D.S.P. office cum Residence building at Rohru in Teh. Rohru, Distt. Shimla |  | No. 6501-03, dated: 02/09/2006 |  |  |  | Issued the drawing No. / 06-2626-30, dated: 14/09/2006 | Work completed. |
| 27 | 7506 | Standard design of Modern Police Post building | No. 31144, dated: 16/09/2006 |  |  |  |  | Issued the drawing No. / 06-3094-96, dated: 19/10/2006 | ….do… |
| 28 | 7506 | C/o Police Station and S.D.P.O. office cum Resident |  | No. /07-1, dated: 24/08/2007 |  |  |  | Colour scheme issued No. 3115-17, dated: 27/11/2008 | Finishing work in Progress |
|  |  |  |  |  |  |  |  |  |  |

**POLICE POST NERWA**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Requirement received** | **Receiving site plan & details** | **Sketch drawing issued** | **Approval vide letter No.** | **Feasibility vide letter No.** | **Status of project** | **Remarks** |
| 29 | 4628 | C/o Police Station building with 2 Nos. Type-III qtr & 8 Nos. Type –II, qtr at Nerwa |  | Vide letter No. 7353-54, dated: 27/10/2006  No. 10614-15, dated: 16/01/2007 |  |  |  | Working drawing issued vide letter No. / 08-4544-46, dated: 18/02/2009 | Site not available |
| 30 |  | C/O Police post building at Baghi, Kotkhai, Shimla, HP. |  |  |  |  |  | Layout plan& working drawing with specifications issued to EE, Jubbal division vide letter no 3642-44 dated 07/01/17  Revised layout plan supplied to EE, Jubbal division, vide letter no 4225-27 vide letter no 18/02/2017 | Site not available |
|  |  |  |  |  |  |  |  |  |  |
| 31 | 4628 | C/o Police Post Kupvi with residence barracks mess dining & Two Nos. type-II, qtrs |  | Vide letter No. / 08-5461-62, dated: 29/08/2008  Revised Site plan received vide letter No./ 08-5353-54, dated: 22/08/2008 |  |  |  | Standard working drawing issued vide letter No. / 05-2446-48, dated: 01/09/2007 | Site not available |
| 32 | 7957 | C/o Mini Sectt. Sub divisional level at Chopal | Still awaited | No. /3669-70, dated: 06/08/2009 |  |  |  | Letter issued for approval vide lt. no 4918-21 dt. 09/02/16 | Site not available |
| 33 | 7050 | C/O Tehsil building at Nerwa. |  | Vide letter no 7590 dated 07/12/2016 |  |  |  | Site plan referred back to EE, Chopal for Correction Amendments vide letter no 3354-57 dt. 17/12/2016 | Site not available |
| 34 | 8169 | C/O Vocational training centre & Hostel at Dodra-Kawar. |  |  |  | Vide letter No. SML-Mise(768)/95-134276 dated 29/03/2017 |  | Layout plan, working drawings alongwith specification issued to DC, Shimla vide letter no 4366-69 dated 01/03/2017  Layout plan,Working drgs. With Specification supplied to DC. Shimla vide letter no 4366-69 dated 01-03-2017  Revised Working drawing(Hostel-II) sent to EE, Dodra Kawar vide letter no 4780 dated 30/03/2017 | A/A& E/S awaited. |

Note :- Red portion shows deposit works Which are not counted in Total Projects