**LIST OR WORK(Other) Police,Home Guard, & fire Brigade 3RD CIRCLE**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval**  | **Date of feasibility** | **Status of project** | **Status of Projects Supplied by SE.**  |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** |
|  |
| 1 | 3393 | Police Barrack Solan | From S.P. Solan on dt. 06.03.14 | on dated 3.3.14 From E.E |  |  | Layout plan a/w w/drgs. Issued on 15.4.14 | Tenders to be invited. |
| 2 | 3339 | C/O 3 Nos Barracks at Police Line Solan.  | Vide letter no 4574 dated 01/02/2017 | Vide letter no 11092-94 dated 26/11/2016  | Vide letter no20823 dated 08/05/2017 | Vide letter no 2900-01 dated 27/05/2017 | Layoutplan,Working drawing alongwith specification sent to SP. Solan vide letter no 4792-95 dated 30/03/2017 | --do-- |
| 3 | 3393 | Police Station building SV & ACB Solan | From I.G office Police Solan on dt. 23.05.14 | Site plan recd. on 3.3.14Vide letter no 13494-96 dt. 16/12/17 | Addl. Director on 2.7.14 | Still awaited | Layout plan & sketch drgs. Issued on dt. 19.06.14 | Site plan submitted |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4 | 8084 | Fire Station Baddi |  |  |  |  | Letter issued to E.E. on dt. 27.02.15\* Reminder issued on dt. 23.03.15 | No budget |
| 5 | 3393 | C/O Kennels including accommodation f or dog handler/Asttt. Dog handler at Police line solan. Contoured site plan thereof.  |  | Vide letter no 10081-83 dated 08/11/2016. | Vide letter no54387 dt. 15/11/2017 | -Vide letter no 13349-50 dt. 13/12/17 | Sketch drgs. issued to Dy. SP (HQ) Police Estate Officer Solan vide letter no 2989-93 dt. 06/11/2017 | Drawing awaited  |
|  |  |  |  |  |  |  |  |  |
| 6 |  | Reg. Proposal for the C/O Homeguard building at Bill(Kunihar) tehsil Arki distt. Solan(HP).  |  | Vide letter no 19442-44 dated 11/01/2017. |  |  | Layout plan w/drgs. with specification sent to EE,vide letter no 3242-45 on 28/11/17 | Funds not available |
| 7 |  | C/O Home Guard 11/6 Company building at Darlaghat distt. Solan. |  |  |  |  | Layout plan ,W/Drgs. issued on 04/02/17Layout plan W/drawings issued to The Commandent Home Guard, 11th battalion Solan. Vide letter no 3450-53 dt. 08/12/2017 | --do-- |
| 8 | 7965 | Home Guard 11/4 Company Solan.  |  | Vide letter no 12291-92 dt. 17/10/2017 |  |  | Layout plan &Working drgs, issued vide letter no 5269-72 | --do-- |
| 9 | 6371 | C/O Admin. Block Modernization of Police force scheme at Kishanpura Baddi.  | Vide letter no 32190 dt. 01/10/14 | Vide letter no 6275-78 dt. 26/03/2015 |  |  | Working drgs. a/w specification issued to SP, Baddi,Distt Solan vide letter no 4702-05 dt. 23/01/2016 | Work in progress |
| 10 | 6371 | C/O Barracks for ladies constable(34 No. )& barracks for NGO,s(34 no,) Under modernization of Police force kisanpura, Tehsil Baddi.  |  |  |  |  | Revised layout plan, Working drgs. a/w specification issued to SP, Baddi vide letter no 634-37 dt. 25/05/2017 | B.S.N.L. is executing the work. |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| a |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |
| **LIST OF WORK OTHER(VETINARY ) 3RD CIRCLE SOLAN** |
| **Sr. Ni o** | **Job No.** | **Name of Project** | **Date of requirement received** | Date of receiving site plan & details | **Date of approval**  | **Date of feasibility** | **Status of project** | **Remarks.** |
|  |  |  |  |  |  |  |  |  |
| 11 | 6526 | C/O Veterinary Dispansary at Badlayana Solan | ----------- | --------------- | ---------------- | ----------------- | -------------- | Not taken up yet. |

|  |
| --- |
| **List of Work(Other) Rest House 3rd Circle Solan** |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval**  | **Date of feasibility** | **Status of project** | **Remarks.** | **New/Completed** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** |  |
| 12 | 3010 | Circuit House Chambaghat Solan | E.E. Solan on 14.10.13 | From E.E. on dated 14.10.13 |  | From E.E.dated 21.5.14From EE, Solan Div. vide letter 8830-33 dated 13/10/2016. | Layout plan a/w w/drgs. Issued on 22.1.15Revised drawings alongwith specifications supplied to EE, Solan Div. Vide letter no 3094-96 dated 03/12/2016. | Drgs. Duly Approved except AC System sent to EE, Electrical division NO-1HPPWD, Shimla-9 vide letter no 4508-11 dated 10/03/2017 | Work is in progress |
| 13 | 8186 | Contour site plan of proposed rest house building at Diggal.  |  | Vide letter no 17506-07 dated 06/12/2016.Vide letter no 18418-19 dated 30/12/2016 |  | Vide letter no 13146 dt. 22/11/2017 | Layout plan, working drgs,alongwith specifications for Checking feasibility issued to EE, Nalagarh division vide letter no 4852-54 dt. 31/03/17 | EE, B&R division Nalagarh requested to supply two ,three cross sections vide letter no 3295-97 dated 15/12/16 | No provisions in buget yet |
| 14 | 7364 | Rest house at Sayri |  | Vide letter no 2798-2800 dt. 02/06/06. |  |  | Working drawing sent to EE. Arki div. vide letter no 791-92 on 26/05/16 |  | Work is in progress |
| 15 | 8199 | Proposal for the C/O rest house building at Bhumti tehsil Arki distt. Solan.  |  | Vide letter no 15620-21 dt. 21/12/2016 |  |  |  | EE, B&R division requested vide letter no 3775-78 dated 20-01-17 for Approval & requirement. | Not available in budget |
| 16 | 8225 | Proposed PWD rest house at haripur Sandoli(Under CM Announcemtnt) |  |  |  |  |  | EE, Nalagarh div. is requested to supply requirementvide letter no 2972-73 dt. 03/11/2017 | Not appearing in budget. |

|  |
| --- |
| **List of Work(Other) 3rd Solan Circle** |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval**  | **Date of feasibility** | **Status of project** | **Remarks.** |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 17 | 8039 | Rajsav Sadan at Solan | From D.C. on dt. 08.10.14 | From EE. Vide letter no 6006-08 dt. 17/08/15.From E.E. on dt. 30.10.14 |  |  From EE. Vide letter no 10897-98 dt. 04/12/15.From EE. Dt. 16-02-16 | Working drgs. Alongwith specifications issued to EE Solan B&R division HPPWD, Solan vide letter no 74-76 Dt. 05/04/2016 | Work awarded |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 18 | 8088 | Office accommodation for Treasury at Kuthar. |  | Vide letter No. 20671-74 dt. 10.12.14 from E.E. |  |  | Working drgs. alongwith specification sent to EE, B&R Div. Kasauli vide letter no 2998-3001 dt. 06/11/2017 | Working estimate being submitted for approval |
|  |  |  |  |  |  |  |  |  |
| 19 | 7783 | Working women hostel Baddi. |  | From E.E.on dt. 03.02.14 | From Director 06.01.12 |  | Layout plan & working drawings issued on dt. 10.12.10 | Approval not given till date. |
| 20 | 7152 | Reg. Proposal for the C/O Sub treasury office building Arki distt. Solan (HP) | Vide letter no.fin(TR)(3)(1)-1/81-VII dated 21/12/2016.  | From EE, Arki div. vide letter no 14964-66 dated 03/12/2016 |  |  | Detail of joinery sent to EE, Div. Arki vide letter no 3338-39 dt. 04/12/17 | Work awarded |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |