**List of Work (Other) 11th Circle Rampur**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. NO.  | Job No.  | Name of Project | Date of Requirement received | Date of receiving site plan & details | Date of Sketch drawing issued  | Date of approval | Date of feasibility  | Status of project  | Remarks |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| 1 | 7323 | C/O Shri Bhima Kali Templi Sarahan Tehsil Rampur Bushar  |  | 4820 dated 21-7-2017 |  |  |  |  | Work not executed by this department..  |
|  |  |  |  |  |  |  |  |  |  |
| 2 | 8190 | C/o Beautification of Nau nag Lake at GP. Sarpara (15/20) Tehsil Rampur  |  |  |  |  |  |  | Tender under process.  |
|  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |
| 3 | 7839 | C/O District Level Conference Bhawn at Reckong peo Kinnaur  |  |  |  |  |  |  | Finishing work is in progress. |
| 4 | 7870 | C/O parking at Chaura Gate  |  |  |  |  |  | Revised working drawing issued  | Revised contour site plan submitted to Chief Architect HPPWD Shimla |
|  |  |  |  |  |  |  |  |  |  |
| **List of Other Works 11th Circle Rampur**  |
| **Sr. No.**  | **Job No.**  | **Name of Project** | **Requirement received**  | **Receiving site plan & details** | **Approval vide letter No.**  | **Feasibility vide letter No.**  | **Status of project**  | **Remarks** |
| 5 | 8076 | C/O Proposed parking at Kalpa, Distt.-Kinnaur | Requirements received vide letter No.4599-4600 dt. 30.7.2014 | Site plan received vide letter No. 2787-88 dt. 19.6.2014 |  |  | Layout plan & sketch drgs. issued vide letter No.3960-63 dt. 29.12.2014 | Work is in progress |
| 6 | -do- | Proposed car parking at Pooh (Koro Labrang Colony) Distt.-Kinnaur.  |  | Site plan received vide letter No. 19338-40 dt. 21.3.2015 |  |  | Layout plan & sketch drawings issued vide letter No.1690-91 dt.20.7.2015  | Yet not started |
| 7 | 8076 | Submission of site plan for the parking place and public toilets at Chaura. Distt. Kinnaur(HP) |  | Vide letter no 7507 dated 11/11/2016Vide letter no 7507 dated 11/11/2016. |  |  |  | Revised contour site plan submitted to Chief Architect HPPWD Shimla |
|  |  |  |  |  |  |  |  |  |
| 8 | 8033 | Bus Stand at Pooh in Distt.-Kinnaur | Requirements received vide letter No.3490 dt. 27.8.2012 | Site plan received vide letter No.5220-23 dt.30.7.12 | Approval received vide letter No.1520506 dt.16.4.2014 | Feasibility received vide letter No. 9945-46 dt. 24.10.13 | W/drawings issued vide letter No.5782-85 dt.16.1.2015 | Yet not started |
| 9 | 8166 | C/O bus stand with rain shelter & Toilet block at Ribba in distt. Kinnaur(HP). |  |  |  | Vide letter no 4306-07 dated 21-09-16. | Layout plan and sketch drgs. Issued to EE,B&R div. Kalpa vide letter no 1870-72 dt. 31/08/16. | Work is in progress |
| 10 | 8073 | C/O bus stand at Nichar |  | Vide letter no.615-16 dt. 05/05/14 |  |  | Revised working drawing issued to EE, vide letter no 2553-54 dt. 20-09-2017Detailed drawings under preparation | Work is in progress |
| 11 | 6423 | Car parking at Kee Gompa at Kaza (L&S) | Requirements received vide letter No.Regd under the societies Act-XXI,1860 | Revised site plan received vide letter No.2152-55 dt.10.6.14 | Approval received vide letter No.3803-5 dt.17.12.14 | Feasibility received vide letter No.12638-39 dt.8.1.2015 | Revised w/drgs. & layout plan issued vide letter No.5317-18 dt.22.1.2015 | Plastering work completed and joinery work is in progress. |
|  |  |  |  |  |  |  |  |  |
| 12 | 7868 | C/o Shopping Complex at Bus Stand Anni Distt. Kullu.  |  |  |  |  | Letter No. 523-26, dated: 07.05.2016 Working drawing Drawings supplied to EE, Electrical division NO:II, Vide letter no 4297 dated 22/02/2017  | Yet not started due non availability of funds. |
| 13 | 7677 | Reg. C/O sub tehsil building Kotgarh.  |  |  | Vide letter no 132003 dated 16/11/2016 | Vide letter no 16014-15 dated 07/12/2016 | Revised working drawings alongwith specifications supplied to The Deputy Commissioner Distt. Shimla vide letter no 2612-16 dated 29/10/2016 | Footing work is in progress. |
| 14 | 7677 | C/O Combined office building at Kumarsain distt. Shimla(HP) | Vide letter no 6565 dt. 29 dec 2017 | Received vide letter no 16387-92 dated 17/12/2016. |  | Vide letter no 10546-47 dt. 16/11/2017 | EE, Kumarsain is requested to give complete details of the building alongwith dimension of the site vide letter no 3574-76 dated 04/01/17. | Detail estimate is under preparation. |
| 15 | 7677 | Contour site plan for the C/O Tehsildar residence at mooring in distt. Kinnaur HP.  |  | Vide letter no 9650-51 dated 06/03/2017 |  |  | Site data received on 2nd January 2018. Revised drawing under preparation.  | Yet not started |

|  |
| --- |
|  **List of Work (Other) Veterinary 11th Circle Rampur** |
| **Sr. No.** | **Job No.** | **Name of Project** | **Date of requirement received** | **Date of receiving site plan & details** | **Date of approval**  | **Date of feasibility** | **Status of project** | **Remarks** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** |
| 16 | 4474 | Office building of Asstt. Director, Animal Husbandry/Health & Breeding at R/Peo |  |  |  | Layout plan working drawing wall section & joinery detail issued vide letter no 4764-64 dated 21/2/2005  | Layout Plan Working drawing Wall section & Joinery detail issued vide letter no 4764 dated 21/2/2017 | Provision has been made in Kisan Bhawan Reckong Peo |
|  |  |  |  |  |  |  |  |  |
| 17 | -do- | Milk Chilling /Processing Plant at R/Peo |  | Site plan received vide letter No. 8934-37 dt. 10.10.2012 |  |  |  | Not started yet.  |
| 18 | -do- | Veterinary Disp. at Hango, Distt.-Kinnaur  |  | Site plan received vide letter No.9785-87 dt. 6.11.2009 |  |  |  | Not started yet. |
| 19 | -do- | Veterinary Hospital & staff residential bldg. at Spillow, Kinnaur |  | Site plan received vide letter No. 9785-87 dt.6.11.09 |  |  | Letter issued to EE Kalpa reg. requirements of acc. vide letter No.3430 dt. 7.12.2012 | Not started yet. |
| 20 | -do- | Veterinary Dispensary (pre-fabricated) at Charang | Requirements received vide letter No.5604 dt. 13.3.2014 | Site plan received vide letter No. 18071-73 dt. 13.3.2014 |  |  | Standard drg. 9 of job No.4145 issued for checking the feasibility vide letter No.2821-24 dt. 14.10.2014 | Work is in progress  |
| 21 | -do- | C/O Combined Middle School, Vety. Disp. & Ayurvedic Disp. at Charang |  | Site plan received vide letter No. 17727 dt. 7.2.2015  |  |  | Layout plan & sketch drgs. issued vide letter No.803-05 dt. 26.5.15 Layout Plan,and working drawing alongwith specification issued vide this office letter no 5355-57 dated15/3/2016  | Work is in progress |
| 22 | -do- | Veterinary Disp. at Spillo, Distt.-Kinnaur |  | Site plan received vide letter No. 19039-41 dt. 16.3.2015 |  |  |  | Not started yet. |
| 23 | -do- | Residential building for Asstt. Director of Animal Husbandry & Vety. Hospital at Kaza\*--do------- | Requirements received vide letter No.AHY-H(II)G1-35/14 dt. 16.4.2015 | Site plan received vide letter No. 8758-62 dt. 15.10.2013Revised site plan received vide letter No. 9959-62 dt. 20.9.2014 | Ar. P.S NEGI. Layout plana & Sketch Drawing Issue For Approval Vide Letter No 2146-50 Dated 21.8.2015  |  | Letter to the Director of Animal Husbandry reg. supply the detailed requirements of proposal vide letter No.6137-40 dt.19.3.2015 Working drawing issued vide this office letter no 5128-29 dated27/2/2016 | Tender opened and under process.  |
| 24 | -do- | C/O Vaterinary Dispensary alongwith Type-II residence of Vety. Pharmacist at Telangi, Distt.-Kinnaur. | Requirements received vide letter No.AHY-H(11)GI-19/76 Vety. Dt.6.12.2014 from Director Animal Husbandry | Site plan not receivedSite plan received vide letter No.1559-60 dt.25.5.2015 | No AHYE-H(11)G1-35/2015-16(TPC) Dated15-9-2015NO AHY-LSP-G(1)-10/82-1038 Dated10/9/2015 | 767-68 dated 4/6/2016 | Letter to E.E. Kalpa Division regarding supply the site plan alongwith cross sections etc. vide letter No.3885-88 dt.22.12.2014Letter to E.E. Kalpa Division regarding supply the site plan as per revenew paper & complete site data i.e. cross section, North point, road/path etc. vide letter No.1645-46 dt.17.7.2015Layout plan & drawing issued for Feasibility | Work is in progress |
| 25 | 4474 | C/O Veterinary Dispansary/Residence at Village Kothi,Duni Distt Kinnaur |  |  |  | 764-66 dated 4-6-2016 | Working drawing issued for Approval & Feasibility | Work is in progress |

|  |
| --- |
| **List of Work (Other) Stadium 11th Circle Rampur** |
| **Sr. No.**  | **Job No.**  | **Name of Project** | **Date of Requirement received** | **Date of receiving site plan & details** | **Date of approval** | **Date of feasibility**  | **Status of project**  | **Remarks** |
|  |  |  |  |  |  |  |  |  |
| 26 | 8152 | C/O ICE Skating Rink At Sangla  |  | Contour site plan ice skating rink at Sangla |  |  | Drawing issued  | Work is in progress.  |
| 27 | 8127 | C/O Sports Complex Dutt Nagar Rampur Bushar Distt Shimla |  |  10292 Dated 4/11/2015  1187 dated1/3/2016 |  | Letter received from Director Letter No 5394-95 dated 28/12/2016NO-2-107/15 YSS/1758 dated 26/4/2017 |  | Work is in progress. 60% work completed |
| 28 | 4573 | C/O Stadium at Virgarh Tehsil Kumarsain |  | Letter no. 14721-24 dated 18-12-2015 |  | 1157-58 Dated 28/4/2016 | Revised Working Drawing issued for feasibility & approval Vide letter no. 288-90 dated 23-4-2016 | Work of retaining wall is in progress. |
| 29 | 6376/ 7876 | C/o Museum Kamru Kila / Museum Kalpa  |  |  |  | NO Bhasni-1/2015 -7705 dated 3/8/217 | Working drawing & specification issued vide letter no 2192-94 dated 1/9/2017Layout plan ,working drawing along with specification issued vide letter no 3177-79 dated 23/11/2017  | Working estimate under preparation  |
| 30 | 8023 | C/o Multipurpose Stadium at Kuftu Tehsil Kumarsain Distt Shimla |  |  |  |  | Revised working drawing of pavilion & Ent. Gate issued  | NPV & CA desposited. Final approval awaited. |
| 31 | 8141 | C/o Multipurpose Complex at Thanadhar Tehsil Kumarsain Distt Shimla  |  | 14825-26 dated 22/12/2015 |  |  | Letter Issued for necessary site detail & photographs & requirement vide letter no 4697-98 dated 23/1/2016 | Site details submitted vide letter No. 2026-27 dated 11-5-2016. |

**LIST OF WORK (OTHER) REST HOUSE 11th Circle RAMPUR**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No.**  | **Job No.**  | **Name of Project** | **Requirement received**  | **Receiving site plan & details** | **Sketch drawing issued**  | **Approval vide letter No.**  | **Feasibility vide letter No.**  | **Status of project**  | **Remarks** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| 32 | 7600 | Reg. Proposed site for C/O PWD rest house building at baragaon.  |  | Vide letter no 5120-21 dt. 22/08/2017 |  |  |  | Layout plan,w/drgs. a/w specification sent to EE, Kumarsain div. vide letter no 3224-26 dt. 27/11/17 | A/A & E/S awaited |
| 33 | 8121 | C/o Sarai Bhawan at Nigulsari, Distt. Kinnaur |  |  |  |  |  | Letter No. 1402-03, dated: 20/07/2016 Working drawing, layout plan & specification send to E.E. Karchham Division, HP. PWD., Bhabanagar for f.n.a. | Site development wor is in progress. |
|  |  |  |  |  |  |  |  |  |  |
| 34 | -do- | Rest House at Leo |  |  |  |  | Feasibility received vide letter No.489 -90 dt. 30.04.2005 | Detail of stairs, toilets, kitchen, wardrobe, Luggage rack & store cabinet issued vide letter No.1136-37 dt.23.6.12 | Work is in progress. |
| 35 | -do- | Addition & Alteration of Rest House at Moorang  |  | Site plan received vide letter No.10178 dt. 20.01.05 & vide letter No.1016-19 dt.21.5.05 |  |  | Feasibility reced. vide letter No. 8572-73 dt. 3.12.07 | W/drgs. a/w specification & detail of cup-boards issued vide letter No.4950-52 dt.5.3.08 | Work is in progress |
| 36 | 7600 | Yatri Niwas at gram Panchayat at Lalung | Requirements received vide letter No. 11660-61 dt. 16.12.09 from Addl. Dy. Commissioner Spiti at kaza | Site plan received vide letter No. 2338-40 dt. 26.6.09 | Approval received vide letter No.8350-51 dt.28.3.11 from Addl. Dy. Commissioner Spiti at kaza | Feasibility received vide letter No.8350-51 dt.28.3.11 | W/drawings issued vide letter No.1675-77 dt.15.7.11 | Funds not available  |
| 37 | -do- | Rest House at Kanam (Addition & Alteration) | No.KNR-ITDP- Kalpa-69-71 dt. 7.4.12 from Dy. Commissioner, Kinnaur | Site plan received vide letter No.127 dt. 4.4.12 from EE Kalpa |  |  |  | W/drawings issued vide letter No.5441-43 dt. 2.2.15 | Work is in progress |
| 38 | -do- | Rest House at Sagnam. (Addl. accommodation) |  | Site plan received vide letter No. 9571-72 dt. 28.11.13from EE Kaza |  |  |  | Layout plan & working drawings (addl. accommodation a/w specification issued vide letter No.201-02 dt.18.4.15 | Funds not available |
| 39 | 7600 | Contour site plan for proposed rest house at Sarahan . Rampur Bsr. Distt. Shimla- |  | Vide letter no 14702 dated 09/01/2017. |  |  |  | EE, Rampur div. requested to SE, 11th Circle vide letter no 15312-15 dated 13/01/17 | Not started yet. |
| 40 | 7600 | C/O rest house at Deothi.  |  | Vide letter no 10079-80 dt. 21/10/2014 |  |  |  | Layout plan and Working drawing sent to EE, Rampur Division vide letter no 3635-37 dt. 02/12/15 | Work is in progress |
| 41 | 7600 | C/O rest house at Delath Tehsil,-Rampur Distt-Shimla,HP.  |  | Vide letter no 2599 dt. 03/06/17 |  |  |  | Layout plan and working drgs. with specifications sent to EE, Rampur Division vide letter no 2086-88 dt. 24/08/2017 | A/A & E/S awaited. Funds not available. |
| **List of Work (Other)Home Guard,Police & Civil Defence 11th Circle Rampur** |
| **Sr. No.**  | **Job No.**  | **Name of Project** | **Requirement received**  | **Receiving site plan & details** | **Approval vide letter No.**  | **Feasibility vide letter No.**  | **Status of project**  | **Remarks** |
| 42 | 8108 | C/O office cum residence and store for 2/4 company of Home guard at Kumarsain Distt. Shimla HP. |  | Vide letter no. 7886-89 dated 5/8/16 |  |  | Working drgs. & specifications A/W layoutplan already issued to EE, Kumar sain div. vide letter no 2475-78 dt. 16/09/2017 | Funds not available. |
| 43 | 8108 | C/O Fire post at kumarsain tehsil kumarsain distt. Shimla(HP) | Vide letter no 4486-89 dated 25/06/16. | Vide letter no 4486-89 dated 25/06/16 |  |  |  |  Funds not available  |
| 44 | 6093 | C/O duty room, store room, Garage etc. at R/peo distt. Kinnarur (HP) | Vide letter no 153-57 dated 23/01/2016 | Vide letter no 153-57 dated 23/01/2016 |  |  | Layout plan & Working drawings alongwith specifications sent to The Commandant Home Guards, Ist Bn. Kinnarur at R/Peo. Vide letter no 2884-87 dated 18/11/2016 | Working estimate approved & tender to be called. |
| 45 | 7343 | Police Check Post at Namgia, Distt.-Kinnaur |  | Site plan received vide letter No.3399-3401 dt. 18.7.07 | Approval received vide letter No. 1984-85 dt. 16.6.08 | Feasibility received vide letter No. 13082-84 dt. 26.2.08 |  W/drawings issued vide letter No. 3452-54 dt. 16.12.08 | Tender under process of award.  |
| 46 | 7343 | New Police Station building at Kaza |  | letter No. 20264-65 dt. 21.01.14 | vide letter No. 15494 dt. 18.6.14 | vide letter No. 2593-94 dt. 23.6.14 | W/drawings issued vide letter No.2437-38 dt. 6.02.14 | Ground floor completed. Tender called for first floor |
| 47 | 7343 | N.G.O’s Police Mess at Police Line at R/Peo | Vide letter No. 32121 dt.6.12.12Vide letter No.1730 dt. 20.01.14 | Revised site plan received vide letter No. 15799-15800 dt. 22.01.14 | Vide letter no 28730 dt. 05/12/2015 | Feasibility received vide letter No. 10423 dt.19.11.14 | Working drgs. issed to EE, kalpa vide letter no 4111-14 dt. 24/12/15. | Yet not started |
| 48 | 7343 | Garrage for vehicles for Police line/Police Station at R/Peo  |  | Site plan received vide letter No.235- 237 dt.10.4.13 |  |  | W/drawings issued vide letter No.6169-71 dt.20.3.15 | Yet not started |
| 49 | 7343 | C/O Vigilance building at R/Peo in distt. Kinnaur. (HP) | Vide letter no 3756-57 dt. 06/09/16. | Vide letter no 4884 dated 24/10/2016. |  |  | Layout plan, Working drawings alongwith specifications sent to SP, Sv&ACB Shimla -2 vide letter no 4847-51 dt. 31/03/17 | Yet not started |
|  |  |  |  |  |  |  |  |  |
| 50 | --do | C/O Police station Sangla.  |  |  |  |  | Layout plan ,Working drawings a/w specifications sent to EE, karchham div. vide letter no 3254-55 dt. 29/11/17 | Work is in progress |
|  |  |  |  |  |  |  |  |  |